## Sheet1
PID | TID | Date Entry | Hrs | Task Name | Project Name | Descr
6 | 5359 | 2015-02-12 15:01 | 2 | Administration Stuff | Self Task | Team building activity meeting with Jason
6 | 5359 | 2015-03-12 11:33 | 8 | Administration Stuff | Self Task | Getting new computer set up.
6 | 5359 | 2015-03-12 11:34 | 6 | Administration Stuff | Self Task | Finished up setting up new computer
6 | 5359 | 2015-06-10 16:28 | 4 | Administration Stuff | Self Task | Went through the procedure to update machine to AUTHZ. Had some questions that Dylan helped me out on.
6 | 5359 | 2015-06-10 16:30 | 4 | Administration Stuff | Self Task | My localhost was broken I made several attempts to fix it myself. But I had to contact Vivek for help. The problem I was seeing was a 503 "Service Unavailable" error on admin and ec. Vivek was able to determine that it was my IIS app pool somehow both admin and ec got turned off.
6 | 5359 | 2015-07-15 15:58 | 2 | Administration Stuff | Self Task | Farewell meeting for three student workers: Adam Thomas, Andrew Adams, and Herbie.
6 | 5359 | 2015-07-23 02:40 | 1 | Administration Stuff | Self Task | Computer updates.
6 | 5359 | 2015-09-10 14:39 | 1 | Administration Stuff | Self Task | Attempted to look for task because I am out of tasks.
6 | 5359 | 2015-09-10 14:40 | 5 | Administration Stuff | Self Task | Reviewed notes taken on ECFTP and WebPro Meeting
6 | 5359 | 2015-09-10 14:48 | 1 | Administration Stuff | Self Task | attempted to look for work again.
6 | 5359 | 2015-09-24 03:37 | 1 | Administration Stuff | Self Task | Talked to Dennis about Web Pro Meetings and we finally got the email listing working for us at EC
6 | 5359 | 2015-10-07 17:22 | 0.5 | Administration Stuff | Self Task | Dennis notified me the 515 was not attached to the email. Resent an email to him with 515 attached
6 | 5359 | 2015-11-06 12:18 | 2 | Administration Stuff | Self Task | Emailed task givers looking for work.
6 | 5359 | 2015-11-06 12:19 | 2 | Administration Stuff | Self Task | Waiting for tasks.
6 | 5359 | 2015-11-06 12:19 | 2 | Administration Stuff | Self Task | Emailed again looking for tasks.
6 | 5359 | 2015-11-18 17:10 | 1.5 | Administration Stuff | Self Task | Web Pro meeting: Presentation on Docker.
6 | 5359 | 2015-12-17 05:44 | 5 | Administration Stuff | Self Task | Began to look over what was said in the meeting and review what could be done style wise for Enlightenment Portal...I dont have a task for this or a queued task for this work, so i am logging it here.
6 | 5359 | 2015-12-17 05:55 | 8 | Administration Stuff | Self Task | again reviewed what i could do for the enlightenment portal. i worked a bit more on the images. I don't have a task for this or a queued task for this work, so i am logging it here.
6 | 5359 | 2015-12-17 05:56 | 8 | Administration Stuff | Self Task | I remembered there was a section that was going to need some layout changes on /reports and /reports/edit for enlightenment portal. I worked on this in anticipation. I don't have a task for this or a queued task for this work, so i am logging it here.
6 | 5359 | 2015-12-17 05:58 | 7 | Administration Stuff | Self Task | Damien uploaded code for the section I was preemptively working on. I worked to fix conflicts and restrucutre what he had scaffold. It was a bit of a mess and took me all day to fix it and make it look good. I also fixed the issues with smaller screen size changes.
6 | 5359 | 2016-02-17 16:11 | 4 | Administration Stuff | Self Task | Meeting with Dennis for Self Appraisal stuff. This was in response for switching supervisors from Dennis to Damien. Then worked from home waiting for new stuff.
6 | 5359 | 2016-02-24 13:25 | 1 | Administration Stuff | Self Task | EC Forum meeting
6 | 5359 | 2016-03-03 12:45 | 1 | Administration Stuff | Self Task | EC Forum meeting
6 | 5359 | 2016-03-17 13:09 | 3 | Administration Stuff | Self Task | Celebrated Pi Day with co-workers by hosting a Pie Day party.
6 | 5359 | 2016-03-17 13:30 | 3 | Administration Stuff | Self Task | Asked Dana and Damien for more work. They didn't have anything for me today. Damien said that he will have something for me tomorrow.
6 | 5359 | 2016-03-17 13:57 | 7 | Administration Stuff | Self Task | Didn't get any new task just yet. I spent most of the day looking into issues with mobile EC site. I am hoping to have something written up to present to a BA.
6 | 5359 | 2016-03-23 13:43 | 0.5 | Administration Stuff | Self Task | Meeting, Spring/Summer 2016 Outreach & Update meeting
6 | 5359 | 2016-04-20 17:14 | 8 | Administration Stuff | Self Task | Spent a good amount of the day looking for tasks from other BA's. I never heard back from them. I told Damien about this and he said that he will look for a task for me. I started to clean up my work machine a bit.
6 | 5359 | 2016-04-26 18:33 | 7 | Administration Stuff | Self Task | Finished my last task and was out looking for more tasks. In the mean time. I started to compile the found errors on EC mobile.
6 | 5359 | 2016-05-25 12:15 | 2 | Administration Stuff | Self Task | CSAC meeting
6 | 5435 | 2015-02-05 14:08 | 2 | Training | Self Task | Roles and Responsibilities test and review with Dennis
6 | 5435 | 2015-02-12 15:26 | 2 | Training | Self Task | Accessibility training
6 | 5435 | 2015-04-24 10:21 | 2 | Training | Self Task | Web Pro Meeting
6 | 5435 | 2015-06-10 16:38 | 1 | Training | Self Task | Webinar meeting: Front-end accessibility.
6 | 5435 | 2015-07-15 16:26 | 2 | Training | Self Task | Web Pro meeting: present NAU ITS Security web site and demo of Selenium IDE
6 | 5435 | 2015-07-15 16:31 | 5.5 | Training | Self Task | I finally got around to summarizing the June 25th Web Pro meeting in an email and sent this out to all of EC Tech Team. This took me some time because I verified the content of the email (verifying NAU ITS Security web site and Selenium IDE web site).
6 | 5435 | 2015-07-30 11:19 | 2 | Training | Self Task | looked into the upcoming Web Pro meeting. I knew that it would need to be in a different location but I didn't know where. I tracked down the head of the Web Pro meetings and asked him about today's meeting. He informed me that this month's meeting had been cancelled and I was placed on the mailing list for Web Pro. I then informed the rest of EC.
6 | 5435 | 2015-09-02 14:33 | 2 | Training | Self Task | Web Pro meeting
6 | 5435 | 2015-09-02 17:40 | 5 | Training | Self Task | Tested the viewing components of the EC public pages in Windows 10 through the Edge web browser. There are some issues i saw with G+ not working in Blog, Images that get dynamically re-sized smaller are looking bad, and some other issues that ares seen in the console logs but nothing ground breaking on the site, visually.
6 | 5435 | 2015-09-10 14:54 | 7 | Training | Self Task | worked with my tablet and home machine to look into Windows 10's Edge web browser. testing more of the admin pages.
6 | 5435 | 2015-09-10 14:58 | 3 | Training | Self Task | continued to look at Edge
6 | 5435 | 2015-09-24 03:42 | 1 | Training | Self Task | watched video of IT Pro meeting on last Friday
6 | 5435 | 2015-09-30 14:28 | 2 | Training | Self Task | Web Pro Meeting
6 | 5435 | 2016-03-29 18:48 | 2 | Training | Self Task | Web pro meeting
6 | 5435 | 2016-04-26 18:30 | 2 | Training | Self Task | Attended IT Pro meeting. learned more about IT centralization and moving.
6 | 5435 | 2016-05-04 17:24 | 2 | Training | Self Task | Web Pro Meeting: Damien presented on Accessibility and EC
6 | 5435 | 2016-05-31 17:56 | 2 | Training | Self Task | Web Pro meeting
311 | 28535 | 2015-01-21 17:51 | 0.1 | Testimonial widget: Make sure info is syncing correctly (Tal) | EC, Yuma, Yav, PL Widget Maintenance | got new tasks so I will final review this task and log time to the new ones. Task status changed from In Progress to Final Review.
311 | 28536 | 2015-01-21 17:52 | 0.1 | Testimonial widget: Stylize edit mode (Tal) | EC, Yuma, Yav, PL Widget Maintenance | got new tasks so I will final review this task and log time to the new ones. Task status changed from In Progress to Final Review.
311 | 28537 | 2015-01-21 17:52 | 0.1 | Testimonial widget: Stylize front end (Tal) | EC, Yuma, Yav, PL Widget Maintenance | got new tasks so I will final review this task and log time to the new ones. Task status changed from In Progress to Final Review.
299 | 28833 | 2015-01-21 18:52 | 2 | Planning Development Tasks and Architecture | State Regulatory Compliance | Meeting with Damien to discuss initial time estimates for front end tasks for Compliance
299 | 28833 | 2015-01-21 18:53 | 0.5 | Planning Development Tasks and Architecture | State Regulatory Compliance | Meeting with Damien to discuss initial time estimates for front end tasks for Compliance
299 | 28880 | 2015-02-05 14:16 | 6 | Set-up Search View | State Regulatory Compliance | Started to do this on my own to find the location and develop the MVC views myself. I unfortunately failed. Task status changed from Assigned to In Progress.
299 | 28880 | 2015-02-05 14:17 | 5 | Set-up Search View | State Regulatory Compliance | Brought in Damien to help develop the starting environment for MVC. However all code we made was not working at all.
299 | 28880 | 2015-02-05 14:22 | 6 | Set-up Search View | State Regulatory Compliance | Finally working with Sam and Damien and SW Adam we found out that the MVC in Visual studio has to be auto code generated in order to just to setup the environment. At the end of the day we have the environment all set up.
299 | 28880 | 2015-02-12 17:13 | 7 | Set-up Search View | State Regulatory Compliance | The environment is all setup, but ran into some issues with viewing a page and modifying the page. Damien helped me out and got it working. I was able to get a page started with basic html written to the page.
299 | 28880 | 2015-02-12 17:37 | 6 | Set-up Search View | State Regulatory Compliance | worked to get the toggling between two views on this page.
299 | 28880 | 2015-02-12 17:43 | 3 | Set-up Search View | State Regulatory Compliance | final bootstrap review. then merged and committed to dev. this was my first time with this new system and took extra precautions to make sure this was build successfully. emailed Kyle about how we should treat these types of task. as they do not need to go to prod; because it is not a full deliverable. I talked to Damien about this earlier and we came to this conclusion.
299 | 28880 | 2015-02-19 16:09 | 1 | Set-up Search View | State Regulatory Compliance | Kyle emailed me back with his response. He would have liked it to go to prod but differed to my discretion. I think it would be better to commit to dev until there is a deliverable. But with that Kyle is happy with the code. So I will move this task to final review. Task status changed from In Progress to Final Review.
299 | 28881 | 2015-02-19 18:06 | 5 | Create State table cell from state search | State Regulatory Compliance | started this task and got the simple structure down. Task status changed from Assigned to In Progress.
299 | 28881 | 2015-02-19 18:11 | 6 | Create State table cell from state search | State Regulatory Compliance | I tried get the structure down to have a two column with boot strap. but I could not figure out how to do the auto fill of one side then start filling the second column. Damien pointed me to Degree Search on EC and this showed how a webkit handles objects in a div to auto column-ized the content.
299 | 28881 | 2015-02-19 18:14 | 8 | Create State table cell from state search | State Regulatory Compliance | there was a meeting today with Kyle to update our current status of the tasks. I notified him that i will be needing some new mock-ups soon for the State Details page. I need some image stuff from the designers too. I then worked on a bit of the style and got it done.
299 | 28881 | 2015-02-26 16:32 | 2 | Create State table cell from state search | State Regulatory Compliance | Final go-over of styling and what I think is needed for later functionality. I think this is ready for testing.
299 | 28881 | 2015-03-12 11:40 | 1 | Create State table cell from state search | State Regulatory Compliance | Committed to dev.
299 | 28881 | 2015-03-12 11:43 | 0.1 | Create State table cell from state search | State Regulatory Compliance | Emailed Kyle to test. Task status changed from In Progress to In Testing.
299 | 28881 | 2015-03-12 11:46 | 0.5 | Create State table cell from state search | State Regulatory Compliance | Kyle approved. Moving task to final review Task status changed from In Testing to Final Review.
299 | 28882 | 2015-02-12 17:27 | 4 | create state filter section | State Regulatory Compliance | Without realizing it I started this task and forgot to assign it to myself. But starting to generate the scaffolding and the Bootstrap components I ran into some issues with the page recognizing some scripts. Task status changed from Assigned to In Progress.
299 | 28882 | 2015-02-12 17:35 | 4 | create state filter section | State Regulatory Compliance | fixed the issues with importing scripts. got the scaffolding and started the bootstrap stuff. I pretty much got this done. I realized at this point i missed the toggling between pages.
299 | 28882 | 2015-02-12 17:43 | 2.5 | create state filter section | State Regulatory Compliance | final bootstrap review. then merged and committed to dev.
299 | 28882 | 2015-02-19 16:10 | 1 | create state filter section | State Regulatory Compliance | I got a response back from Kyle. He is happy with the code. So I will move this task to final review. Task status changed from In Progress to Final Review.
299 | 28883 | 2015-04-29 18:06 | 7 | create state filter keyword method | State Regulatory Compliance | Had to confirm with Kyle that we are in fact going to search on state name. Damien had already contacted Jason and got this confirmation but i wanted a secondary opinion. I integrated the filter and this is done. I also did work on adding another option to State Search dropdown list; "In Progress". Lastly fixed an issue where someone didn't remove an extra space in razor to a data field. This was causing an issue. Task status changed from Assigned to In Progress.
299 | 28883 | 2015-04-29 18:07 | 1 | create state filter keyword method | State Regulatory Compliance | Merged all other tasks in addition to this one to test. Emailed Kyle to test. Task status changed from In Progress to In Testing.
299 | 28883 | 2015-05-06 15:10 | 0.1 | create state filter keyword method | State Regulatory Compliance | Kyle approved. Moving to final review. Task status changed from In Testing to Final Review.
299 | 28884 | 2015-04-23 12:47 | 6 | Filter Status Dropdown | State Regulatory Compliance | Began work on the javascript code. Task status changed from Assigned to In Progress.
299 | 28884 | 2015-04-23 13:07 | 2 | Filter Status Dropdown | State Regulatory Compliance | got this and the SARA partner all fixed.
299 | 28884 | 2015-04-29 17:46 | 8 | Filter Status Dropdown | State Regulatory Compliance | While working another task Damien helped me make that more efficient and better all around. But I had to rework this section for both State and Program search.
299 | 28884 | 2015-04-29 17:47 | 0.5 | Filter Status Dropdown | State Regulatory Compliance | Emailed Kyle to test Task status changed from In Progress to In Testing.
299 | 28884 | 2015-05-06 15:10 | 0.1 | Filter Status Dropdown | State Regulatory Compliance | Kyle approved. Moving to final review. Task status changed from In Testing to Final Review.
299 | 28885 | 2015-04-23 12:58 | 8 | Filter Sera Partner | State Regulatory Compliance | some logic errors got me on this and had a brain freeze on trying to integrate it with the drop down logic. Task status changed from Assigned to In Progress.
299 | 28885 | 2015-04-29 17:53 | 3 | Filter Sera Partner | State Regulatory Compliance | Earlier in the week Damien helped me write a more efficient filtering method. I finally got to incorporate the SARA Partner filtering into this method. So I need to touch on this again. But now it should be all done.
299 | 28885 | 2015-04-29 17:53 | 0.5 | Filter Sera Partner | State Regulatory Compliance | Emailed Kyle to test this. Task status changed from In Progress to In Testing.
299 | 28885 | 2015-05-06 15:09 | 0.1 | Filter Sera Partner | State Regulatory Compliance | Kyle approved. Moving to final review. Task status changed from In Testing to Final Review.
299 | 28886 | 2015-02-19 18:16 | 8 | Create Progrram table from program | State Regulatory Compliance | started work on this task. this was actually more complicated, code, wise than i expected. I wrestled with the structure just to have the toggling of the area blow it to show/hide. Task status changed from Assigned to In Progress.
299 | 28886 | 2015-02-19 18:17 | 8 | Create Progrram table from program | State Regulatory Compliance | I worked on the structure for the three tiles in the hidden area. I got the structure all done and got good work done on styling.
299 | 28886 | 2015-02-26 17:30 | 4 | Create Progrram table from program | State Regulatory Compliance | I began work on structuring the tiles in the three column area of the hidden div.
299 | 28886 | 2015-02-26 17:35 | 6 | Create Progrram table from program | State Regulatory Compliance | continued to style the tiles in the three column area. also had a quick meeting with Kyle to update him where i am at in the project.
299 | 28886 | 2015-02-26 17:38 | 8 | Create Progrram table from program | State Regulatory Compliance | I thought i had gotten this done but I found an issue with styling alternate row coloring. I had to restructure the tile again.
299 | 28886 | 2015-02-26 17:51 | 4 | Create Progrram table from program | State Regulatory Compliance | Got the structure down so that the alternate rows work with the smaller tiles. Then finished the overall styling. I think this might be ready for testing.
299 | 28886 | 2015-03-12 11:40 | 1 | Create Progrram table from program | State Regulatory Compliance | Committed to dev.
299 | 28886 | 2015-03-12 11:43 | 0.1 | Create Progrram table from program | State Regulatory Compliance | Emailed Kyle to test. Task status changed from In Progress to In Testing.
299 | 28886 | 2015-03-12 11:45 | 0.5 | Create Progrram table from program | State Regulatory Compliance | Kyle approved. Moving task to final review Task status changed from In Testing to Final Review.
299 | 28887 | 2015-04-23 12:25 | 0.1 | create expandable internship requirement and licensure section | State Regulatory Compliance | this is actually done a long time ago. i'm gonna move this task to final review. Task status changed from Assigned to Final Review.
299 | 28888 | 2015-02-12 17:39 | 4 | create program filter section | State Regulatory Compliance | started work on this view of the page. got the scaffolding and bootstrap stuff done. Task status changed from Assigned to In Progress.
299 | 28888 | 2015-02-12 17:44 | 2.5 | create program filter section | State Regulatory Compliance | final bootstrap review. then merged and committed to dev.
299 | 28888 | 2015-02-19 16:10 | 1 | create program filter section | State Regulatory Compliance | I got a response back from Kyle. He is happy with the code. So I will move this task to final review.
299 | 28888 | 2015-02-19 16:10 | 0.1 | create program filter section | State Regulatory Compliance | Task status changed from In Progress to Final Review.
299 | 28889 | 2015-04-29 17:58 | 5 | create program filter keyword method | State Regulatory Compliance | This is actually tricky for me. I am trying to figure out how to search on the substring of an attribute but still keep filtering. Task status changed from Assigned to In Progress.
299 | 28889 | 2015-04-29 17:59 | 8 | create program filter keyword method | State Regulatory Compliance | Damien was able to help me grasp this better and I figured out how to incorporate this into my existing filter method. had some hiccups with the correct jquery function but I got it.
299 | 28889 | 2015-04-29 18:00 | 0.5 | create program filter keyword method | State Regulatory Compliance | Emailed Kyle to test. Task status changed from In Progress to In Testing.
299 | 28889 | 2015-05-06 15:09 | 0.5 | create program filter keyword method | State Regulatory Compliance | Kyle approved. Moving to final review. Task status changed from In Testing to Final Review.
299 | 28890 | 2015-04-23 13:09 | 5 | create filter program level method | State Regulatory Compliance | started working on Javascript code for this Task status changed from Assigned to In Progress.
299 | 28890 | 2015-04-23 13:10 | 8 | create filter program level method | State Regulatory Compliance | There are some missing data missing from the comp for me to work off of. I asked around and found the information i needed. continued work on this. this is a bit more tricky than State search because of the multiple checkboxes.
299 | 28890 | 2015-04-29 17:48 | 3 | create filter program level method | State Regulatory Compliance | Worked to re-do the entire filtering section.
299 | 28890 | 2015-04-29 17:48 | 0.5 | create filter program level method | State Regulatory Compliance | Emailed Kyle to test. Task status changed from In Progress to In Testing.
299 | 28890 | 2015-05-06 15:09 | 0.5 | create filter program level method | State Regulatory Compliance | Kyle approved. Moving to final review. Task status changed from In Testing to Final Review.
299 | 28891 | 2015-04-23 13:08 | 0.1 | create program checkbox filters | State Regulatory Compliance | this was actually done a while back. I will move this task to final review. Task status changed from Assigned to Final Review.
299 | 28892 | 2015-02-26 17:56 | 4 | Create State Compliance Layout | State Regulatory Compliance | Had to do some meetings with designers as the layout for this page was changed. After we got that all sorted I was able to start the layout stuff. Task status changed from Assigned to In Progress.
299 | 28892 | 2015-03-05 18:38 | 4 | Create State Compliance Layout | State Regulatory Compliance | continued adding components to the page.
299 | 28892 | 2015-03-05 18:41 | 8 | Create State Compliance Layout | State Regulatory Compliance | finished up nav and page layout and started to add components to the page
299 | 28892 | 2015-03-12 11:41 | 1 | Create State Compliance Layout | State Regulatory Compliance | Committed to dev.
299 | 28892 | 2015-03-12 11:43 | 0.1 | Create State Compliance Layout | State Regulatory Compliance | Emailed Kyle to test. Task status changed from In Progress to In Testing.
299 | 28892 | 2015-03-12 11:45 | 0.5 | Create State Compliance Layout | State Regulatory Compliance | Kyle approved. Moving task to final review
299 | 28892 | 2015-03-12 11:45 | 0.1 | Create State Compliance Layout | State Regulatory Compliance | Task status changed from In Testing to Final Review.
299 | 28893 | 2015-03-12 11:52 | 6 | Scaffold view state tile | State Regulatory Compliance | I forgot to give myself a task to scaffold and bootstrap-ify the area below the stat title stuff. so i am adding that work to this task. Task status changed from Assigned to In Progress.
299 | 28893 | 2015-03-26 10:13 | 8 | Scaffold view state tile | State Regulatory Compliance | Worked on this task and got a good portion of this done. Later I found out I only did the "Group Tile" version. I then did the "regular tile" version. There is still somethings to get done to finish this up. I will pick this back up after the edit state is done.
299 | 28893 | 2015-04-02 11:37 | 7 | Scaffold view state tile | State Regulatory Compliance | picked this back up after getting like 90% of the edit view done. i added in the components that match up with the edit view. then started to do styling on both the viewstate and editstate.
299 | 28893 | 2015-04-09 03:17 | 2 | Scaffold view state tile | State Regulatory Compliance | Finished up the code and stylization.
299 | 28893 | 2015-04-09 03:18 | 1 | Scaffold view state tile | State Regulatory Compliance | Committed to dev and emailed Kyle to test. Task status changed from In Progress to In Testing.
299 | 28893 | 2015-04-09 17:15 | 0.1 | Scaffold view state tile | State Regulatory Compliance | Because a new task had me redesign the original source I am going to final review this task. Kyle never got back to me about this but the new one is in test. Task status changed from In Testing to Final Review.
299 | 28894 | 2015-03-26 10:14 | 8 | Scaffold edit state tile | State Regulatory Compliance | Started work in adding all the components and structure right now. Task status changed from Assigned to In Progress.
299 | 28894 | 2015-04-02 11:29 | 7 | Scaffold edit state tile | State Regulatory Compliance | Started work on the edit view of a regular tile. working mainly on scaffolding for the section again.
299 | 28894 | 2015-04-02 11:32 | 6 | Scaffold edit state tile | State Regulatory Compliance | Worked on adding input controls for the description, links, and notes.
299 | 28894 | 2015-04-02 11:34 | 7 | Scaffold edit state tile | State Regulatory Compliance | Had to ask a few questions about clarity of the structure of all the components. as all of it was spread out. I think I got majority of the edit stuff done.
299 | 28894 | 2015-04-09 03:15 | 2 | Scaffold edit state tile | State Regulatory Compliance | finished up the edit state and got the styling done.
299 | 28894 | 2015-04-09 03:16 | 1 | Scaffold edit state tile | State Regulatory Compliance | Committed to dev and email Kyle to test. Task status changed from In Progress to In Testing.
299 | 28894 | 2015-04-09 17:15 | 0.1 | Scaffold edit state tile | State Regulatory Compliance | Because a new task had me redesign the original source I am going to final review this task. Kyle never got back to me about this but the new one is in test. Task status changed from In Testing to Final Review.
299 | 28895 | 2015-04-16 10:55 | 7 | scaffold empty tile section | State Regulatory Compliance | created new section with two buttons. all done. Task status changed from Assigned to In Progress.
299 | 28895 | 2015-04-29 17:39 | 0.5 | scaffold empty tile section | State Regulatory Compliance | Emailed Kyle to test this Task status changed from In Progress to In Testing.
299 | 28895 | 2015-05-06 15:08 | 0.5 | scaffold empty tile section | State Regulatory Compliance | Kyle approved. Moving to final review. Task status changed from In Testing to Final Review.
299 | 28896 | 2015-05-06 17:49 | 8 | pull flag on state details | State Regulatory Compliance | had to wait a bit on this because I asked around on where i should get the flag images. I first tried to pull from free sources on the net but nothing really worked. I ended up pulling the images from wiki and placing them into a folder in the images folder. then asked Damien to provide me a better angular variable to pull the images from. Task status changed from Assigned to In Progress.
299 | 28896 | 2015-05-06 17:55 | 0.5 | pull flag on state details | State Regulatory Compliance | Presented this during the meeting and Kyle approved so I am moving this task to final review. Task status changed from In Progress to Final Review.
299 | 28897 | 2015-04-16 10:53 | 6 | skin additional approvals | State Regulatory Compliance | mainly copied code from search page. this should be done now.
299 | 28897 | 2015-04-16 11:01 | 6 | skin additional approvals | State Regulatory Compliance | I don't have another task for this work but I worked on a control to change the status of the State Approval. This is only bootstrap controls and visual stuff.
299 | 28897 | 2015-04-23 11:35 | 2 | skin additional approvals | State Regulatory Compliance | I updated my revisions and found a lot of conflicts. it took me a while to sort it all out.
299 | 28897 | 2015-04-29 17:37 | 0.5 | skin additional approvals | State Regulatory Compliance | Emailed Kyle to test this. Task status changed from In Progress to In Testing.
299 | 28897 | 2015-05-06 15:07 | 0.5 | skin additional approvals | State Regulatory Compliance | kyle approved moving to final review.
299 | 28897 | 2015-05-06 15:07 | 0.1 | skin additional approvals | State Regulatory Compliance | Task status changed from In Testing to Final Review.
299 | 28898 | 2015-05-06 17:35 | 4 | write javascript to filter selections | State Regulatory Compliance | Began work to filter on state search. pulling from angular data attributes and processing them into in the monolithic jquery function I created for checkbox filtering. Task status changed from Assigned to In Progress.
299 | 28898 | 2015-05-06 17:42 | 6 | write javascript to filter selections | State Regulatory Compliance | Finished up the jquery function alteration to filter by textfield entry. I then implemented it on state search. I then applied the code change to program search.
299 | 28898 | 2015-05-06 17:56 | 0.5 | write javascript to filter selections | State Regulatory Compliance | Presented this during our meeting. Kyle approved so I'm gonna place this in final review. Task status changed from In Progress to Final Review.
299 | 28898 | 2015-05-06 17:57 | 0.1 | write javascript to filter selections | State Regulatory Compliance | Task status changed from Final Review to Assigned.
299 | 28898 | 2015-05-06 17:57 | 0.1 | write javascript to filter selections | State Regulatory Compliance | Task status changed from Assigned to Final Review.
299 | 28899 | 2015-05-18 14:59 | 1 | finalize styling | State Regulatory Compliance | Jason emailed me and said that Dalasie will be picking up the review of Details page. Later I somewhat caught up with Dalasie and tried to explain how Details page worked. Task status changed from Assigned to In Progress.
299 | 28899 | 2015-05-18 15:26 | 8 | finalize styling | State Regulatory Compliance | Dalasie provided me the first round of changes. I noticed that he was using the Balsamic Wireframe as the final design. We had some miscommunication. I had to explain to him that I didn't have a final design from anyone. And the balsamic should only be used as a wireframe only; not end all, be all design. I then started the changes to the Details page.
299 | 28899 | 2015-05-20 15:05 | 4 | finalize styling | State Regulatory Compliance | Continued to work on stuff from Dalasie. He provided more input by adding two more drafts of what is to be done. I work on some of this today.
299 | 28899 | 2015-05-20 15:50 | 8 | finalize styling | State Regulatory Compliance | Finished what I could from Dalasie's list. Somethings I cannot do because I am waiting on some components from Damien.
299 | 28899 | 2015-05-20 16:06 | 0.1 | finalize styling | State Regulatory Compliance | Kyle is going to give Damien and I new tasks for the finishing of the project. So I will move this task to final review. Task status changed from In Progress to Final Review.
311 | 28910 | 2015-01-21 18:55 | 6 | Testimonial widget: person overlaps quote at some page widths | EC, Yuma, Yav, PL Widget Maintenance | I had originally committed all my current code for testimonial widget to dev and tested it to make sure it was good. After that I committed to test. Notified Amanda to test. Task status changed from Assigned to In Progress.
311 | 28910 | 2015-01-21 19:06 | 6 | Testimonial widget: person overlaps quote at some page widths | EC, Yuma, Yav, PL Widget Maintenance | looked into this task and messed around with changing css. the problem is much bigger than i thought and may lie in Dalasie code.
311 | 28910 | 2015-01-21 19:08 | 8 | Testimonial widget: person overlaps quote at some page widths | EC, Yuma, Yav, PL Widget Maintenance | worked it out that the css is working on the image to be an arbitrary size and grows as a percentage. This gets messed up as a widget when placed in the main area of the page. I brought up this issue with Jason and informed him the images i got from Dalasie will not work as we had originally planned them. He then got Joshua give me the right size images.
311 | 28910 | 2015-01-21 19:10 | 6 | Testimonial widget: person overlaps quote at some page widths | EC, Yuma, Yav, PL Widget Maintenance | The images that Joshua gave me are a bit off. Jason then personally gave me the images i needed. I then was able incorporate them into the code and got the page to work....i think. Well I then merged and committed the code to test. and notified Amanda to re-test. Task status changed from In Progress to In Testing.
311 | 28910 | 2015-01-28 18:57 | 8 | Testimonial widget: person overlaps quote at some page widths | EC, Yuma, Yav, PL Widget Maintenance | Amanda found some styling issues. This required a meeting with Jason to figure out how to move the image person to allow more room for larger quotes. Then I took the time to clean up CSS rules and ensure all forms of screen sizes looked good for widgets that had a person in them.
311 | 28910 | 2015-01-28 19:02 | 8 | Testimonial widget: person overlaps quote at some page widths | EC, Yuma, Yav, PL Widget Maintenance | Finished up styling for all version of widgets; without image, with video, etc. published to test and had Amanda test again. She approved then requested this code be migrated to Yuma and Yavapai. I then spent the rest of the day migrating this code to all version of Yuma and Yavapai (dev, test, and prod). Amanda has approved the EC version and I checked the Yuma and Yavapai testpages. So...I'm gonna move to final review. Task status changed from In Testing to Final Review.
311 | 28911 | 2015-01-21 18:58 | 6 | Testimonial widget: add padding to bottom of the 'person' version of the widget | EC, Yuma, Yav, PL Widget Maintenance | Amanda got back to me about testing and revealed to me the error present for this task and the other task i have. She then created these tasks for me. I then looked into this task and found a solution. I added a padding-bottom to the main area. Task status changed from Assigned to In Progress.
311 | 28911 | 2015-01-21 19:13 | 0.1 | Testimonial widget: add padding to bottom of the 'person' version of the widget | EC, Yuma, Yav, PL Widget Maintenance | committed to test Task status changed from In Progress to In Testing.
311 | 28911 | 2015-01-28 19:03 | 0.1 | Testimonial widget: add padding to bottom of the 'person' version of the widget | EC, Yuma, Yav, PL Widget Maintenance | Amanda approved EC version and I checked the Yuma and Yavapai testpages. So...I am going to go ahead and move to final review. Task status changed from In Testing to Final Review.
299 | 29233 | 2015-03-05 18:37 | 8 | Scaffold Nav bar (in conjunction with details page scaffolding) | State Regulatory Compliance | forgot i requested to have this task made. This is to be done in conjunction with general scaffolding. I attempted several types of solutions; one type was trying to maintain responsive-ness for the nav menu. in the end i had to go with a structure that keeps the nav menu as one size and the other side can be responsive. Task status changed from Assigned to In Progress.
299 | 29233 | 2015-03-12 11:41 | 1 | Scaffold Nav bar (in conjunction with details page scaffolding) | State Regulatory Compliance | Committed to dev.
299 | 29233 | 2015-03-12 11:42 | 1 | Scaffold Nav bar (in conjunction with details page scaffolding) | State Regulatory Compliance | Meeting with Kyle, Damien, Sam, and myself. Explained that these task are ready for testing. Later I emailed Kyle to test Task status changed from In Progress to In Testing.
299 | 29233 | 2015-03-12 11:44 | 0.1 | Scaffold Nav bar (in conjunction with details page scaffolding) | State Regulatory Compliance | Emailed Kyle to test.
299 | 29233 | 2015-03-12 11:44 | 0.5 | Scaffold Nav bar (in conjunction with details page scaffolding) | State Regulatory Compliance | Kyle approved. Moving task to final review Task status changed from In Testing to Final Review.
299 | 29234 | 2015-03-12 11:48 | 6 | Generate bootstrap component Nav bar | State Regulatory Compliance | began to start this task by adding in components Task status changed from Assigned to In Progress.
299 | 29234 | 2015-03-20 12:04 | 8 | Generate bootstrap component Nav bar | State Regulatory Compliance | I forgot to ask Kyle to make a new task for me and I need to generate time for reporting so I am logging the time here. I started work to add components and bootstrap stuff for the navigation bar on the right hand side. This will include stylization. Today was getting scaffolding down.
299 | 29234 | 2015-03-20 12:07 | 6 | Generate bootstrap component Nav bar | State Regulatory Compliance | Worked on Nav bar Side. worked on the scaffolding for the secondary level.
299 | 29234 | 2015-03-20 12:12 | 8 | Generate bootstrap component Nav bar | State Regulatory Compliance | worked on stylization and javascript component for clicking a button to expand secondary level.
299 | 29234 | 2015-03-20 12:13 | 8 | Generate bootstrap component Nav bar | State Regulatory Compliance | This took me too long but finally got the javascript portion done and now the nav bar can expand and collapse with style. this (sub) task is done.
299 | 29234 | 2015-03-26 09:23 | 0.1 | Generate bootstrap component Nav bar | State Regulatory Compliance | I got a new task but I think this stuff is done. I'm gonna final review this task and log new entries to the new task. Task status changed from In Progress to Final Review.
299 | 29235 | 2015-03-26 10:10 | 2 | Scaffold Group tile with Bootstrap components | State Regulatory Compliance | started this task but realize that this can't really done without the other components structure first. Task status changed from Assigned to In Progress.
299 | 29235 | 2015-04-09 03:19 | 2 | Scaffold Group tile with Bootstrap components | State Regulatory Compliance | Migrated code I did for Edit/View state and modify it to work the same as those ones.
299 | 29235 | 2015-04-09 03:20 | 2 | Scaffold Group tile with Bootstrap components | State Regulatory Compliance | Finished up the component stuff.
299 | 29235 | 2015-04-09 03:20 | 1 | Scaffold Group tile with Bootstrap components | State Regulatory Compliance | Committed to Dev and email Kyle to test. Task status changed from In Progress to In Testing.
299 | 29235 | 2015-04-09 17:15 | 0.1 | Scaffold Group tile with Bootstrap components | State Regulatory Compliance | Because a new task had me redesign the original source I am going to final review this task. Kyle never got back to me about this but the new one is in test. Task status changed from In Testing to Final Review.
299 | 29686 | 2015-03-26 09:41 | 1 | Nav Bar - Create bootstrap components and Toggle views | State Regulatory Compliance | emailed Kyle to test this task. Task status changed from Assigned to In Testing.
299 | 29686 | 2015-04-02 11:02 | 1 | Nav Bar - Create bootstrap components and Toggle views | State Regulatory Compliance | Kyle Approved. Moving task to final review. Task status changed from In Testing to Final Review.
299 | 29742 | 2015-05-06 17:58 | 4 | final styling with Jason | State Regulatory Compliance | Sent email to Jason to request final stylizing. Started on some styling on my own and stuff Kyle added. Task status changed from Assigned to In Progress.
299 | 29742 | 2015-05-06 18:00 | 6 | final styling with Jason | State Regulatory Compliance | Jason responded back and i started to implement his changes. This was all for state search only. I have not received changes for program search.
299 | 29742 | 2015-05-18 13:50 | 4 | final styling with Jason | State Regulatory Compliance | Continued with the list that Jason gave me to work on for search page. Last time worked on combining State and Program buttons into a single looking control. and began work on placing the 'X' into the search bar as a control. I started back up on that today. It took me sometime but was able to get the look and functionality down. I requested "Not Authorized" changed to "Unathorized".
299 | 29742 | 2015-05-18 13:53 | 8 | final styling with Jason | State Regulatory Compliance | Continued with Jason's list. Worked on new SARA Icon. the one that Jason provided seem to small and Kyle had requested the colored version. I just whipped up something on the fly and committed that. Moved on to changing width of State column sizes. I basically finished up the first list.
299 | 29742 | 2015-05-18 14:21 | 8 | final styling with Jason | State Regulatory Compliance | I attempted to look into some of the more complicated stuff from Jason's list. One of which was the use of a glyphicon that we currently do not have access to. Damien mentioned that he was going to upgrade bootstrap so we may have access to it later. I also worked on adding 'tooltips' to input controls on the details page.
299 | 29742 | 2015-05-18 14:35 | 7 | final styling with Jason | State Regulatory Compliance | Jason gave me a second list to work on for Search and Program pages. Worked on resizing textfields to the HR size. And worked on some responsive stuff that was requested.
299 | 29742 | 2015-05-18 14:57 | 5 | final styling with Jason | State Regulatory Compliance | Continued working on list 2 from Jason. I started to fix layout issues when resizing the screen.
299 | 29742 | 2015-05-18 15:11 | 5 | final styling with Jason | State Regulatory Compliance | Still working on Jason's second list. working on changing label font weight, adding in two column look to icon section so licensure and experiential doesn't look all over the place.
299 | 29742 | 2015-05-18 15:23 | 7 | final styling with Jason | State Regulatory Compliance | finished up Jason's second list. Well almost I still have new glyphicons to implement; but Damien has not updated Bootstrap.
299 | 29742 | 2015-05-20 16:06 | 0.1 | final styling with Jason | State Regulatory Compliance | Kyle is going to give Damien and I new tasks for the finishing of the project. So I will move this task to final review. Task status changed from In Progress to Final Review.
299 | 29744 | 2015-03-26 10:09 | 3 | style add new group tile | State Regulatory Compliance | started work on this button. it's pretty indepth. but i shifted gears after our meeting to work on another task Task status changed from Assigned to In Progress.
299 | 29744 | 2015-04-09 03:21 | 2 | style add new group tile | State Regulatory Compliance | finished up styling for group tile.
299 | 29744 | 2015-04-09 03:21 | 1 | style add new group tile | State Regulatory Compliance | Commited to Dev and email Kyle to test. Task status changed from In Progress to In Testing.
299 | 29744 | 2015-04-09 17:14 | 0.1 | style add new group tile | State Regulatory Compliance | Because a new task had me redesign the original source I am going to final review this task. Kyle never got back to me about this but the new one is in test. Task status changed from In Testing to Final Review.
299 | 29766 | 2015-03-26 09:24 | 1 | Meetings, conversations, etc | State Regulatory Compliance | Meeting with Damien and Sam. Basic review of what we have accomplished so far.
299 | 29766 | 2015-03-26 09:25 | 1 | Meetings, conversations, etc | State Regulatory Compliance | Meeting with Kyle, Damien, and Sam. This meeting was to catch up Kyle he was on vacation for a while.
299 | 29766 | 2015-03-26 09:31 | 1 | Meetings, conversations, etc | State Regulatory Compliance | First talked to Jason, then Damien, about design issues from the design doc. Then later Damien talked to Sam and I about this new task. We can now log meetings and conversations to this task.
299 | 29766 | 2015-04-02 09:36 | 0.5 | Meetings, conversations, etc | State Regulatory Compliance | quick meeting with Kyle
299 | 29766 | 2015-04-09 03:23 | 4 | Meetings, conversations, etc | State Regulatory Compliance | Talked to Damien and discussed what I should be work on next. Later Jason stopped by my desk and we discussed the interstices of the current design for Details Page. This lead to many more questions and clarifications on how the page was meant to be. This means that what I sent to be tested is not the fully correct version of what the page should be.
299 | 29766 | 2015-04-09 03:26 | 4 | Meetings, conversations, etc | State Regulatory Compliance | Had a meeting with Sam and Damien to review what we did. I brought up the conflicting designs I had with the design doc and actual code. Later Damien, Jason, and I sat down and we hashed out the details for how the Details page should be reworked to conform to what we want.
299 | 29766 | 2015-04-16 10:35 | 1 | Meetings, conversations, etc | State Regulatory Compliance | Meeting with Damien and Sam
299 | 29766 | 2015-04-23 13:11 | 1 | Meetings, conversations, etc | State Regulatory Compliance | Meeting with Kyle and Damien
299 | 29766 | 2015-04-29 17:29 | 1 | Meetings, conversations, etc | State Regulatory Compliance | Meeting with Sam, Damien, and Kyle
299 | 29766 | 2015-05-06 15:11 | 1 | Meetings, conversations, etc | State Regulatory Compliance | Meeting with Sam, Kyle, and Damien
299 | 29766 | 2015-05-14 14:19 | 1 | Meetings, conversations, etc | State Regulatory Compliance | Meeting with Kyle, Damien, and Sam
299 | 29766 | 2015-05-18 15:14 | 1 | Meetings, conversations, etc | State Regulatory Compliance | Meeting with Kyle, Sam, and Damien
299 | 29766 | 2015-05-27 16:32 | 1 | Meetings, conversations, etc | State Regulatory Compliance | Meeting with Damien, Kyle, and Sam. Kyle suggested that I (and Sam) can leave this project; Amanda was wanting to start her project. Damien will work with Dalasie to finish up the front end stuff. So I will go ahead and remove myself from this task.
299 | 29915 | 2015-04-09 09:57 | 4 | Details Page, View/Edit State redesign | State Regulatory Compliance | started work on redesigning the edit and view state. this includes pretty much removing the 'monolithic' edit tile view. and going for a edit in place design. Task status changed from Assigned to In Progress.
299 | 29915 | 2015-04-09 09:59 | 8 | Details Page, View/Edit State redesign | State Regulatory Compliance | continued to redesign the views. as i move components around I have to clean up the css classes. this actually helped me clean up the overall layout.
299 | 29915 | 2015-04-09 10:00 | 8 | Details Page, View/Edit State redesign | State Regulatory Compliance | finished up the edit/view states. Included simple jquery methods to show the overall goal.
299 | 29915 | 2015-04-09 10:19 | 1 | Details Page, View/Edit State redesign | State Regulatory Compliance | Committed to dev and emailed Kyle to test. Task status changed from In Progress to In Testing.
299 | 29915 | 2015-04-16 10:36 | 1 | Details Page, View/Edit State redesign | State Regulatory Compliance | Kyle approved the task moving this to final review. Task status changed from In Testing to Final Review.
349 | 30100 | 2015-06-03 16:48 | 8 | Learn how to use Git online for Talbert Tso | Programmer Trng/Develop | started and got through lesson 1 of the GIT stuff
349 | 30100 | 2015-07-01 13:44 | 7 | Learn how to use Git online for Talbert Tso | Programmer Trng/Develop | continued git lessons
349 | 30100 | 2015-07-23 02:45 | 3 | Learn how to use Git online for Talbert Tso | Programmer Trng/Develop | continued lessons.
349 | 30100 | 2015-07-23 02:46 | 8 | Learn how to use Git online for Talbert Tso | Programmer Trng/Develop | continued training.
349 | 30100 | 2015-08-20 12:07 | 4 | Learn how to use Git online for Talbert Tso | Programmer Trng/Develop | Went back and answered questions for reflections.txt
299 | 30121 | 2015-05-27 16:22 | 7 | Final Bug Fixes: Front-End | State Regulatory Compliance | Reviewed document provided again to see if I missed anything. Waiting on Dalasie about new stuff. Task status changed from Assigned to In Progress.
299 | 30121 | 2015-05-27 16:25 | 8 | Final Bug Fixes: Front-End | State Regulatory Compliance | Contacted Dalasie to see if he had new stuff for me. Still attempted little changes to the site for enhancements.
299 | 30121 | 2015-05-27 16:28 | 8 | Final Bug Fixes: Front-End | State Regulatory Compliance | Dalasie did not have a fully developed document for me to work on. But he was able to request some changes. It took me some time but I found a solution.
299 | 30121 | 2015-05-27 16:35 | 5 | Final Bug Fixes: Front-End | State Regulatory Compliance | Dalasie emailed Damien and I; he said he would have a doc for us for styling. I reviewed the page one last time. I then decided to commit what changes I have made. Damien then pushed this to test. We had our meeting and Kyle decided I can be let go from this project. And Damien will finish off styling. I will now move this task to final review. Task status changed from In Progress to Final Review.
86 | 30253 | 2015-05-27 16:38 | 2 | Review code | Admin Connect | Talked to Amanda about this task. Later Damien, Amanda, and I had a quick meeting to discuss the start of this project. We decided to do some code review first then meet again on Friday to flesh out the details of the project. I then pulled up the code to begin review. Task status changed from Assigned to In Progress.
86 | 30253 | 2015-06-03 16:30 | 6 | Review code | Admin Connect | Continued to review the code. I discovered that changing the front end controls and scaffolding is going to be easy. I am now trying to figure out the backend code stuff.
86 | 30253 | 2015-06-03 16:32 | 2 | Review code | Admin Connect | Found the files that integrate with front end. The code is heavily reliant on mustache js. Code wise I can foresee some time needed to learn mustache in depth.
86 | 30253 | 2015-06-03 16:50 | 6 | Review code | Admin Connect | finished reviewing the code. I believe I can confidently complete this task. Task status changed from In Progress to Final Review.
233 | 30274 | 2015-06-03 16:40 | 1 | 2014-2015 Annual Self-Appraisal from Talbert | Programming Staff Appraisals | Worked on updated SQL to pull all relevant TME logs to be used in this years self appraisal. Task status changed from Assigned to In Progress.
233 | 30274 | 2015-06-10 16:25 | 8 | 2014-2015 Annual Self-Appraisal from Talbert | Programming Staff Appraisals | worked to sort my data.
233 | 30274 | 2015-07-01 13:19 | 6 | 2014-2015 Annual Self-Appraisal from Talbert | Programming Staff Appraisals | Continued to work to sort the data.
233 | 30274 | 2015-07-01 13:20 | 8 | 2014-2015 Annual Self-Appraisal from Talbert | Programming Staff Appraisals | finished up sorting the data. begin to analyze the data.
233 | 30274 | 2015-07-01 13:32 | 8 | 2014-2015 Annual Self-Appraisal from Talbert | Programming Staff Appraisals | continue to mark my data as fitting to the specific goals.
233 | 30274 | 2015-07-15 15:56 | 7.5 | 2014-2015 Annual Self-Appraisal from Talbert | Programming Staff Appraisals | I have no active task at this moment so I worked on myself appraisal. However, I made a huge mistake by saving over some of my completed work with an earlier version and erased a good portion of my work. So I had to redo a lot of the work again.
233 | 30274 | 2015-07-23 02:47 | 6 | 2014-2015 Annual Self-Appraisal from Talbert | Programming Staff Appraisals | getting down to the wire so started back on this.
233 | 30274 | 2015-07-30 11:15 | 6 | 2014-2015 Annual Self-Appraisal from Talbert | Programming Staff Appraisals | continued work on data sorting
233 | 30274 | 2015-07-30 11:15 | 6 | 2014-2015 Annual Self-Appraisal from Talbert | Programming Staff Appraisals | finished data sorting
233 | 30274 | 2015-07-30 11:15 | 8 | 2014-2015 Annual Self-Appraisal from Talbert | Programming Staff Appraisals | started draft of word doc
233 | 30274 | 2015-07-30 11:16 | 8 | 2014-2015 Annual Self-Appraisal from Talbert | Programming Staff Appraisals | continued on word doc
233 | 30274 | 2015-07-30 11:16 | 8 | 2014-2015 Annual Self-Appraisal from Talbert | Programming Staff Appraisals | continued on word doc
233 | 30274 | 2015-08-06 13:16 | 4 | 2014-2015 Annual Self-Appraisal from Talbert | Programming Staff Appraisals | continued to work on.
233 | 30274 | 2015-08-06 13:17 | 6 | 2014-2015 Annual Self-Appraisal from Talbert | Programming Staff Appraisals | continued to work on
233 | 30274 | 2015-08-06 13:17 | 6 | 2014-2015 Annual Self-Appraisal from Talbert | Programming Staff Appraisals | continued to work on
233 | 30274 | 2015-08-13 17:10 | 5 | 2014-2015 Annual Self-Appraisal from Talbert | Programming Staff Appraisals | Worked on the document
233 | 30274 | 2015-08-13 17:11 | 6 | 2014-2015 Annual Self-Appraisal from Talbert | Programming Staff Appraisals | attempted to finish
233 | 30274 | 2015-08-13 17:13 | 8 | 2014-2015 Annual Self-Appraisal from Talbert | Programming Staff Appraisals | Had a meeting with Dennis to help me look over my Self Appraisal. After he looked at it he said that this was not the correct direction to be taking. He then super helped me figure a great way to breakdown the goals and and summary sections. I began to re-work my document.
233 | 30274 | 2015-08-13 17:14 | 4 | 2014-2015 Annual Self-Appraisal from Talbert | Programming Staff Appraisals | Sickness has really got me down and i was not able to do much work for this. but i tried.
233 | 30274 | 2015-08-13 17:17 | 8 | 2014-2015 Annual Self-Appraisal from Talbert | Programming Staff Appraisals | using Dennis' outline for how to write for a Self Appraisal has made writing the document much easier and faster. I know now that I have been doing my self appraisal wrong.
233 | 30274 | 2015-08-20 12:05 | 8 | 2014-2015 Annual Self-Appraisal from Talbert | Programming Staff Appraisals | Worked with Dennis to finish up the document. Got it signed and turned in.
233 | 30274 | 2015-08-20 12:06 | 1 | 2014-2015 Annual Self-Appraisal from Talbert | Programming Staff Appraisals | Reviewed final document. Signed and sent.
86 | 30285 | 2015-06-10 16:25 | 3 | Add checkbox to delete dialog box | Admin Connect | Took me a while to see the layout but got the check box and label in the correct place. Task status changed from Assigned to In Progress.
86 | 30285 | 2015-06-10 16:37 | 0.1 | Add checkbox to delete dialog box | Admin Connect | Just sent an email to Amanda to test. Task status changed from In Progress to In Testing.
86 | 30285 | 2015-06-18 01:53 | 1 | Add checkbox to delete dialog box | Admin Connect | Amanda approved. I will hold off on one big push to test and prod later. Moving to final review. Task status changed from In Testing to Final Review.
86 | 30288 | 2015-06-10 16:27 | 4 | Scaffolding: add new area below existing list | Admin Connect | began working on this. sorting through the code is much harder than i thought. I needed to stop though to update the AUTHZ thing. Task status changed from Assigned to In Progress.
86 | 30288 | 2015-06-10 16:32 | 4 | Scaffolding: add new area below existing list | Admin Connect | began work on this again but this code is rather loose. declaration of sections start and never really seem to have an end.
86 | 30288 | 2015-06-10 16:33 | 7 | Scaffolding: add new area below existing list | Admin Connect | ok the code is not making any more sense to me. I think i have it figured out. I need to add my new stuff in a js file then somehow add that to the index page. i think.
86 | 30288 | 2015-06-18 02:09 | 5 | Scaffolding: add new area below existing list | Admin Connect | I am getting more lost trying to figure out this code.
86 | 30288 | 2015-06-18 02:16 | 8 | Scaffolding: add new area below existing list | Admin Connect | I have read the code but there is just simply no explanation of variable declaration. I am reading up on mustache.js to see if i can explain this.
86 | 30288 | 2015-06-18 02:44 | 8 | Scaffolding: add new area below existing list | Admin Connect | i have now extensively looked through all the files in the project and I cannot for the life of me figure out how declarations are establish.
86 | 30288 | 2015-06-18 02:46 | 7 | Scaffolding: add new area below existing list | Admin Connect | I have exhausted all my resources i can think of to figure out this code. I emailed out a call for help to fellow programmers. Thankfully Duke responded. He told me that what i was looking at was not fully mustache.js code but something called backbone.js. This was a revelation. I am now looking into backbone.
86 | 30288 | 2015-06-18 03:32 | 8 | Scaffolding: add new area below existing list | Admin Connect | with more help from Duke i found out the declaration area but there is still a lot that is confusing. I am looking into backbone.js. this still seems like a daunting task.
86 | 30288 | 2015-06-24 16:17 | 8 | Scaffolding: add new area below existing list | Admin Connect | Looked a little into backbone.js it is still hard to figure out how things are used and set.
86 | 30288 | 2015-06-24 16:19 | 6 | Scaffolding: add new area below existing list | Admin Connect | Well attempting to write some new code. I think I understand the structure of the files now. hopefully the code will run when im all done. right now I am setting up a new 'DeleteCoordinator' model.
86 | 30288 | 2015-06-24 16:20 | 8 | Scaffolding: add new area below existing list | Admin Connect | Continued working on the model of DeleteCoordinator. I then started to create the views for DeleteCoordinator. I think it would be best if i can replicate 'coordinator_list' and 'coordinator_item' and bind them to the index page after the current list of coordinators.
86 | 30288 | 2015-06-24 16:21 | 8 | Scaffolding: add new area below existing list | Admin Connect | continue to work on views of DeleteCoordinator.
86 | 30288 | 2015-07-15 16:17 | 1 | Scaffolding: add new area below existing list | Admin Connect | I was told by Amanda that this task was to be halted because changes were happening with the client. At that time I started to work on the Platform Client. I then talked to Dennis on how I should treat this task. He told me that Amanda should be the one to define if the task should be closed or whatnot. He explained the rules again to me.
86 | 30288 | 2015-07-15 16:18 | 1 | Scaffolding: add new area below existing list | Admin Connect | Talked to Amanda and she said it would be best to close out this task and if the project comes up again I will just get new tasks. For now I am moving this task to final review. Task status changed from In Progress to Final Review.
86 | 30292 | 2015-06-03 16:45 | 1 | TCLM meetings | Admin Connect | Met with Amanda to discuss the proposed project timeline. I sat down and worked out an estimated task list with hours. Task status changed from Assigned to In Progress.
86 | 30292 | 2015-07-01 13:07 | 1 | TCLM meetings | Admin Connect | Meeting with Amanda. I finally updated Amanda of my situation. She informed me that the project needs to be placed on hold. Major changes are happening.
86 | 30292 | 2015-07-15 16:13 | 1 | TCLM meetings | Admin Connect | Talked to Dennis about this task and he told me that Amanda should have answer for what I should do with this task.
86 | 30292 | 2015-07-15 16:14 | 0.1 | TCLM meetings | Admin Connect | Talked to Amanda and she told me just to close this task. If the project comes up again, I'll just get new tasks. So moving this task to final review. Task status changed from In Progress to Final Review.
379 | 30430 | 2015-07-09 12:08 | 6 | Develop client side alert tool | Platform PPI | Talked to Amanda, Kevin, and Vivek. I will now be placed on this priority one task. To develop a windows application to pull from a database to display a number with a button that links to a web page. I began asking questions on what type of application this should be, C# or something else. Vivek told me to look into a C++ application. Task status changed from Assigned to In Progress.
379 | 30430 | 2015-07-09 12:26 | 8 | Develop client side alert tool | Platform PPI | Continued to look into development of windows applications in C++.
379 | 30430 | 2015-07-09 12:30 | 8 | Develop client side alert tool | Platform PPI | Was confirmed by Vivek and Kevin that the users will all have Windows machines so I can make a C# desktop application. I asked if it should be Windows Form or WPF. Vivek confirmed WPF. He then initialized the repo. I pulled it down and got a simple GUI up with a Button that links to the proper web page.
379 | 30430 | 2015-07-09 12:31 | 7 | Develop client side alert tool | Platform PPI | I worked on the application some more and got the code to pull from Vivek's external API to pull the prospect count. So now the application, on-load, will display the number of prospects in queue. Also there was a meeting today with Marc C., Kevin, Amanda, Marc L., Vivek and myself. We are hopeful to have the application done by Thursday.
379 | 30430 | 2015-07-15 15:48 | 8 | Develop client side alert tool | Platform PPI | Vivek provided me Josh's design for the client application. I then spent the day re-organizing and stylizing the GUI. I checked in with Vivek all day and found new things to add to the application. I committed all my code by the end of the day.
379 | 30430 | 2015-07-15 15:50 | 6 | Develop client side alert tool | Platform PPI | Continued to tweak the UX of the application. End of the day I have finished all that Vivek asked me to do. I committed all my code.
379 | 30430 | 2015-07-15 15:50 | 0.5 | Develop client side alert tool | Platform PPI | Checked in with Vivek and all my work for the application is done. I have nothing else to work on for this project so I will close out this task by end of the sprint.
379 | 30430 | 2015-07-15 15:51 | 0.5 | Develop client side alert tool | Platform PPI | Quick meeting with Amanda, Marc L., Marc C., Kevin, and Vivek. Sounds like they will begin testing this day.
379 | 30430 | 2015-07-15 15:52 | 0.1 | Develop client side alert tool | Platform PPI | Finally moving this task to final review. I am done with this project. Task status changed from In Progress to Final Review.
381 | 30536 | 2015-11-18 17:05 | 4 | MY QUERIES: create wireframe and styling for page (Front) | The Enlightenment Portal | I kind of worked on this task too; along side the Tile styling. I just now pulled it so my hours are not correctly reflected on to this task. I am done with the styling of the page. I have sent to Damien to test. Task status changed from Assigned to In Testing.
381 | 30536 | 2015-12-10 11:33 | 6.5 | MY QUERIES: create wireframe and styling for page (Front) | The Enlightenment Portal | Damien asked me to add a color scheme to denote tile types. Started work to add a color stripe.
381 | 30536 | 2015-12-10 11:39 | 8 | MY QUERIES: create wireframe and styling for page (Front) | The Enlightenment Portal | worked to get the color stripe into all versions of tiles. then worked on choosing colors. after that i worked on the css to ensure color schemes match for hover states and arrows. I haven't a task for this so i am recording my time in this task.
381 | 30536 | 2016-02-17 13:27 | 0.1 | MY QUERIES: create wireframe and styling for page (Front) | The Enlightenment Portal | Talked to Damien. He said to move task to final review. Task status changed from In Testing to Final Review.
381 | 30537 | 2015-11-18 16:34 | 8 | MY QUERIES: create wireframe and styling for tile (Front) | The Enlightenment Portal | took time to look over the environment Task status changed from Assigned to In Progress.
381 | 30537 | 2015-11-18 16:35 | 8 | MY QUERIES: create wireframe and styling for tile (Front) | The Enlightenment Portal | Talked with Damien to begin the project. I was able to start fiddling with code and seeing it in the localhost
381 | 30537 | 2015-11-18 16:37 | 8 | MY QUERIES: create wireframe and styling for tile (Front) | The Enlightenment Portal | had questions about what the design doc portrayed. once that was clear I was able to have a very rough draft completed.
381 | 30537 | 2015-11-18 16:38 | 8 | MY QUERIES: create wireframe and styling for tile (Front) | The Enlightenment Portal | Finished up the first draft Sent to Damien to test. He was able to have some quick changes to start. In addition I have started and theoretically completed the styling needed for the "All Queries" page. It uses the same css, wireframe, and layout for "My Queries" tiles but has a preview popover control.
381 | 30537 | 2015-11-18 16:38 | 4 | MY QUERIES: create wireframe and styling for tile (Front) | The Enlightenment Portal | Finished the second draft and including a new icon. Sent to Damien to test. Task status changed from In Progress to In Testing.
381 | 30537 | 2016-02-17 13:27 | 0.1 | MY QUERIES: create wireframe and styling for tile (Front) | The Enlightenment Portal | Talked to Damien. He said to move task to final review. Task status changed from In Testing to Final Review.
381 | 30538 | 2015-12-03 11:59 | 8 | MY QUERIES: create wireframe and styling for group (Front) | The Enlightenment Portal | added in the javascript to allow the toggling of the groups. added in the change of the file icon to "open" icon; to add a more visual queue. moving to testing Task status changed from Assigned to In Testing.
381 | 30538 | 2016-02-17 13:26 | 0.1 | MY QUERIES: create wireframe and styling for group (Front) | The Enlightenment Portal | Talked to Damien. He said to move task to final review. Task status changed from In Testing to Final Review.
381 | 30566 | 2015-12-10 11:27 | 8 | ALL QUERIES: create all queries dropdown (Front) | The Enlightenment Portal | created the front end portion of this task. committed to dev. Moving task to test. Task status changed from Assigned to In Testing.
381 | 30566 | 2016-02-17 13:26 | 0.1 | ALL QUERIES: create all queries dropdown (Front) | The Enlightenment Portal | Talked to Damien. He said to move task to final review. Task status changed from In Testing to Final Review.
381 | 30567 | 2015-12-07 16:43 | 0.1 | ALL QUERIES: create add dropdown button (Front) | The Enlightenment Portal | Damien told me he did this. So I am going to Assign this to him. Task status changed from Assigned to In Progress.
381 | 30583 | 2015-11-18 17:07 | 8 | MANAGE GROUPS: setup wireframe and skin add group (Front) | The Enlightenment Portal | started this project. first started off by styling and wireframing the Manage Groups page. Task status changed from Assigned to In Progress.
381 | 30583 | 2015-11-18 17:07 | 7 | MANAGE GROUPS: setup wireframe and skin add group (Front) | The Enlightenment Portal | Finished up styling and sent to Damien to test. Task status changed from In Progress to In Testing.
381 | 30583 | 2016-02-17 13:26 | 0.1 | MANAGE GROUPS: setup wireframe and skin add group (Front) | The Enlightenment Portal | Talked to Damien. He said to move task to final review. Task status changed from In Testing to Final Review.
381 | 30584 | 2015-12-03 11:39 | 8 | MANAGE GROUPS: setup wireframe and skin edit group (Front) | The Enlightenment Portal | Created the input areas for both Create Group and Edit Group. Set to test. Task status changed from Assigned to In Testing.
381 | 30584 | 2016-02-17 13:26 | 0.1 | MANAGE GROUPS: setup wireframe and skin edit group (Front) | The Enlightenment Portal | Talked to Damien. He said to move task to final review. Task status changed from In Testing to Final Review.
381 | 30596 | 2015-12-10 11:42 | 8 | QUERY RESULT: create wireframe and style results (Front) | The Enlightenment Portal | Searched for existing code/libraries that will work with bootstrap. I found one and implemented the first part. It seemed like this will work. I will need to discuss with Damien to find out if this will work. Task status changed from Assigned to In Progress.
381 | 30596 | 2015-12-10 11:48 | 8 | QUERY RESULT: create wireframe and style results (Front) | The Enlightenment Portal | delved into the third party code for styling/sorting bootstrap tables. something isn't the same. styling is not right.
381 | 30596 | 2015-12-17 05:51 | 8 | QUERY RESULT: create wireframe and style results (Front) | The Enlightenment Portal | Showed what I had earlier. Damien was impressed about what the code can do. But want him to still confirm that this is viable code. In the mean time I worked and got the styling and displaying of the table to what we desired.
381 | 30596 | 2016-01-14 12:36 | 6 | QUERY RESULT: create wireframe and style results (Front) | The Enlightenment Portal | attempted to get the fixed header to "scroll" with horizontal scrolling.
381 | 30596 | 2016-01-14 12:39 | 6 | QUERY RESULT: create wireframe and style results (Front) | The Enlightenment Portal | continued to work with the third party lib to get scrolling and fixed headers working. There was a problem, the lib supports scrolling (both horizontal and vertical) and fixed header/footers but they do not work together. As the user scrolls the header stays in the same position. I notified Damien about this. He said that should not be a problem. So I will look into that tomorrow.
381 | 30596 | 2016-01-14 12:45 | 6 | QUERY RESULT: create wireframe and style results (Front) | The Enlightenment Portal | Damien had assigned the task to look into fixing the horizontally long tables. I suggested horizontal scrolling. And in addition, fixed headers. Today I looked through the API of the third party lib to see if it had these features already coded. I saw some features and attempted to implement them.
381 | 30596 | 2016-01-20 16:39 | 8 | QUERY RESULT: create wireframe and style results (Front) | The Enlightenment Portal | continued to look into fixed divs and scroll bars. I mainly did research today. Attempted some implementations but nothing seems to have an effect. and the code doesn't look that promising.
381 | 30596 | 2016-01-20 16:39 | 6 | QUERY RESULT: create wireframe and style results (Front) | The Enlightenment Portal | continued again with research and attempting code samples.
381 | 30596 | 2016-01-20 16:41 | 8 | QUERY RESULT: create wireframe and style results (Front) | The Enlightenment Portal | finally found some promising code examples to help me figure out the fixed header with scroll bar. attempted to implement but just nothing was appearing to happen on the screen. but this code is better than the others i have seen.
381 | 30596 | 2016-01-20 16:42 | 8 | QUERY RESULT: create wireframe and style results (Front) | The Enlightenment Portal | using the code example i was able to see some variable changes that would lead to a visual change in the UI.
381 | 30596 | 2016-02-10 14:24 | 0.1 | QUERY RESULT: create wireframe and style results (Front) | The Enlightenment Portal | As far as I know I am done with this task. Moving to Testing. It will be up to Damien to move to Final Review. Task status changed from In Progress to In Testing.
381 | 30596 | 2016-02-17 13:25 | 0.1 | QUERY RESULT: create wireframe and style results (Front) | The Enlightenment Portal | Talked to Damien. He said to move task to final review. Task status changed from In Testing to Final Review.
227 | 30662 | 2015-08-20 12:08 | 2 | PL Dashboard - edit invoice page - Talbert | Personalized Learning | read into this project and looked for code location.
227 | 30662 | 2015-08-20 12:10 | 7 | PL Dashboard - edit invoice page - Talbert | Personalized Learning | took me a while to figure out how to access the pl extended site. Joe was able to help me remember. Started to change the content.
227 | 30662 | 2015-08-20 12:11 | 4 | PL Dashboard - edit invoice page - Talbert | Personalized Learning | finished up changes. but I need to find out how Kevin wants this change to be saved to the repository.
227 | 30662 | 2015-08-27 11:18 | 6 | PL Dashboard - edit invoice page - Talbert | Personalized Learning | published all my code to dev. Dana looked it over and had some changes. Interactively reviewed and modified the page. End of the day got all the code in dev.
227 | 30662 | 2015-08-28 11:19 | 0.5 | PL Dashboard - edit invoice page - Talbert | Personalized Learning | confirmed with Dana that I can move this task to final review. Task status changed from Queued to Final Review.
227 | 30663 | 2015-08-20 12:33 | 4 | PL Dashboard - create popup 1 - talbert | Personalized Learning | Started work on this.
227 | 30663 | 2015-08-20 12:34 | 8 | PL Dashboard - create popup 1 - talbert | Personalized Learning | continued to work on this.
227 | 30663 | 2015-08-26 18:30 | 4 | PL Dashboard - create popup 1 - talbert | Personalized Learning | finished up the popup. have to wait to see what Kevin wants to do with this.
227 | 30663 | 2015-08-28 11:20 | 0.5 | PL Dashboard - create popup 1 - talbert | Personalized Learning | confirmed with Dana that I can move this task to final review. Task status changed from Queued to Final Review.
227 | 30664 | 2015-08-26 18:31 | 4 | PL Dashboard - popup 2 - talbert | Personalized Learning | started this. started the pop-up
227 | 30664 | 2015-08-26 18:31 | 6 | PL Dashboard - popup 2 - talbert | Personalized Learning | finished up the content of the pop up
227 | 30664 | 2015-08-26 18:42 | 8 | PL Dashboard - popup 2 - talbert | Personalized Learning | Spent the day trying to figure out a bug where the first modal window's closing button does not work.
227 | 30664 | 2015-08-26 18:44 | 8 | PL Dashboard - popup 2 - talbert | Personalized Learning | I found several solutions but found an equal number of problems that surfaced because of it.
227 | 30664 | 2015-08-26 18:46 | 8 | PL Dashboard - popup 2 - talbert | Personalized Learning | I attempted to debug the pop up stuff. But I decided to implement a solution by having only one modal window and the different content gets generated on the button click. I then had to figure out an issue with .NET components and bootstrap event handling. I needed to remove the .NET buttons and replace them with regular input types. I am now able to incorporate the checkbox validation to enable the buttons.
227 | 30664 | 2015-08-28 11:20 | 0.5 | PL Dashboard - popup 2 - talbert | Personalized Learning | confirmed with Dana that I can move this task to final review.
227 | 30664 | 2015-08-28 11:20 | 0.1 | PL Dashboard - popup 2 - talbert | Personalized Learning | Task status changed from Queued to Final Review.
381 | 30709 | 2015-11-18 16:30 | 1 | Consensus Building Opportunities | The Enlightenment Portal | Meeting with Blanche, Dylan, Sam, and I. Basic intro to the group as a group. Damien has already informed many of us of the project details.
381 | 30709 | 2015-11-18 16:32 | 4 | Consensus Building Opportunities | The Enlightenment Portal | Damien has informed me that there will be a new project on the way. He was able to get a quick meeting with Dylan, himself, and I to debrief us on the project details.
381 | 30709 | 2015-11-18 16:33 | 1 | Consensus Building Opportunities | The Enlightenment Portal | Meeting with Blanche, Dylan, Damien, Sam and I. Quick meeting to update each other on our progress.
381 | 30709 | 2015-12-10 10:54 | 1 | Consensus Building Opportunities | The Enlightenment Portal | Meeting with Sam, Damien, Dylan, Blanche.
381 | 30709 | 2015-12-17 05:59 | 1 | Consensus Building Opportunities | The Enlightenment Portal | Meeting with Blanche, Dylan, Sam, Damien and I.
227 | 30770 | 2015-09-02 17:18 | 8 | PL Touchnet - wire up popups using javascript | Personalized Learning | Kevin approached me and told me that he was not able to work the behind the code stuff with the front end stuff. Vivek assured me that this was possible. Kevin had to leave but he wanted me to figure out a way to have the back end talk to the front end. So I started my work on this.
227 | 30770 | 2015-09-02 17:22 | 8 | PL Touchnet - wire up popups using javascript | Personalized Learning | I attempted several solutions but each one would break something on either side of the code. I ended up changing the buttons into asp elements and was able to have those asp controls call the javascript function to call the modal windows. I still kept the checkbox as a regular HTML element and was able to control the toggling of disability via JQuery of the asp elements. I committed to dev for Kevin to use.
227 | 30770 | 2015-09-02 17:37 | 3 | PL Touchnet - wire up popups using javascript | Personalized Learning | I emailed Dana and Kevin to test the new code. This was after waiting for the Dev Environment to be brought back up. They were down for some time. Kevin wrote back and said that it was all green. So I am going to move this task to final review. Task status changed from Queued to Final Review.
227 | 30770 | 2015-09-02 17:41 | 0.1 | PL Touchnet - wire up popups using javascript | Personalized Learning | Task status changed from Final Review to In Progress.
227 | 30770 | 2015-09-02 17:43 | 0.1 | PL Touchnet - wire up popups using javascript | Personalized Learning | Task status changed from In Progress to Final Review.
240 | 30803 | 2015-09-10 14:39 | 8 | PL faculty dashboard - create hours app part 1 | PL Admin Tools | assigned the task and looked it over to evaluate the task. then started to attempt to implement bootstrap-datetimepicker. realized that will not work. started to look into other plugins and other solutions.
240 | 30803 | 2015-09-10 14:43 | 3 | PL faculty dashboard - create hours app part 1 | PL Admin Tools | Dana mentioned that he has a task that will becoming my way. having to deal with office hours.
240 | 30803 | 2015-09-16 12:47 | 7 | PL faculty dashboard - create hours app part 1 | PL Admin Tools | Still attempted to implement javascript plugins to use at a time picker. Task status changed from Assigned to In Progress.
240 | 30803 | 2015-09-16 12:53 | 6 | PL faculty dashboard - create hours app part 1 | PL Admin Tools | Determined that a specific time range picker plugin was not going to work. So I looked into an alternative to just dropdowns. I came up with the idea of using sliders; especially a double ended slider. I looked at the code source and saw that we did have a slider library installed. I worked to implement this into the current project. I later found out that this library was "developed" by Eddie and more than likely did not have the proper slider code I wanted.
240 | 30803 | 2015-09-16 13:00 | 8 | PL faculty dashboard - create hours app part 1 | PL Admin Tools | I talked it over with Dana a bit and we agreed that dropdowns will just have to be the way to go. I spent the day getting the dropdowns into the code by dynamically generating the code via JQuery. This way I didn't have to copy past lines of code. I then worked a bit on stabilization and the bottom part of the page. All in all the scaffolding should be done.
240 | 30803 | 2015-09-16 13:04 | 0.1 | PL faculty dashboard - create hours app part 1 | PL Admin Tools | This is being placed on hold to work on a higher priority task. Should be able to pick back up on Thursday. Task status changed from In Progress to On Hold. Task status changed from In Progress to On Hold.
240 | 30803 | 2015-10-01 01:21 | 0.5 | PL faculty dashboard - create hours app part 1 | PL Admin Tools | Moving this task out of hold and continue to work on this project. Task status changed from On Hold to In Progress.
240 | 30803 | 2015-10-07 17:34 | 8 | PL faculty dashboard - create hours app part 1 | PL Admin Tools | worked on some client side validation. once this gets done. the insertions should be much easier and not having to do many checks and the data should be clean and ready to go into the database cleanly. today got the checking of one time (in or out) and the other associated time to not be "No Office Hours"; this way no one can enter a start or end time without the corresponding end or start time.
240 | 30803 | 2015-10-07 17:36 | 8 | PL faculty dashboard - create hours app part 1 | PL Admin Tools | moved on to try validate if the start time was not set past the end time. this lead to some heavy thinking and i had to redesign the jquery that pulled the data.
240 | 30803 | 2015-10-07 17:39 | 8 | PL faculty dashboard - create hours app part 1 | PL Admin Tools | cleaned up the jquery and began the visual looks of the validation. If a time did not have its corresponding in/out time that control would turn red. if the time was mis-matched or equal ("in time" ended after "end time") then both controls turned orange. if it was a valid "in" and "out" entry both controls turned green. ended with beginning the code to enable/disable the submit button accordingly.
240 | 30803 | 2015-10-14 17:14 | 4 | PL faculty dashboard - create hours app part 1 | PL Admin Tools | Worked with Damien to ensure the functionally worked seamlessly with the front end. Covered many user interface issues.
240 | 30803 | 2015-10-28 14:35 | 4 | PL faculty dashboard - create hours app part 1 | PL Admin Tools | Tested and merged to test. Then notified Dana about this to test. He performed some testing and found some issues to work on.
240 | 30803 | 2015-10-28 15:56 | 8 | PL faculty dashboard - create hours app part 1 | PL Admin Tools | using the secondary model for data passing I got the onload data filling of the labels working. I then got it working for updating the dropdowns. I took time to debug this.
240 | 30803 | 2015-10-28 15:57 | 8 | PL faculty dashboard - create hours app part 1 | PL Admin Tools | Label population and updating was finished. I then started on populating the dropdowns with current schedule on load.
240 | 30803 | 2015-10-28 15:59 | 8 | PL faculty dashboard - create hours app part 1 | PL Admin Tools | Finished up the on-load dropdown population. started some work on the on change interface updates, this means updating the views when the user changes their times.
240 | 30803 | 2015-10-28 16:01 | 6 | PL faculty dashboard - create hours app part 1 | PL Admin Tools | Did some quick edits then tested and merged to test. Notified Dana to test. He tested and found one bug. I was able to get to this bug and re-sent to test. He approved. I am now moving this task to final review. Task status changed from In Progress to Final Review.
240 | 30806 | 2015-09-16 13:03 | 8 | PL Faculty Dashboard - create hours app Part II | PL Admin Tools | I attempted to work on some End User stuff like visual ques and validation via jquery. Task status changed from Assigned to In Progress.
240 | 30806 | 2015-09-16 13:04 | 0.1 | PL Faculty Dashboard - create hours app Part II | PL Admin Tools | This is being placed on hold to work on a higher priority task. Should be able to pick back up on Thursday. Task status changed from In Progress to On Hold.
240 | 30806 | 2015-09-24 03:41 | 7 | PL Faculty Dashboard - create hours app Part II | PL Admin Tools | touched on this again. waiting for Kevin to tell me something for another task.
240 | 30806 | 2015-10-01 01:27 | 7.5 | PL Faculty Dashboard - create hours app Part II | PL Admin Tools | Moving this task out from On Hold to in progress. I continued to work on the sql. It took me some time to finalize the sql call. I have not done this from the back end in a while.
240 | 30806 | 2015-10-01 01:29 | 4 | PL Faculty Dashboard - create hours app Part II | PL Admin Tools | finalized the back end code and was able to show the raw data to the front end.
240 | 30806 | 2015-10-01 01:43 | 8 | PL Faculty Dashboard - create hours app Part II | PL Admin Tools | Took me longer than I expected to format the time string so that it shows up as 12 hour time with AM/PM markings. In addition I had work on multiple entries per day. As a mentor can have multiple hours specified.
240 | 30806 | 2015-10-01 01:49 | 8 | PL Faculty Dashboard - create hours app Part II | PL Admin Tools | started work on the sql for insertion. this will need to pull the information from the client page then insert the data. however there are a lot of loop holes to cover before i can implement the insertion section.
240 | 30806 | 2015-10-01 01:50 | 8 | PL Faculty Dashboard - create hours app Part II | PL Admin Tools | continued to work on insertion stuff and all the closing of the loop holes. such as not allowing insertion if the person viewing the page has no existing hours.
240 | 30806 | 2015-10-07 17:31 | 6 | PL Faculty Dashboard - create hours app Part II | PL Admin Tools | continued to work but realized that i was running into mental blocks with validation on the back end. I decided that I would need to do the validation from the front end to lift the load from the back end.
240 | 30806 | 2015-10-14 17:03 | 6 | PL Faculty Dashboard - create hours app Part II | PL Admin Tools | Validation is complete on the front end. I started to begin work on processing the data from the front-end and sending it to the database. In order to do this by the ways that I saw in another project. I would need to implement AJAX. I started my research into AJAX. Started to implement what i have seen.
240 | 30806 | 2015-10-14 17:05 | 8 | PL Faculty Dashboard - create hours app Part II | PL Admin Tools | I got so far in AJAX learning but I know that this was some crazy voodoo magic. So I asked Damien for help. He aided me in getting the AJAX setup. But we quickly realized that I needed to implement a different structure for accessing C# back end code as methods for SQL calls. Thus we created a WebMethods.aspx file and filled it with WebMethods this way they became accessible to the front end code of the Office Hours page.
240 | 30806 | 2015-10-14 17:07 | 8 | PL Faculty Dashboard - create hours app Part II | PL Admin Tools | Worked again with Damien to get SQL calls working properly. At this point there are going to be many variables that we will need to address later; like getting the EmplID. We just worked on getting the WebMethod calls to some actual SQL stuff. We got the insertion working and the "clear" method working.
240 | 30806 | 2015-10-14 17:12 | 4 | PL Faculty Dashboard - create hours app Part II | PL Admin Tools | Worked with Damien again to pull other files into this project to get the emplid. In the end, we had to pull what I originally got. In the end we all functionally of the page working correctly. with validation and everything.
240 | 30806 | 2015-10-28 14:34 | 4 | PL Faculty Dashboard - create hours app Part II | PL Admin Tools | Tested and merged to test. Then notified Dana about this to test. He performed some testing and found some issues to work on.
240 | 30806 | 2015-10-28 15:00 | 8 | PL Faculty Dashboard - create hours app Part II | PL Admin Tools | Dana has seen an issue with on load the drop downs not loading the current schedule. I didn't that was necessary as the user can see their current schedule below. So I started to work on this. Starting out, i know that I need to pull individual times from the data. But currently this will not work as i am sending the data as a formatted string to the front end. Attempted to pull the data from the formatted string.
240 | 30806 | 2015-10-28 15:05 | 8 | PL Faculty Dashboard - create hours app Part II | PL Admin Tools | Pulling data from the formatted string is proving to be very stressful. I then decided to change up the structure to use ASP HiddenValue fields. This will allow me to access data more efficiently. It took me the rest of the day to set up the HiddenValues with getting some data.
240 | 30806 | 2015-10-28 15:40 | 8 | PL Faculty Dashboard - create hours app Part II | PL Admin Tools | I spent the day figuring out the optimal way to populate the hiddenvalue and pull the data. A lot of testing with JavaScript and value reading.
240 | 30806 | 2015-10-28 15:54 | 8 | PL Faculty Dashboard - create hours app Part II | PL Admin Tools | Took longer than expected but was finally able to parse the time correctly. I am now working to just populate the label field below. After I got everything passing data properly I looked at the code overall and realized that this was a cluttered mess. So I made the decision to clean up the code by having one interface to populate the labels and dropdowns.
240 | 30806 | 2015-10-28 16:02 | 2 | PL Faculty Dashboard - create hours app Part II | PL Admin Tools | Finished up bugs. Tested and merged to test. Had Dana test. He found one bug. I fixed the bug and he tested again. he approved. I then merged and committed to prod. Moving this task to final review. Task status changed from On Hold to Final Review.
227 | 30846 | 2015-09-16 13:12 | 6 | PL Touchnet - remove existing Invoice link | Personalized Learning | This was simple to do after i got some clarification from Dana. The link in the dropdown menu item was removed and the file was renamed. So no saved URLs will be able to access the page again. Task status changed from Assigned to In Progress.
227 | 30846 | 2015-09-24 03:23 | 6 | PL Touchnet - remove existing Invoice link | Personalized Learning | Kevin re-wrote the database view. After he confirmed that it was working I was able to revert the other task. But I needed to discuss with him what he wanted to do about the overall task. He informed me that it would be better if this button only appeared on Account History from the point Louie took over and provide a link/button to Louie for the information. I had do some code work but I was able to do this.
227 | 30846 | 2015-09-24 03:48 | 7 | PL Touchnet - remove existing Invoice link | Personalized Learning | Dennis had a meeting with me to clarify the situation with this task. I spent the day waiting for Kevin to test this project. he had to do some work with the databases. He later approved the work after it seem to have worked in test. In migrating to to prod I needed to work with Vivek to make sure this worked properly in the prod environment. All is well. Kevin then approved for this task to be moved to final review. Task status changed from In Progress to Final Review.
227 | 30846 | 2015-09-24 03:49 | 0.1 | PL Touchnet - remove existing Invoice link | Personalized Learning | Task status changed from Final Review to In Progress.
227 | 30846 | 2015-09-24 03:50 | 0.1 | PL Touchnet - remove existing Invoice link | Personalized Learning | Task status changed from In Progress to Final Review.
227 | 30847 | 2015-09-16 13:15 | 2 | PL Touchnet - Account history - talbert | Personalized Learning | Looked into this to see what I need to do. Was able to add button. But I need to figure out how to give myself a payment and note. Task status changed from Assigned to In Progress.
227 | 30847 | 2015-09-24 03:29 | 6 | PL Touchnet - Account history - talbert | Personalized Learning | got some info and was able to implement the suggested SQL and submitted to Dana for test. He informed me that something wasn't right. I attempted to implement what Dana wanted. but things are unclear.
227 | 30847 | 2015-09-24 03:32 | 7 | PL Touchnet - Account history - talbert | Personalized Learning | changed up the sql again and tried to understand what Dana wanted. i had to talk to Joe to get his help. We figured out something and i submitted the code. Dana tested but still said something was wrong.
227 | 30847 | 2015-09-24 03:34 | 1 | PL Touchnet - Account history - talbert | Personalized Learning | Dana is on vacation. Kevin is taking over. He needs to work on the table first. So i need to wait for him first.
227 | 30847 | 2015-09-24 03:36 | 1 | PL Touchnet - Account history - talbert | Personalized Learning | With Kevin's new table view I needed to revert the old code back. I then submitted to Kevin for testing. Task status changed from In Progress to In Testing.
227 | 30847 | 2015-09-24 03:51 | 1 | PL Touchnet - Account history - talbert | Personalized Learning | Kevin approved. Moving this task to final review. Task status changed from In Testing to Final Review.
240 | 31134 | 2015-10-29 11:11 | 0.1 | PL - Add more time options to faculty office hours | PL Admin Tools | Task status changed from Queued to Assigned.
240 | 31134 | 2015-11-04 17:51 | 4 | PL - Add more time options to faculty office hours | PL Admin Tools | Emailed out to task givers that I had not work. Later Dana, said that he had something for me. Got this task. Looked it over. Task status changed from Assigned to In Progress.
240 | 31134 | 2015-11-04 17:52 | 8 | PL - Add more time options to faculty office hours | PL Admin Tools | Made the change. tested it in local. Took some time to add comments that i meant to add last time. Merged and committed to test. test it and it looked good.
240 | 31134 | 2015-11-04 17:53 | 2 | PL - Add more time options to faculty office hours | PL Admin Tools | Emailed Dana to test. He approved. Moving task to final review. Task status changed from In Progress to Final Review.
381 | 31379 | 2016-01-14 12:48 | 8 | ALL QUERIES: Expand on styling of the new elements (Front) | The Enlightenment Portal | Reviewed many of the pages and looked through them to see what I can change. I did some changes like rounding edges, adding more spaces here and there, and change some colors around. Task status changed from Assigned to In Progress.
381 | 31379 | 2016-01-14 12:58 | 8 | ALL QUERIES: Expand on styling of the new elements (Front) | The Enlightenment Portal | Worked again to look through the site to look for visual improvements. The best I could do for today is to match up the permissions page by adding in the "container" class to 'frame' up the main content of the pages.
381 | 31379 | 2016-02-10 14:24 | 0.1 | ALL QUERIES: Expand on styling of the new elements (Front) | The Enlightenment Portal | As far as I know I am done with this task. Moving to Testing. It will be up to Damien to move to Final Review. Task status changed from In Progress to In Testing.
381 | 31379 | 2016-02-17 13:25 | 0.1 | ALL QUERIES: Expand on styling of the new elements (Front) | The Enlightenment Portal | Talked to Damien. He said to move task to final review. Task status changed from In Testing to Final Review.
381 | 31380 | 2016-02-04 05:28 | 8 | MANAGE GROUPS: Expand on styling of the new elements (Front) | The Enlightenment Portal | Looked into a separate list Damien provided me. Mainly little fixes here and there. Task status changed from Assigned to In Progress.
381 | 31380 | 2016-02-04 05:29 | 8 | MANAGE GROUPS: Expand on styling of the new elements (Front) | The Enlightenment Portal | Attempted to look into providing a solution for query pages. Client wants filter tool bar to activate filtering on button click not on keypress. I found no easy solution. Their should be a way to work around this however.
381 | 31380 | 2016-02-10 14:24 | 0.1 | MANAGE GROUPS: Expand on styling of the new elements (Front) | The Enlightenment Portal | As far as I know I am done with this task. Moving to Testing. It will be up to Damien to move to Final Review. Task status changed from In Progress to In Testing.
381 | 31380 | 2016-02-17 13:25 | 0.1 | MANAGE GROUPS: Expand on styling of the new elements (Front) | The Enlightenment Portal | Talk to Damien. He said to move to task to final review. Task status changed from In Testing to Final Review.
299 | 31559 | 2016-02-09 18:26 | 8 | wrap long URLS that currently run off side of the page | State Regulatory Compliance | Asked Damien for some tasks. After awhile was able to get this task. Looked into the background. Task status changed from Assigned to In Progress.
299 | 31559 | 2016-02-09 18:29 | 8 | wrap long URLS that currently run off side of the page | State Regulatory Compliance | Found some CSS to make the change. committed to dev. looked good. commited to test. Asked Damien to test. He liked it but wanted me to add the CSS to more areas. I added them tested in dev and test. Then asked Damien to re-test. He approved. Merged and committed to prod. Moving task to final review. Task status changed from In Progress to Final Review.
299 | 31566 | 2016-04-06 23:53 | 6 | updating status on tile does not refresh text description of status | State Regulatory Compliance | Waited for a new task. Damien presented this to me. I began research into this.
299 | 31566 | 2016-04-06 23:57 | 4 | updating status on tile does not refresh text description of status | State Regulatory Compliance | attempted to find the cause of the problem. I had to ask Damien for direction. A little bit of Angular questioning had to be done. I looked at controllers but I couldn't find the right area to change.
299 | 31566 | 2016-04-07 | 8 | updating status on tile does not refresh text description of status | State Regulatory Compliance | Finally determined the final cause of the area that needs to be changed but the actual implementation area was still missing. I asked Damien and he pointed me to details.js. This was the missing puzzle. I was concentrating on controllers not script controllers.
299 | 31566 | 2016-04-07 00:06 | 6 | updating status on tile does not refresh text description of status | State Regulatory Compliance | I had the script area to work with and was able to pull the right if/else statement; but I had no idea why the page was not updating correctly. I asked Damien about it and he discovered that I had the order of operations wrong. Once corrected the code worked as intended. I then merged and committed to dev and test. Damien tested and approved. I will wait till tomorrow to push to prod.
299 | 31566 | 2016-04-07 00:07 | 4 | updating status on tile does not refresh text description of status | State Regulatory Compliance | while in test I made one last testing run. by chance I found a small error. The terminology is different for different tile types. I need to add extra logic for this to be fully done.
299 | 31566 | 2016-04-12 17:50 | 3 | updating status on tile does not refresh text description of status | State Regulatory Compliance | Looked into issue with "Authorized" vs "In Compliance", figured out that it was pulling "In Compliance" from database. And "Authorized" was being set from client. But in test and prod, this would be changed to "In Compliance" when refreshed. I explained this to Damien. He said that it would be fine because more re-engineering will have to be done to tiles later. So for now just push to prod this task and final review. Which I did. Task status changed from In Progress to Final Review.
240 | 31579 | 2016-02-09 18:39 | 8 | PL Fac Tools - have connect button link to EAN | PL Admin Tools | Had to get some additional information from Dana first. The attachment folder did not exists. Was able to make the change simply. But had to make sure that it was the only control that I was affecting. End of the day I have a solution in test. Dana said it looked good but should wait till tomorrow to push to prod.
240 | 31579 | 2016-02-10 14:25 | 1 | PL Fac Tools - have connect button link to EAN | PL Admin Tools | Merged and committed to prod. Notified Dana. Moving to final review. Task status changed from Queued to Final Review.
240 | 31601 | 2016-02-15 13:28 | 6 | PL Admin - add transfer units to transfer tool - JOE or TALBERT | PL Admin Tools | updated the sql to show the values of Units Transferred and Units to the Transfer Tool. I did make sure that the results were correct by consulting Dana. I still need to look into getting the totals into the last row. Task status changed from Queued to Assigned.
240 | 31601 | 2016-02-15 13:30 | 8 | PL Admin - add transfer units to transfer tool - JOE or TALBERT | PL Admin Tools | based on instincts I do not think that the mock up for totals will be able to be done. the totals can be calculated but the placement in the table appears to be problematic. I spent the day looking into solutions either by SQL or Radgrids. No solutions appears to be within sight. Task status changed from Assigned to In Progress.
240 | 31601 | 2016-02-17 16:31 | 8 | PL Admin - add transfer units to transfer tool - JOE or TALBERT | PL Admin Tools | I started to look into using javascript to total the numbers together. I did see if i could put a div at the bottom of the table and that was still good. The javascript was looking to be more of a challenge because I could not assign the specific table cells a class name without that the javascript would have to be based on structure; and that can become dangerous for maintenance. Oh a whim I looked up more stuff on telerik and found a leading code bit that could work.
240 | 31601 | 2016-02-17 16:42 | 8 | PL Admin - add transfer units to transfer tool - JOE or TALBERT | PL Admin Tools | I looked more into telerik solution and was able to get the total sum to appear in the footer of the radgrid. however, I needed help with performing some checks on the PL Course name duplicates. I knew there is a solution in waiting for either Telerik or c# but I decided to call upon Damien to help me brainstorm and figure out a solution. With our combine effort we were able to get a custom aggregate function working to not count units if it was a duplicate.
240 | 31601 | 2016-02-22 15:02 | 6 | PL Admin - add transfer units to transfer tool - JOE or TALBERT | PL Admin Tools | Tested the code in dev. Once that was good, I moved it test. I emailed to Dana to test. It took him a while to test but he found out that the SQL he provided did not provide for a specific condition. He then said that the new SQL will take a while to be done. In the mean time, he will assign me a new task.
240 | 31601 | 2016-03-03 12:49 | 4 | PL Admin - add transfer units to transfer tool - JOE or TALBERT | PL Admin Tools | I asked Dana about this and he said that he was still waiting on new SQL. At the end of the day he emailed me the completed SQL. I started the procedure to implement the new code.
240 | 31601 | 2016-03-03 12:51 | 6 | PL Admin - add transfer units to transfer tool - JOE or TALBERT | PL Admin Tools | Implemented the new code. Somethings had some bugs; but i found them and fixed it. Merged and committed to dev and test. Email Dana to test.
240 | 31601 | 2016-03-04 10:18 | 0.1 | PL Admin - add transfer units to transfer tool - JOE or TALBERT | PL Admin Tools | Task status changed from In Progress to In Testing.
240 | 31601 | 2016-03-09 18:36 | 4 | PL Admin - add transfer units to transfer tool - JOE or TALBERT | PL Admin Tools | Dana gave the blessing to goto prod. I little bit later I got the notification to reverse merge this task. Another bigger wig need to review this in test first. Reversed merged and waiting.
240 | 31601 | 2016-03-09 18:46 | 3 | PL Admin - add transfer units to transfer tool - JOE or TALBERT | PL Admin Tools | Dana told me I can push to prod. I did so. Later he noticed missing data from a different column. I wasn't focusing on that column and missed that this data was missing. I looked at the code and found a column name discrepancy. I made the change and pushed to dev and test. Dana tested again. He approved. Merged to Prod. I'm gonna wait a half day to make sure this will be ready for final review tomorrow.
240 | 31601 | 2016-03-17 12:52 | 8 | PL Admin - add transfer units to transfer tool - JOE or TALBERT | PL Admin Tools | Dana informed me that some issues are popping up. We looked into some of it. He found a potential issue and had me replace a line in SQL. I committed and merged to dev and test. He came back and found another issue. He gave me another line of SQL to commit and merge to dev and test. He found another issue and gave me another SQL line change. I merged and committed to dev and test. I think finally found the full solution. Dana said to wait till Monday to push to prod.
240 | 31601 | 2016-03-17 12:59 | 1 | PL Admin - add transfer units to transfer tool - JOE or TALBERT | PL Admin Tools | got the green light from Dana to push to prod the recent changes. going to wait another day to final review.
240 | 31601 | 2016-03-17 13:34 | 0.1 | PL Admin - add transfer units to transfer tool - JOE or TALBERT | PL Admin Tools | Didn't hear anything from Dana. So I am guessing this is good for Final Review. Task status changed from In Testing to Final Review.
240 | 31607 | 2016-02-24 13:22 | 6 | PL Admin - add a column to faculty tools - talbert | PL Admin Tools | Looked into the background for this code. Took me some time to find the right one. I took the time to review the code.
240 | 31607 | 2016-02-24 13:24 | 8 | PL Admin - add a column to faculty tools - talbert | PL Admin Tools | After looking at the code I found it to be very convoluted. I showed this to Dana and he thought so too. He then generated new SQL to directly pull the number of lessons waiting for mastery. I spent the rest of the day trying to incorporate the SQL into the background code.
240 | 31607 | 2016-02-24 13:28 | 0.1 | PL Admin - add a column to faculty tools - talbert | PL Admin Tools | Task status changed from Queued to In Progress.
240 | 31607 | 2016-03-03 12:40 | 5 | PL Admin - add a column to faculty tools - talbert | PL Admin Tools | I finished up coding this today. Merged and committed to dev and test. Emailed Dana asking to test and if i should publish to prod. I wanted to do it today, but he said this could wait till i get back. Task status changed from In Progress to In Testing.
240 | 31607 | 2016-03-03 12:42 | 3 | PL Admin - add a column to faculty tools - talbert | PL Admin Tools | my vacation time left me a bit disoriented. I got scared that this may have gotten pushed to prod. but I found out that it was another task that was pushed to prod. I asked about this task and Dana said yes, this task is ready for prod. I merged and committed to prod. I informed Dana. I will now move this task to final review. Task status changed from In Testing to Final Review.
240 | 31670 | 2016-02-22 15:30 | 8 | PL Tools - have connect button link to EAN on all tabs - talbert | PL Admin Tools | started off by looking into the background code for this task. it took me a while to figure out where this is at. Once that was completed i started to mess with the code and see if I could to some altering. I first tried to do the same thing Damien and I tried with the previous task. But there are now specific changes to the radgrid that the same solution will not work. Task status changed from Assigned to In Progress.
240 | 31670 | 2016-02-22 15:40 | 8 | PL Tools - have connect button link to EAN on all tabs - talbert | PL Admin Tools | Dana pointed out I missed a key part to this task. In general I need to change all Connect columns to EAN with EAN links. However, "Current Prospects" does not always have a supplied EmplID so I first had to figure out how to show the Img Button for only those with EmplID. I did bring in Damien to help me with this. We got that done and I changed the links to be all EAN for all sections for the page. I then sent email for Dana to test. He had one last change for the buttons to open into a new tab/window. I did that committed to test and are now waiting for his response. Task status changed from In Progress to In Testing.
240 | 31670 | 2016-02-24 13:32 | 2 | PL Tools - have connect button link to EAN on all tabs - talbert | PL Admin Tools | Dana had one more update for me to have the button open in a new link. I Made the change had him test. He approved. Merged and committed to prod. Moving task to final review. Task status changed from In Testing to Final Review.
123 | 31704 | 2016-03-23 13:14 | 6 | Format the URLs on the Reading Dev page to Jason's design | Landing Pages | Worked with the Ektron content block for the links. I re-wrote the html to be a div with an onclick event. I was able to insert a style block so that the divs look like a button. I pretty much got this done at the end of the day, but I needed to ask a question to Jason about on hover style changes and what the "share" button should do. Task status changed from Assigned to In Progress.
123 | 31704 | 2016-03-23 13:42 | 4 | Format the URLs on the Reading Dev page to Jason's design | Landing Pages | Jason got back to me and said that the "share" button wasn't intended to be seen as "share" and decided to remove them from the design. He also provided the hover color. After i made the changes I copied the code to test environment. But here I ran into an issue with publishing in test Ektron environment. I contacted Dave again to see if there was any solutions. He could not figure out the reason but provided a work around. I made the change and emailed Amanda and Jason to test. Amanda approved. I copied the code to prod. She approved and said to move this task to final review. Task status changed from In Progress to Final Review.
123 | 31705 | 2016-03-22 11:15 | 8 | Add youtube video to bottom of Reading dev page | Landing Pages | Mainly took this day to familiarize myself with Ektron stuff again. I had to have a back and fourth with Dave Dennehey to get me access to either localhost or dev version of EC ektron. There was a problem with licence violations. Finally got this done. And started to work with Ektron again to insert this video. I looked through the widgets and saw that there was one for Related Video. Amanda was out, so I stared to ask Jason for more information. He thought that maybe Dana had embedded the youtube video into our system. But I could not find it there.
123 | 31705 | 2016-03-22 11:34 | 4 | Add youtube video to bottom of Reading dev page | Landing Pages | started to look into this. i was very confused as to where the code was at. I looked through all of the solution files and didn't find the page. I asked Amanda about this and she reminded me that it was an Ektron page. After that I looked at the page in prod and saw what Amanda had already done. I attempted to look into the dev or local version of this page, but it didn't exists. A database refresh had to be done. But then ran into some licencing violations.
123 | 31705 | 2016-03-22 12:00 | 8 | Add youtube video to bottom of Reading dev page | Landing Pages | Talked to Jason about styling for videos. i still have not found the video in our system. Dana is out on vacation, so i cannot ask him for help. I looked into possibly embedding the video into a different widget instead.
123 | 31705 | 2016-03-22 12:03 | 2 | Add youtube video to bottom of Reading dev page | Landing Pages | I asked Dana about the youtube video and if it was in our own system. He was unsure, so i asked Amanda about more information. She took some time to talk to Dana about this and found out that it wasn't possible for an existing youtube video to be processed into our system. She then talked to the client (I think) and they decided to drop the video completely. And this task will be closed.
240 | 31713 | 2016-03-04 10:17 | 0.1 | PL - show units for crses not transferred - talbert | PL Admin Tools | Task status changed from Queued to In Progress.
240 | 31713 | 2016-03-09 18:13 | 6 | PL - show units for crses not transferred - talbert | PL Admin Tools | With my activity with Transfer Tool code I was able to figure out what to do this task. Thankfully the table already pulled the column I needed and i just had to show it in the front end. I committed to dev then merged and committed to dev; both environments look good. sent an email for Dana to test. Task status changed from In Progress to In Testing.
240 | 31713 | 2016-03-09 18:37 | 2 | PL - show units for crses not transferred - talbert | PL Admin Tools | Was given goto to published to prod. Then later told to reverse merge. Testing by another is needed first.
240 | 31713 | 2016-03-09 18:48 | 1 | PL - show units for crses not transferred - talbert | PL Admin Tools | Got the green light to push to prod. Did so. Gonna wait a half day tomorrow before moving this task to final review.
240 | 31713 | 2016-03-17 12:31 | 0.1 | PL - show units for crses not transferred - talbert | PL Admin Tools | Did not hear anything bad about this so i am going to move this task to final review. Task status changed from In Testing to Final Review.
239 | 31715 | 2016-03-04 10:18 | 0.1 | PL - update text on dashboard pay page | PL Student dashboard | Task status changed from Queued to In Progress.
239 | 31715 | 2016-03-09 18:33 | 8 | PL - update text on dashboard pay page | PL Student dashboard | It took me some time just to be able to view the local host page. Required Dana's help to insert me as a faux student. Once there I was able to see the changes I made in the code. Merged and committed to dev and test. Informed Dana to test. Task status changed from In Progress to In Testing.
239 | 31715 | 2016-03-09 18:40 | 2 | PL - update text on dashboard pay page | PL Student dashboard | got the green light to go to prod. merged and committed to prod. Dana then noticed that I missed some additional text at the bottom. I immediately caught this and merged and committed changes to dev and test. Dana wanted me to hold off pushing the final big as additional changes maybe needed.
239 | 31715 | 2016-03-09 18:41 | 1 | PL - update text on dashboard pay page | PL Student dashboard | Got the green light for the missed part. Merged and committed to prod. Dana tested and looked good. Moving this task to final review. Task status changed from In Testing to Final Review.
240 | 31726 | 2016-03-09 18:43 | 7 | PL - show pl courses completed on course transfer page -Talbert | PL Admin Tools | Looked into this task and first started out to create the SQL myself. I tried an tried, but I had to turn to Damien for help. He was able to create a working SQL but was unsure about Effective Status and Effective Date. I reviewed the SQL as best as i can.
240 | 31726 | 2016-03-09 18:43 | 0.1 | PL - show pl courses completed on course transfer page -Talbert | PL Admin Tools | Task status changed from Queued to In Progress.
240 | 31726 | 2016-03-09 18:50 | 2 | PL - show pl courses completed on course transfer page -Talbert | PL Admin Tools | Asked Dana for more information about this task. He was able to give more hints with another table that could be used. I tried to create a whole new SQL using this information but ran into issue with LEFT JOINS. Damien looked at what I was doing and just told me to show what he and I created yesterday to Dana to test. I emailed the SQL to Dana for his input.
240 | 31726 | 2016-03-17 12:28 | 8 | PL - show pl courses completed on course transfer page -Talbert | PL Admin Tools | Dana approved the SQL. I incorporated it into the code and worked to display it to the front end. After that I merged and committed to dev and test. I checked them out and they looked good. I then emailed Dana to test. Task status changed from In Progress to In Testing.
240 | 31726 | 2016-03-17 13:00 | 1 | PL - show pl courses completed on course transfer page -Talbert | PL Admin Tools | Dana approved the test version and got it tested by the client. They all approved. Merged and committed to prod. Moving this task to final review. Task status changed from In Testing to Final Review.
381 | 31773 | 2016-03-29 19:12 | 7 | MY QUERIES: Display the correct frequency on the report tiles | The Enlightenment Portal | First was looking for new tasks. Damien supplied me with this one. He went over the basics. We looked through the code and found out that the main code to develop on was linq code. I first made the attempt to just use the existing data column. but it wasn't the same.
381 | 31773 | 2016-03-29 19:32 | 5 | MY QUERIES: Display the correct frequency on the report tiles | The Enlightenment Portal | Because the code is based in linq I took the day to refresh my mind on linq code. However, just like SQL the syntax is small but the implementation is huge. Even reviewing the basics didn't help to uncover what i needed to change in code.
381 | 31773 | 2016-03-29 19:43 | 8 | MY QUERIES: Display the correct frequency on the report tiles | The Enlightenment Portal | attempted to modify linq code. less to say...it did not go well.
381 | 31773 | 2016-03-29 19:43 | 8 | MY QUERIES: Display the correct frequency on the report tiles | The Enlightenment Portal | Contacted Sam to help me with the code. He said he would and get back to me when the changes are made.
381 | 31773 | 2016-03-29 19:51 | 4 | MY QUERIES: Display the correct frequency on the report tiles | The Enlightenment Portal | Sam made the change. We reviewed what was to be done next with Damien. I implemented the code but saw no change. I asked Damien about this and he found a different issue that was missed. This should have been changed before I started work. But once he made the change the code worked perfectly.
381 | 31773 | 2016-04-06 23:51 | 2 | MY QUERIES: Display the correct frequency on the report tiles | The Enlightenment Portal | uploaded to dev and test. Had Damien test. he approved. merged and committed to prod. Damien approved. moving this task to final review Task status changed from In Progress to Final Review.
299 | 31830 | 2016-04-06 23:49 | 4 | Add flag for District of Columbia | State Regulatory Compliance | pulled the flag image from Wikipedia then formatted to height ratio as the rest of the flags on state compliance.
299 | 31830 | 2016-04-07 00:02 | 2 | Add flag for District of Columbia | State Regulatory Compliance | Asked for a new task and Damien got this one to me.
299 | 31830 | 2016-04-12 17:47 | 3 | Add flag for District of Columbia | State Regulatory Compliance | These were merged and committed to prod. Damien approved. Moving to final review Task status changed from In Progress to Final Review.
381 | 31872 | 2016-04-20 17:20 | 8 | Pagehit log not working on query and resreport pages | The Enlightenment Portal | Damien was able to get me this tasks. I was only able to look to the description today to figure out the task. I am currently looking at the code structure and seeing if i can see the layout of the code. Task status changed from Assigned to In Progress.
381 | 31872 | 2016-04-20 17:27 | 4 | Pagehit log not working on query and resreport pages | The Enlightenment Portal | Talked to Damien about this and he was able to explain the main problem seen. I am still having issues finding the area of code work with. I am able to debug and and see where the breaking is happening but not sure what the call stack is.
381 | 31872 | 2016-04-20 17:33 | 8 | Pagehit log not working on query and resreport pages | The Enlightenment Portal | I spent the entire day trying to breakdown the structure of the MVC here. I needed to do this to understand where the call stack was happening. I still have no idea what structure is calling ControllerLayout.cs
381 | 31872 | 2016-04-20 17:38 | 8 | Pagehit log not working on query and resreport pages | The Enlightenment Portal | Finally broke down, and asked Damien what I needed to do. He was able to sit with me and point out what how to determine which (of three) script files were making the call. We were able to do this from the console log and Chrome Web Developer tool. After we were able to determine that it was a difference in POST structure. The one that Layout Mobile was calling was an ajaxPost method; whereas, the others were just jquery $.post method. I switched it out for the jquery one and it seemed to work great. But Damien wanted me to check in with Duke about typescript stuff.
381 | 31872 | 2016-04-21 12:36 | 1 | Pagehit log not working on query and resreport pages | The Enlightenment Portal | Talked to Duke about TypeScript he said the change to jquery type post should be fine to use.
381 | 31872 | 2016-04-21 12:40 | 4 | Pagehit log not working on query and resreport pages | The Enlightenment Portal | notified Damien about what Duke said. He said to go to test. I merged and committed up to test. I notified him and told him I didn't have access to rsreports (some were not assigned to me). He added some to me and I tested again; and so did he. We both saw our page hits in the database. Green light to go to prod. Merged and committed. Notified Damien. He said to final review. Task status changed from In Progress to Final Review.
381 | 31936 | 2016-04-26 18:36 | 2 | Fix the issue with adding a new group and moving tiles | The Enlightenment Portal | Damien notified me about this task and he spent some time explaining the ins and outs of this task. Task status changed from Assigned to In Progress.
381 | 31936 | 2016-04-26 18:40 | 4 | Fix the issue with adding a new group and moving tiles | The Enlightenment Portal | started to look into this task. I started my testing in firefox.
381 | 31936 | 2016-04-26 18:41 | 8 | Fix the issue with adding a new group and moving tiles | The Enlightenment Portal | Continued to test in firefox. however, i am not seeing the major issue (or at least, the work around seems to be working fine). I asked Damien about this and he said not to forget to test IE. I started testing in IE.
381 | 31936 | 2016-04-26 18:43 | 5.5 | Fix the issue with adding a new group and moving tiles | The Enlightenment Portal | I tested in IE. But the work around seem to work too. I did testing in Chrome and the behavior here was exactly the same i have seen in firefox and IE. I showed Damien and he was intrigued, because these were issues that he has not seen before. We may have identified a few of the issues, and he wants me to look specifically into drag and drop on an established group.
381 | 31936 | 2016-05-04 16:28 | 8 | Fix the issue with adding a new group and moving tiles | The Enlightenment Portal | Looked through code to try to find the source of the problem; specifically the drag and drop stuff.
381 | 31936 | 2016-05-04 16:41 | 6 | Fix the issue with adding a new group and moving tiles | The Enlightenment Portal | Couldn't find the issue in the code easily. Damien suggested I look through his past commits and look for "collapse" methods.
381 | 31936 | 2016-05-04 16:55 | 8 | Fix the issue with adding a new group and moving tiles | The Enlightenment Portal | looked through all the past revisions but nothing stood out as a change in "collapse". Damien meant to just look through revisions by updating to past revisions and seeing when the drag and drop started to break.
381 | 31936 | 2016-05-04 17:19 | 8 | Fix the issue with adding a new group and moving tiles | The Enlightenment Portal | After revision diving I found the specific revision that was causing the issue. Thankfully it wasn't a big revision. I tackled each file change in the revision and applied it to the working copy. From there I narrowed the problem to a specific line in one file. I took out the change. But I still needed a work around. I then implemented a Jquery solution. It would seem to work.
381 | 31936 | 2016-05-04 17:23 | 6 | Fix the issue with adding a new group and moving tiles | The Enlightenment Portal | Performed testing in three web browsers. All seems to be good to go to test. Unfortunately test environment was down for a bit for updating. Will have to wait to commit to test.
381 | 31936 | 2016-05-11 15:38 | 4 | Fix the issue with adding a new group and moving tiles | The Enlightenment Portal | Merged and committed to test. Tested and informed Damien to test. He came back with a green light. Merged and committed to prod. moving this task to final review.
381 | 31936 | 2016-05-11 15:39 | 0.1 | Fix the issue with adding a new group and moving tiles | The Enlightenment Portal | Task status changed from In Progress to Final Review.
311 | 31985 | 2016-05-04 17:20 | 2 | Move blog down the homepage and style like blog page | EC, Yuma, Yav, PL Widget Maintenance | Test environment was down. I told Damien I had a solution for another task but that would have to wait. Until then I asked for another task. He provided me this one. I will start by analyzing the problem. Task status changed from Assigned to In Progress.
311 | 31985 | 2016-05-11 15:49 | 2 | Move blog down the homepage and style like blog page | EC, Yuma, Yav, PL Widget Maintenance | Found Sql and imported it into Sql Studio Manager. Started to tweak it to pull images.
311 | 31985 | 2016-05-11 15:51 | 8 | Move blog down the homepage and style like blog page | EC, Yuma, Yav, PL Widget Maintenance | Something seemed a bit wrong. The returning result was not matching up to the dummy data I had entered into the EC Site Management. Upon further investigation I completely had the wrong sql.
311 | 31985 | 2016-05-11 15:56 | 8 | Move blog down the homepage and style like blog page | EC, Yuma, Yav, PL Widget Maintenance | Took me a while to find the right sql again. started to break down the sql to figure out how to incorporate the images.
311 | 31985 | 2016-05-11 16:30 | 8 | Move blog down the homepage and style like blog page | EC, Yuma, Yav, PL Widget Maintenance | images incorporation is going to be tough as the blog code accommodates for video's to be blog article images. I will need to break down the original code more to be able to do this as well on the index page.
311 | 31985 | 2016-05-19 11:42 | 6 | Move blog down the homepage and style like blog page | EC, Yuma, Yav, PL Widget Maintenance | After a quick talk with Damien, he determined that the sql would need to be the focus of the code. So I started to pull out the necessary sql and see if i can combine them.
311 | 31985 | 2016-05-19 11:51 | 8 | Move blog down the homepage and style like blog page | EC, Yuma, Yav, PL Widget Maintenance | As I am working with the SQL the resultant page is returning several rows. This is bad because the original only had three rows returning. I am considering just migrating all of the code from blog to the front page but this will over bloat the front page.
311 | 31985 | 2016-05-19 11:53 | 4 | Move blog down the homepage and style like blog page | EC, Yuma, Yav, PL Widget Maintenance | I asked Damien what would be the best call here. And he said that a JavaScript call know what to do if the attributes are all set. With this information I think I will be able to have the sql return the correct attributes in three rows.
311 | 31985 | 2016-05-25 12:55 | 8 | Move blog down the homepage and style like blog page | EC, Yuma, Yav, PL Widget Maintenance | Took the blog sql and started to work with it to return featured and top three
311 | 31985 | 2016-05-25 13:01 | 4 | Move blog down the homepage and style like blog page | EC, Yuma, Yav, PL Widget Maintenance | the sql is giving me a lot of problems in trying to return the top three only. the inclusion of the different types is expanding the rows by a lot.
311 | 31985 | 2016-05-25 13:31 | 8 | Move blog down the homepage and style like blog page | EC, Yuma, Yav, PL Widget Maintenance | my sql looks aghast. I asked Damien for help. He said it would be easier to just take the major bits of blog and just throw them into the index page. to help me out he said he would make the sql.
311 | 31985 | 2016-05-25 13:31 | 8 | Move blog down the homepage and style like blog page | EC, Yuma, Yav, PL Widget Maintenance | waited most of the day for Damien. He was able to provide me the sql. I started the process to incorporate it into the index page.
311 | 31985 | 2016-05-25 13:46 | 8 | Move blog down the homepage and style like blog page | EC, Yuma, Yav, PL Widget Maintenance | incorporated the code. then applied stylings. tested to ensure functionality. merged and committed all the way to test. found an issue if there are no featured stories.
311 | 31985 | 2016-05-31 16:43 | 2 | Move blog down the homepage and style like blog page | EC, Yuma, Yav, PL Widget Maintenance | I am waiting to hear from Damien and Amanda about what to do about no featured stories. Damien said it would best to leave it blank. I have not heard from Amanda just yet. In the mean time I have removed the text completely and merge to test.
311 | 31985 | 2016-05-31 17:52 | 6 | Move blog down the homepage and style like blog page | EC, Yuma, Yav, PL Widget Maintenance | Talked to Amanda about the blank featured stories and she said that she would have to talk to the clients first. I have decided that it would be better for me to close out this task than holding on to this task. I moved on to the part 2 of testing. I created three test featured blogs on test. It took me some time after that to figure out how to publish them to the test page.
311 | 31985 | 2016-05-31 17:54 | 4 | Move blog down the homepage and style like blog page | EC, Yuma, Yav, PL Widget Maintenance | I emailed Damien and Amanda about testing the blogs again. Damien said that this may need to be migrated to Yuma and Yavapai. I looked into it. but I had to leave early for errands.
311 | 31985 | 2016-05-31 17:55 | 4 | Move blog down the homepage and style like blog page | EC, Yuma, Yav, PL Widget Maintenance | Amanda gave the green light. I merged and committed to prod. Amanda approved. I will now moved this task to final review. Task status changed from In Testing to Final Review.
311 | 32054 | 2016-05-16 17:03 | 8 | Expand PL Tuition widget and migrate to all four sites | EC, Yuma, Yav, PL Widget Maintenance | Amanda assigned me this task and I wanted a quick break from the Blog thing. took me sometime to figure out where the code was at. I had to reset the access key to the right one for pl ektron. after that I found out that the area is a widget. I looked into the code in VS and found it. From there it was easy to add the content. Just took me time to style it correctly. I merged to dev and test and emailed Amanda. Task status changed from Assigned to In Progress.
311 | 32054 | 2016-05-16 17:53 | 8 | Expand PL Tuition widget and migrate to all four sites | EC, Yuma, Yav, PL Widget Maintenance | Amanda approved the one on PL. She then said to make the change on the other sites. I made sure that this widget was code synced among the four different sites. Made the change and merged to dev and test. Notified Amanda and she approved. Merged and committed to prod for all four sites. Moving this task to final review. Task status changed from In Progress to Final Review.
311 | 32106 | 2016-05-31 17:59 | 2 | Migrate 'blog on homepage' to Yuma and Yavapai | EC, Yuma, Yav, PL Widget Maintenance | I had already notified Amanda about this and told her that this and another task should be created. I began this by starting to migrate the code from EC; code that I have created. Task status changed from Assigned to In Progress.