## Sheet1
PID | TID | Date Entry | Hrs | Task Name | Project Name | Descr
6 | 5359 | 2014-07-09 18:22 | 1 | Administration Stuff | Self Task | Adam Cook came looking for help. I offered to help but in the process found out that mt localhost was messed up for admin site. I took time to get this fixed. I had to ask Joe for help.
6 | 5359 | 2014-07-17 00:52 | 4 | Administration Stuff | Self Task | Sean Vance had me take the time to uninstall adobe stuff so that I an install Adobe Creative Cloud.
6 | 5359 | 2014-08-12 16:12 | 0.5 | Administration Stuff | Self Task | Started a meeting with Marc Lord, but have to reschedule because not all programmers were present for the meeting. We discussed a little about the topic of EC workflow process and mentoring/mentee program. Homework is to answer questions sent out by Marc.
6 | 5359 | 2014-08-12 16:16 | 1.5 | Administration Stuff | Self Task | Meeting with Marc Lord to discuss workflow process and what to do with student workers.
6 | 5359 | 2014-09-23 17:04 | 2 | Administration Stuff | Self Task | Bryan's going away party.
6 | 5359 | 2014-09-30 18:10 | 1 | Administration Stuff | Self Task | Meeting with Dennis (along with Damien and Sam) to discuss the presentation packet of a student worker on MVC. Dennis asked us to review the packet and see if we can become available to help them out with questions and reviews. Afterwards me, Sam, and Damien discussed MVC in our environment and concluded that only code that pulls from the database should be considered the Model. Else we will get into MVC inception.
6 | 5359 | 2015-01-14 19:28 | 8 | Administration Stuff | Self Task | Half way point evaluation for self appraisal.
6 | 5359 | 2015-02-12 15:01 | 2 | Administration Stuff | Self Task | Team building activity meeting with Jason
6 | 5359 | 2015-03-12 11:33 | 8 | Administration Stuff | Self Task | Getting new computer set up.
6 | 5359 | 2015-03-12 11:34 | 6 | Administration Stuff | Self Task | Finished up setting up new computer
6 | 5359 | 2015-06-10 16:28 | 4 | Administration Stuff | Self Task | Went through the procedure to update machine to AUTHZ. Had some questions that Dylan helped me out on.
6 | 5359 | 2015-06-10 16:30 | 4 | Administration Stuff | Self Task | My localhost was broken I made several attempts to fix it myself. But I had to contact Vivek for help. The problem I was seeing was a 503 "Service Unavailable" error on admin and ec. Vivek was able to determine that it was my IIS app pool somehow both admin and ec got turned off.
6 | 5435 | 2014-09-11 11:42 | 1 | Training | Self Task | ACM Webinar: Async Javascript with Netflix
6 | 5435 | 2014-10-16 12:24 | 1.5 | Training | Self Task | Attended a presentation from student worker, Ryan, on MVC in combination with third party lib. the meeting covered 2 of the three proposed presentation segments. This covered basic intro to MVC and uses.
6 | 5435 | 2014-10-16 12:53 | 2 | Training | Self Task | Final presentation from Ryan on MVC. This is mainly a demo presentation.
6 | 5435 | 2014-10-22 14:02 | 2 | Training | Self Task | Travel to Phoenix for "Trust" workshop for EC Development Day
6 | 5435 | 2014-10-22 14:03 | 9 | Training | Self Task | Trust workshop EC Development Day and travel back to Flagstaff
6 | 5435 | 2015-01-14 19:27 | 7 | Training | Self Task | began reading Roles and Responsibilities document
6 | 5435 | 2015-02-05 14:08 | 2 | Training | Self Task | Roles and Responsibilities test and review with Dennis
6 | 5435 | 2015-02-12 15:26 | 2 | Training | Self Task | Accessibility training
6 | 5435 | 2015-04-24 10:21 | 2 | Training | Self Task | Web Pro Meeting
6 | 5435 | 2015-06-10 16:38 | 1 | Training | Self Task | Webinar meeting: Front-end accessibility.
331 | 25931 | 2014-07-09 17:11 | 2 | Create control for expanded ticket and attachment view | Admin TSC Development | Assisted in getting jquery and angularJS working to allow toggle slide up and slide down working for each ticket.
331 | 25931 | 2014-07-17 01:15 | 2 | Create control for expanded ticket and attachment view | Admin TSC Development | coded up some bootstrap and played with some jquery (but removed) to get the "My Campuses" dropdown list to look like bootstrap style.
123 | 26069 | 2014-07-02 16:44 | 0.1 | Create Body Content Widget (Talbert) | Landing Pages | i have committed all working code so far and Damien pushed to test. Task status changed from In Progress to In Testing.
123 | 26069 | 2014-07-03 11:36 | 0.1 | Create Body Content Widget (Talbert) | Landing Pages | Amanda gave the green light. Task status changed from In Testing to Final Review.
280 | 26076 | 2014-07-01 17:37 | 0.1 | 2014 Initial BB Learn training for Talbert | Onboarding & Orientation | Task status changed from In Testing to Final Review.
123 | 26179 | 2014-07-02 16:37 | 6 | Implement images/video on the formatted content widget | Landing Pages | Meeting this morning to discuss progress. Then worked with Damien to finish up this widget. loading the videos and background images to the edit page seem to be working but no the setting of those values. A big discussion occurred between me and Damien about the design of the code. we came to an amicable solution.
123 | 26179 | 2014-07-02 16:40 | 7 | Implement images/video on the formatted content widget | Landing Pages | I implemented a third radio button for images and videos. this object was "none". since it is possible that a user does not need an image or video they can have none. But by doing this i had to change up a lot of logic for the controls. Also made "none" default value.
123 | 26179 | 2014-07-02 16:47 | 0.1 | Implement images/video on the formatted content widget | Landing Pages | all working code has been merged and committed to test. however, there are still some issues with images. Damien has fixed issues with videos.
123 | 26179 | 2014-07-03 11:38 | 0.1 | Implement images/video on the formatted content widget | Landing Pages | There are still some work to be done with this task but the actual implementation is complete. Another task will be given to me for the detail work I need to get done. For now moving to final review. Task status changed from In Progress to Final Review.
123 | 26180 | 2014-07-02 16:45 | 0.1 | Implement WYSIWYG on the formatted content widget | Landing Pages | i have committed all working code so far and Damien has merged to test Task status changed from In Progress to In Testing.
123 | 26180 | 2014-07-03 11:36 | 0.1 | Implement WYSIWYG on the formatted content widget | Landing Pages | Amanda gave the green light. Task status changed from In Testing to Final Review.
123 | 26329 | 2014-07-02 16:46 | 0.1 | Aligh Request Info with the top of the body content (Talbert) | Landing Pages | all working code for this has been merged and committed to test by Damien. Task status changed from In Progress to In Testing.
123 | 26329 | 2014-07-03 11:37 | 0.1 | Aligh Request Info with the top of the body content (Talbert) | Landing Pages | Amanda gave the green light. Task status changed from In Testing to Final Review.
123 | 26330 | 2014-07-02 16:43 | 7 | Stylize widget content (Talbert) | Landing Pages | by adding the new radio button, "none", there was some logic in viewing to be changed so I did this and styled up the new functionality. in addition, styled up more of the widget. mainly here i am nit-picking on specific details. I have committed my code and Damien merged to test. Task status changed from In Progress to In Testing.
123 | 26330 | 2014-07-03 11:37 | 0.1 | Stylize widget content (Talbert) | Landing Pages | Amanda gave the green light. Task status changed from In Testing to Final Review.
123 | 26513 | 2014-07-09 23:10 | 4 | Stylize video in formattedbodycontent widget | Landing Pages | started to fix the sizing of the images for the video. Task status changed from Assigned to In Progress.
123 | 26513 | 2014-07-09 23:11 | 1 | Stylize video in formattedbodycontent widget | Landing Pages | Meeting with team to discuss current progress. I showed my current implementation and this brought up more questions about images in the body text and images on their resolution size when in the body of the widget.
123 | 26513 | 2014-07-24 10:29 | 1 | Stylize video in formattedbodycontent widget | Landing Pages | Talked to Amanda about this and told her there was one last aspect to this task to complete.
123 | 26513 | 2014-07-31 03:16 | 5 | Stylize video in formattedbodycontent widget | Landing Pages | Meeting today about this project so far; about 2 hours. For this task, it turned out to be a simple change. I was able to get it so that the width of all images/videos in the right hand side of the widget to be a static size and the height will adjust accordingly. Another aspect to this task that I completed too was images inside the body content area. I made these all 100% width. This is task is done but i have not push to test yet.
123 | 26513 | 2014-08-07 02:01 | 2 | Stylize video in formattedbodycontent widget | Landing Pages | Published to test but there was a problem with certs with cc.net and things are all kinds of wonky. Task status changed from In Progress to In Testing.
123 | 26513 | 2014-08-07 02:11 | 0.1 | Stylize video in formattedbodycontent widget | Landing Pages | Testing is complete and I am moving this to final review. Task status changed from In Testing to Final Review.
123 | 26514 | 2014-07-09 23:14 | 4 | Assist with fixing images for formattedbodycontent widget | Landing Pages | After some sleuthing around I found out that the code I wrote, I forgot to add one logic to allow the visibility of the images. Task status changed from Assigned to In Progress.
123 | 26514 | 2014-07-24 10:28 | 1 | Assist with fixing images for formattedbodycontent widget | Landing Pages | Discussed my task list with Amanda and she said to move this to final review. Task status changed from In Progress to Final Review.
123 | 26569 | 2014-07-09 23:17 | 4 | Add abiliy to include image in the Formatted Body Content widget | Landing Pages | Started to research this, the current examples we have do not include entering in a image into the body textarea. Task status changed from Assigned to In Progress.
123 | 26569 | 2014-07-17 01:01 | 4 | Add abiliy to include image in the Formatted Body Content widget | Landing Pages | Continued looking into options to get this done. I talked to both Joe and Vivek and they both had opposing ideas. Joe brought up many good points to how this idea of inserting images could be a security risk. But Vivek brings up the point that this should be ok and the client wants this feature.
123 | 26569 | 2014-07-17 01:07 | 6 | Add abiliy to include image in the Formatted Body Content widget | Landing Pages | Started code write up. Testing out many variations to inserting an image. The Wysiwyg version seems ok. But it allows for drag and drop from desktop to text edit area. which can be bad. I had to alter the white list to allow for images to be allowed.
123 | 26569 | 2014-07-17 01:09 | 6 | Add abiliy to include image in the Formatted Body Content widget | Landing Pages | Continued with code development. I do need Damien's help but he is not in today. I was able to implement a dropdown list, but i need to hook it up to ektron folder I made so that i am only pulling file names.
123 | 26569 | 2014-07-17 01:12 | 4 | Add abiliy to include image in the Formatted Body Content widget | Landing Pages | Damien was able to help me, along with Vivek, and I was able to populate the dropdown list with file names of images from a specific Ektron folder. We then spent some time getting jquery to append the image to the wysiwyg area. Damien suggested to insert the image at the end. From there the user can move it to where they would like. got this working and merged to dev. Damien will merged to test tomorrow.
123 | 26569 | 2014-07-24 10:26 | 1 | Add abiliy to include image in the Formatted Body Content widget | Landing Pages | Talked to Amanda and this is working great and is in test. Amanda said to move this task to final review. Task status changed from In Progress to Final Review.
123 | 26573 | 2014-07-24 10:50 | 4 | Stylize the Landing Page block quote | Landing Pages | started out this task by researching if bootstrap wysiwyg and if I can implement a button that can insert blockquotes. It doesn't look like our current version of wysiwyg can do that with out another plugin. Task status changed from Assigned to In Progress.
123 | 26573 | 2014-07-24 10:54 | 7 | Stylize the Landing Page block quote | Landing Pages | Explained the situation to Amanda and she thought it would be better if I changed the task to be a separate widget; as oppose to including it into the wysiwyg. So I started making the new widget.
123 | 26573 | 2014-07-31 02:49 | 5 | Stylize the Landing Page block quote | Landing Pages | Amanda asked me to explain the situation to Jason. I did and he agreed that this should be its own widget. I then finished up the code implementation of the blue block quote widget. I then moved on to stylization of the widget. I met up with Jason later to go over final looks. I am now complete with this task. But have yet to publish to test.
123 | 26573 | 2014-08-07 02:01 | 2 | Stylize the Landing Page block quote | Landing Pages | Published to test but cc.net is all kinds of funky right now. something to do with certs. Task status changed from In Progress to In Testing.
123 | 26573 | 2014-08-07 02:22 | 1 | Stylize the Landing Page block quote | Landing Pages | Forgot to mention this to Amanda that this is ready for testing. She will get back to me tomorrow with results of testing.
123 | 26573 | 2014-08-12 13:40 | 1 | Stylize the Landing Page block quote | Landing Pages | Merged and committed to test. This then was published to prod via Damien. Moving this task to final review. Task status changed from In Testing to Final Review.
123 | 26728 | 2014-08-07 01:40 | 2 | Set up reg-ex on the FormattedBodyContent images | Landing Pages | Started on this task to have the body content wysiwyg text area go through another validation method to ensure that all image tags have a src attribute that matches "/uploadedImages/Landing_Pages/images/" and can only be of file type .jpeg, .jpg, .png, etc. Task status changed from Assigned to In Progress.
123 | 26728 | 2014-08-12 13:59 | 6 | Set up reg-ex on the FormattedBodyContent images | Landing Pages | Researched many methods to get this done. I can try to do this with regex, but I think i could do this with javascript. In any case I am looking for a way to first target only image tags then look for the src attr. This is proving to be the hardest part.
123 | 26728 | 2014-08-12 14:05 | 2 | Set up reg-ex on the FormattedBodyContent images | Landing Pages | When working with Jason to finish up review of the FormattedBodyContent widget I found out that moving an image after it has been inserted it actually deletes the old code and rewrites the code in the new area. In addition, it fully qualifies the image src attr. This means that if I implement the regex it will break the moving of the image functionality. I talked to Amanda about this and we agreed that we can just dump this task. Images cannot be dragged/drop from any location and can only be insert through the wysiwyg so images should be somewhat secure. Moving this task to final review. Task status changed from In Progress to Final Review.
123 | 26792 | 2014-07-31 03:24 | 2.5 | Add Insert URL Link to WYSIWYG (Talbert) | Landing Pages | Copied out the code that will allow for inserting links. However this is not working. I have debugged it as much as I could for the day and could not see why it is not working. I did confirm with Damien that a onblur attribute was not necessary; and that was what was throwing the initial error. But the inserting will still not work. Task status changed from Assigned to In Progress.
123 | 26792 | 2014-08-07 01:58 | 3 | Add Insert URL Link to WYSIWYG (Talbert) | Landing Pages | Attempted to track down the issue. I have already added in the bootstrap buttons into the wysiwyg (the same as Joe's example) but in my localhost the button is doing nothing and console log is empty.
123 | 26792 | 2014-08-07 02:14 | 5 | Add Insert URL Link to WYSIWYG (Talbert) | Landing Pages | Tried many things to get this working. But I am not getting any errors or any other visual cue that something is not working.
123 | 26792 | 2014-08-07 02:17 | 6 | Add Insert URL Link to WYSIWYG (Talbert) | Landing Pages | I have a theory that it has to do with stopPropagation() method. Looking at the code it looks like JQuery is looking for a click event on a hidden field. So though maybe another code was blocking this event. After awhile of trying to find this error, I finally asked Damien for help. When I showed him this it was working for a sec. I reloaded the page and it went to broken again. Damien checked his localhost and it was working as intended. I asked Amanda to test again.
123 | 26792 | 2014-08-07 02:19 | 2 | Add Insert URL Link to WYSIWYG (Talbert) | Landing Pages | I had published this to test. I have not tested it completely but Amanda wanted code to be migrated to test. The code was not breaking anything so I did not see a problem committing this. Task status changed from In Progress to In Testing.
123 | 26792 | 2014-08-07 02:21 | 1 | Add Insert URL Link to WYSIWYG (Talbert) | Landing Pages | Amanda said that it worked in test. I have concluded that it is just my local host that is not working completely. I am moving this to final review. Task status changed from In Testing to Final Review.
123 | 26794 | 2014-07-31 02:53 | 2.5 | Remove underline from WYSIWYG (Talbert) | Landing Pages | Removed the code for the underline button in both BlueBlockQuote widget and FormattedBodyTextWidget. I then had to change my test pages to reflect the what was there. This is pretty much done but I have not published to test yet. Task status changed from Assigned to In Progress.
123 | 26794 | 2014-08-07 02:09 | 2 | Remove underline from WYSIWYG (Talbert) | Landing Pages | Published to test but things are unsure if it made it to test because certs expired for cc.net Task status changed from In Progress to In Testing.
123 | 26794 | 2014-08-07 02:12 | 0.1 | Remove underline from WYSIWYG (Talbert) | Landing Pages | Testing is complete and I am moving this to final review. Task status changed from In Testing to Final Review.
123 | 26928 | 2014-08-12 13:48 | 4 | Walk through Blue Callout widget with Jason (Tal) | Landing Pages | Worked with Jason to look over the looks and style on the view mode section of Landing Pages, specifically the FormattedBodyContent widget and BlueBlockQuote widget. Task status changed from Assigned to In Progress.
123 | 26928 | 2014-08-12 13:49 | 3 | Walk through Blue Callout widget with Jason (Tal) | Landing Pages | Worked with Jason again to look over the edit mode of the FormattedBodyContent widget. Made some updates and committed to dev. Later, after testing, merged and committed to test. This was then merged to prod via Damien's update. Task status changed from In Progress to Final Review.
123 | 26935 | 2014-08-14 11:22 | 4 | Numbered lists should always show up behind lists (Talbert) | Landing Pages | I have made the change in css to have the OL tag have a spacing above it. This will only target the list as a whole, not just specific LI items. In addition, I have been working to solve specific style issues I have seen on the site. Task status changed from Assigned to In Progress.
123 | 26935 | 2014-08-19 14:03 | 1 | Numbered lists should always show up behind lists (Talbert) | Landing Pages | Published to test. Notified Amanda to test. Task status changed from In Progress to In Testing.
123 | 26935 | 2014-08-19 14:04 | 0.5 | Numbered lists should always show up behind lists (Talbert) | Landing Pages | Amanda approved. Merged and committed to prod. Moving task to final review. Task status changed from In Testing to Final Review.
123 | 26936 | 2014-08-14 11:20 | 2 | Add spacing between paragraphs on the Formatted Body Content widget (Talbert) | Landing Pages | I had assumed that when an editor was going to use the wysiwyg they would just double [Enter] to get a new line with space between paragraphs. After talking to Amanda, she informed me that Jason wants to have the editors just have one [Enter] return on the wysiwyg and when they publish it will add the spacing for them. I used css to perform this change. Task status changed from Assigned to In Progress.
123 | 26936 | 2014-08-19 14:00 | 1 | Add spacing between paragraphs on the Formatted Body Content widget (Talbert) | Landing Pages | Looking at this again and the text area I realized that the wysiwyg was in actually placing the new paragraphs into a separate div. So that means the original code does work as intended.
123 | 26936 | 2014-08-19 14:01 | 1 | Add spacing between paragraphs on the Formatted Body Content widget (Talbert) | Landing Pages | Published to test. Notified Amanda to test. Task status changed from In Progress to In Testing.
123 | 26936 | 2014-08-19 14:02 | 0.5 | Add spacing between paragraphs on the Formatted Body Content widget (Talbert) | Landing Pages | Amanda approved. Merged and committed to prod. Moving task to final review. Task status changed from In Testing to Final Review.
123 | 26943 | 2014-08-19 14:08 | 5 | Remove extra space above banner and pad quote | Landing Pages | Spent the entire day looking for the problem to this. I had before already fixed this for chrome and IE, by applying a css style rule to hide all images that have a src attr that contained "googleadservices". But for some reason Firefox still has this space above the banner. I found out that Firefox was rendering margin-bottom:30px as 30px above and below the content. I changed it to a padding-bottom and that worked. Task status changed from Assigned to In Progress.
123 | 26943 | 2014-08-19 14:09 | 1 | Remove extra space above banner and pad quote | Landing Pages | I had to check on an error I saw on Amanda's computer. She saw an iframe vs and img for the googleadservices. I had other employees look at the page and all they got were images. I just have to chalk this up to being a fluke.
123 | 26943 | 2014-08-19 14:10 | 1 | Remove extra space above banner and pad quote | Landing Pages | Merged and committed to test. Notified Amanda to test. Task status changed from In Progress to In Testing.
123 | 26943 | 2014-08-19 14:12 | 0.5 | Remove extra space above banner and pad quote | Landing Pages | Amanda approved. Merged and committed to prod. moving task to final review. Task status changed from In Testing to Final Review.
123 | 26948 | 2014-08-19 14:17 | 4 | Request Info styling issues | Landing Pages | Worked on the image and captcha area and got the images to stay within frame. I did this with css style rules as an external rule. Before, in code, this was attempted to be done as inline styling. But the external css rule allows for the rule to be applied after rendering. Task status changed from Assigned to In Progress.
123 | 26948 | 2014-08-19 14:21 | 5 | Request Info styling issues | Landing Pages | Worked with Damien to fix the styling with EC custom dropdown object. Damien found out that Firefox stopped supporting a mozilla specific styling rule. For now I just applied more css rules to cover the dropdown button. I then tried to use asp/c# "MaintainScrollPosition" function but this did not fix the jumping action after clicking submit on the request info. I researched some ways and the easiest one i found to implement was a javascript function.
123 | 26948 | 2014-08-19 14:22 | 1 | Request Info styling issues | Landing Pages | Merged and committed to test.
123 | 26948 | 2014-08-19 14:23 | 2 | Request Info styling issues | Landing Pages | Damien convinced me to merged and commit to prod so that he can merged and commit to prod. I did that then notified Amanda to test. She approved. Moving this task to final review. Task status changed from In Progress to Final Review.
123 | 27078 | 2014-08-21 10:40 | 0.5 | Create manual log functionality on the landing page tracker tool (Ray) | Landing Pages | Attempted to help with collapse stuff by suggesting different bootstrap layout.
123 | 27115 | 2014-08-19 13:44 | 1 | Create the scaffolding for the Add Thumbnail on the Doc Uploader page (Talbert) | Landing Pages | Initial meeting to plan out the new control. Task status changed from Assigned to In Progress.
123 | 27115 | 2014-08-21 10:53 | 3 | Create the scaffolding for the Add Thumbnail on the Doc Uploader page (Talbert) | Landing Pages | Spent majority of the time trying to debug removing old code. I was informed that Damien and Robbie worked on something similar to this but that code was not going to work. I tried to erase the code but their was a connection that somewhere that wouldn't allow the page to render. I then tried to reverse merge. I tried to edit the conflicts but the same error was happening. I finally decided that this really should be Damien and Robbie's problem as it is their code.
123 | 27115 | 2014-08-21 11:04 | 5 | Create the scaffolding for the Add Thumbnail on the Doc Uploader page (Talbert) | Landing Pages | While waiting for Damien to reverse merge out the old code I just hide the front end components. I got the scaffolding in with an area for an image preview. And an area for the button to go. After that I looked up how to implement the file chooser dialog box. This is where I found out that the file chooser dialog box is static code from the browser; meaning the component has fixed functionality and look. I researched other methods to do a file chooser but this is not possible without scripts.
123 | 27115 | 2014-08-28 12:25 | 3 | Create the scaffolding for the Add Thumbnail on the Doc Uploader page (Talbert) | Landing Pages | Created a simple image that would become a placeholder for no image selected. Then placed the image into the form.
123 | 27115 | 2014-08-28 12:35 | 2 | Create the scaffolding for the Add Thumbnail on the Doc Uploader page (Talbert) | Landing Pages | Started implementing javascript stuff, to supplement this I created two buttons. one to replace the current input (type=file) and one to be the clear selection button. After all the components were javascripted up I then published to test. Notified Amanda and Jason. Task status changed from In Progress to In Testing.
123 | 27115 | 2014-08-28 13:24 | 1 | Create the scaffolding for the Add Thumbnail on the Doc Uploader page (Talbert) | Landing Pages | This got approved by Amanda and Jason. I am moving this to final review but i will not publish to prod until the background code is done. Task status changed from In Testing to Final Review.
123 | 27162 | 2014-08-21 11:18 | 2 | Hook up thumb nail selector on Doc Management page (Talbert) | Landing Pages | I started some of this and marked it in another task. I started to research what customization could I do to an input type=file. I found out that the only way to do some customization is going to use heavy javascript. And this is limited customization. Task status changed from Assigned to In Progress.
123 | 27162 | 2014-08-28 12:09 | 6 | Hook up thumb nail selector on Doc Management page (Talbert) | Landing Pages | Researched ways to work with input type=file. This includes pulling the filepath from the input element. I discovered that web browsers implement a good amount of security checks. For example, when you get the value of this kind of input file, Chrome will return "www.fakepath.com/(filename)". Also, It is not possible to set the path of this element. I learned a lot about input type file elements.
123 | 27162 | 2014-08-28 12:41 | 3 | Hook up thumb nail selector on Doc Management page (Talbert) | Landing Pages | Worked with javascript to update the image preview section when the user selects an image using the input (type=file) element.
123 | 27162 | 2014-08-28 12:45 | 6 | Hook up thumb nail selector on Doc Management page (Talbert) | Landing Pages | Prior to this day i was trying to avoid using javascript as the handler of events. But all my research this week did not show this would be possible. So I spent the day javascripting all the elements on the page. I switched out the input element for a single button with a label next to it. I was able to do this with the JQuery function .trigger(). Then to add more functionality to the user I implemented a clear selection button. I then used JQuery to do a show/hide event for the label and delete buttons. After all this I published to test. Notified Amanda and Jason. Task status changed from In Progress to In Testing.
123 | 27162 | 2014-08-28 13:21 | 6 | Hook up thumb nail selector on Doc Management page (Talbert) | Landing Pages | Spent the entire day planning out the actual background code that must be implemented for the control to work. This included the process when the user creates a new document, views a document, edits a document, and "deleting" a document; all this with the idea that the user may or may not affect the thumbnail image.
123 | 27162 | 2014-08-28 13:26 | 3 | Hook up thumb nail selector on Doc Management page (Talbert) | Landing Pages | Amanda stopped by to ask about this and the progress. I showed her the "map" I created for the process I will need and she created the extra tasks i need to complete this project. Now that i have those tasks i will move this task to final review. Again I will not commit stuff to prod until the background stuff is done. Task status changed from In Testing to Final Review.
123 | 27252 | 2014-08-28 13:28 | 3 | Code thumbnail on Add Doc page | Landing Pages | Reviewed the back-end code to see how the whole page is wired. This will help me understand where i will need to add code or alter code. Task status changed from Assigned to In Progress.
123 | 27252 | 2014-09-02 14:55 | 5 | Code thumbnail on Add Doc page | Landing Pages | Ran into an issue with my logic that I had planned out recently. Had to rethink the plan. After that found the area of code I need to change to add SQL logic.
123 | 27252 | 2014-09-11 12:18 | 5 | Code thumbnail on Add Doc page | Landing Pages | Worked on sql and functionality to insert file into the database. Also had to get the insertion into the Document_Attr working too. Worked on the logic too so that the functionality works when a user either edits or inserts a new document.
123 | 27252 | 2014-09-17 13:49 | 5 | Code thumbnail on Add Doc page | Landing Pages | Tested in dev. Ran into multiple hickups. some was dealing with blank text input and missing values in the database.
123 | 27252 | 2014-09-17 13:52 | 2 | Code thumbnail on Add Doc page | Landing Pages | After fixing more minor stuff I was able to get this working. the user can now insert a new document with a new image.
123 | 27252 | 2014-09-17 14:04 | 1 | Code thumbnail on Add Doc page | Landing Pages | Merged to test. tested and looked good. Notified Amanda to test.
123 | 27252 | 2014-09-17 14:04 | 0.1 | Code thumbnail on Add Doc page | Landing Pages | Task status changed from In Progress to In Testing.
123 | 27252 | 2014-09-23 16:33 | 0.5 | Code thumbnail on Add Doc page | Landing Pages | Checked in on Amanda to see the status of the task. Still testing.
123 | 27252 | 2014-09-23 16:36 | 1 | Code thumbnail on Add Doc page | Landing Pages | Amanda said the testing went well. Merged and committed to prod. Build is green. Moving task to final review. Task status changed from In Testing to Final Review.
123 | 27253 | 2014-09-02 14:58 | 6 | Code thumbnail on View Doc page | Landing Pages | I realized that I actually need to work on the view state first in order to do the insertion. Because after I insert the image stuff how was I going to look at it? So I am working on logic and SQL code to view a page with an image on it. Task status changed from Assigned to In Progress.
123 | 27253 | 2014-09-04 11:45 | 7 | Code thumbnail on View Doc page | Landing Pages | integrated the sql logic into the background code (DAL area) along the way had to work out additional sql calls to be made when i am accessing the image. At first I was pulling the byte code and trying to turn it into an image when i return the data to the back-end code. but Damien pointed out that i can just return the base64 string code to the source of the image element and that will render the image. So i changed the sql logic to accommodate this.
123 | 27253 | 2014-09-11 11:50 | 7 | Code thumbnail on View Doc page | Landing Pages | Continued working and thinking that I had the code in place I started to look at the website. But in doing so I found a strange error on my page. I began to debug it and found an issue with my repo. Something was not right in the logic. I got errors that was saying a DLL was missing. when it should not. I tried to rebuild but nothing was fixing the error.
123 | 27253 | 2014-09-11 11:54 | 7 | Code thumbnail on View Doc page | Landing Pages | I asked Damien for help. We looked at the build and he was looking at his local host. After we were able to get his repo up to date we saw that his builds were fine. We tried several fixes but nothing seemed to have worked. We then decided just to manually copy the dll from one source to the area the computer thinks it should be at. After that I build and everything seem to have worked. Not sure why that happened. I continued my work debugging the view of the image on the page.
123 | 27253 | 2014-09-11 12:04 | 6 | Code thumbnail on View Doc page | Landing Pages | Finish debugging and got the Image to show up. This is accomplished by pulling the [Document_Data] field from the [Document] table from [DMS]. Then displaying the image to the page. Next I added more sql to pull filename and formatting this to display the filename to the page; this will help out later.
123 | 27253 | 2014-09-17 14:04 | 1 | Code thumbnail on View Doc page | Landing Pages | Merged to test. tested and looked good. Notified Amanda to test. Task status changed from In Progress to In Testing.
123 | 27253 | 2014-09-23 16:34 | 0.5 | Code thumbnail on View Doc page | Landing Pages | Checked in on Amanda to see the status of the task. Still testing.
123 | 27253 | 2014-09-23 16:36 | 1 | Code thumbnail on View Doc page | Landing Pages | Amanda said the testing went well. Merged and committed to prod. Build is green. Moving task to final review. Task status changed from In Testing to Final Review.
123 | 27254 | 2014-09-11 12:21 | 7 | Code thumbnail on Edit Doc page | Landing Pages | Worked on sql and functionality for editing the thumbnail image. This was a bit tricky as there are some necessary checks to be made first. So I had to add more sql to return some Boolean values. Task status changed from Assigned to In Progress.
123 | 27254 | 2014-09-17 13:58 | 5 | Code thumbnail on Edit Doc page | Landing Pages | Worked on the update version of the page. This is where the user edits an existing document, so the user should be able to change up the image and save the new image. I got this working pretty well at the end of the day.
123 | 27254 | 2014-09-17 14:04 | 1 | Code thumbnail on Edit Doc page | Landing Pages | Merged to test. tested and looked good. Notified Amanda to test. Task status changed from In Progress to In Testing.
123 | 27254 | 2014-09-23 16:34 | 0.5 | Code thumbnail on Edit Doc page | Landing Pages | Checked in on Amanda to see the status of the task. Still testing.
123 | 27254 | 2014-09-23 16:37 | 1 | Code thumbnail on Edit Doc page | Landing Pages | Amanda said the testing went well. Merged and committed to prod. Build is green. Moving task to final review. Task status changed from In Testing to Final Review.
123 | 27255 | 2014-09-11 12:23 | 7 | Code thumbnail on Delete Doc page | Landing Pages | There was a meeting to day with the project leader and other programmers. I updated them on my status. I have delete functionality left as well as major debugging/testing on my end to make sure all the sql and functionality i have added work together. I finished the day getting the delete sql working. Task status changed from Assigned to In Progress.
123 | 27255 | 2014-09-17 14:02 | 5 | Code thumbnail on Delete Doc page | Landing Pages | Worked on the Deleting the image from document, specifically when the user "Retires" a document. End of the day I got this working but found another issue with just clearing the image and not retiring the document.
123 | 27255 | 2014-09-17 14:03 | 3 | Code thumbnail on Delete Doc page | Landing Pages | Finished up code development and logic for clearing the image only. After that I merged to test and tested there. I have notified Amanda this is now in test. Task status changed from In Progress to In Testing.
123 | 27255 | 2014-09-23 16:35 | 0.5 | Code thumbnail on Delete Doc page | Landing Pages | Checked in on Amanda to see the status of the task. Still testing.
123 | 27255 | 2014-09-23 16:37 | 1 | Code thumbnail on Delete Doc page | Landing Pages | Amanda said the testing went well. Merged and committed to prod. Build is green. Moving task to final review. Task status changed from In Testing to Final Review.
308 | 27364 | 2014-09-11 11:47 | 1 | some calendar events are displaying in 24 hour military format | Site Management: Admin Calendar Maintenance | Helped Adam find the place in code where the time was being pulled from. Attempted to fix the problem right there but had to ask Vivek questions. Adam took over at this point. I think Vivek helped him from here.
308 | 27364 | 2014-09-11 11:48 | 0.5 | some calendar events are displaying in 24 hour military format | Site Management: Admin Calendar Maintenance | Helped Adam track down the location of time variable in Calendar pages. It was a simple change as the original coder did not exchange out the formatted time variable for the raw time variable in place.
311 | 27589 | 2014-09-25 12:07 | 7 | Hook up thumbnail on the Related Documents widget (Talbert) | EC, Yuma, Yav, PL Widget Maintenance | began this project by researching the background code and the taking to Damien about how the code he is developing will integrate into this task. we figured out the change in the code that should be done. this involved moving code from a local scope to the data access layer. Task status changed from Assigned to In Progress.
311 | 27589 | 2014-09-25 12:19 | 6 | Hook up thumbnail on the Related Documents widget (Talbert) | EC, Yuma, Yav, PL Widget Maintenance | Damien migrated his code to the data access layer and i began code development to implement this into the page i am working on. at the end of the day i got the image to appear and began some work on css.
311 | 27589 | 2014-09-25 12:22 | 4 | Hook up thumbnail on the Related Documents widget (Talbert) | EC, Yuma, Yav, PL Widget Maintenance | Finished up css. had to have jason stop by for a min to give me input. after that I committed to dev. tested and it looked good. I then merged and committed to test. I noticed that my picture was not showing up. I asked damien about this and he said it was not working for png. for the sake of testing i change the test case to use a jpg and asked Amanda to test. Task status changed from In Progress to In Testing.
311 | 27589 | 2014-09-25 12:24 | 6 | Hook up thumbnail on the Related Documents widget (Talbert) | EC, Yuma, Yav, PL Widget Maintenance | spent the day css'ing the page and testing the various screen sizes.
311 | 27589 | 2014-10-01 11:43 | 1 | Hook up thumbnail on the Related Documents widget (Talbert) | EC, Yuma, Yav, PL Widget Maintenance | Got the green light from Amanda. Merged and committed to prod. Build is green and Amanda said it looked good. Moving to final review. Task status changed from In Testing to Final Review.
123 | 27604 | 2014-09-25 15:05 | 1.5 | Update the image handler to accpet png and gif files (Damien) | Landing Pages | Assisted Damien look for an error on Ektron pages not rendering png files. First looked at the code behind and found nothing wrong. Finally looked at the configuration files for Ektron and found out that .png was not in the list of accepted extension files.
86 | 27699 | 2014-09-30 18:22 | 2.5 | Add 2NAU picker to the TC Load Manager admin page (Talbert) | Admin Connect | Was assigned this task and talked to Jason and Amanda to get an idea how this task should be done. Task status changed from Assigned to In Progress.
86 | 27699 | 2014-09-30 18:30 | 7 | Add 2NAU picker to the TC Load Manager admin page (Talbert) | Admin Connect | Spent the day looking at the background code. This is all done with mustache.js and a lot of front end stuff. This changes my ideas on how to handle the user controls. I asked for a possible redesign from Jason. I am just looking over the code to see how this is all working.
86 | 27699 | 2014-09-30 18:33 | 8 | Add 2NAU picker to the TC Load Manager admin page (Talbert) | Admin Connect | I started to look at other examples of mustache but nothing really jumped out at me. I started to manipulate some code and was able to change up the scaffolding of the area. this will make it easier to add user controls and buttons to later.
86 | 27699 | 2014-09-30 18:35 | 7 | Add 2NAU picker to the TC Load Manager admin page (Talbert) | Admin Connect | contacted Eddie to see what resources he used to learn mustache. they helped out a bit. I started to mess with sql code for what i believe to be the direct area that effects what gets displayed to the front end. But my code did nothing to the view. Started to look at the structure of code in depth. I figured out how this all relates to MVC.
86 | 27699 | 2014-09-30 18:37 | 6 | Add 2NAU picker to the TC Load Manager admin page (Talbert) | Admin Connect | I am convinced that the area of code i am changing should be having an affect. I finally asked Damien for help. We debugged the code and found out that I was working with the right sql but my select statement was broken and returning null. I then used another version of the select statement and that worked. I am now able to show the 2nau campuses that are associated with a specific coordinator.
86 | 27699 | 2014-10-08 18:25 | 6 | Add 2NAU picker to the TC Load Manager admin page (Talbert) | Admin Connect | Had a discussion with Jason and at first I showed that his design was going to be difficult to implement. But then Damien said that it should not be that hard to implement the select2 stuff. I notified Jason and Amanda about this. Jason said that if I can get it to the design he created first he would prefer that. So I started to implement select2 stuff on this page.
86 | 27699 | 2014-11-06 01:59 | 0.5 | Add 2NAU picker to the TC Load Manager admin page (Talbert) | Admin Connect | Amanda tested and found one problem. She has made me a task for this. But for now she said this task can be moved to final review. Task status changed from In Progress to Final Review.
86 | 27806 | 2014-10-08 18:27 | 8 | Add 'Select To' to the TC Load Manager tool (Talbert) | Admin Connect | Continued to implement the Select2 library into the TcLoadManger project. By the end of the day, I was able to successfully get the library working and loading. but the area i was working with did not show up as a select2 element. Task status changed from Assigned to In Progress.
86 | 27806 | 2014-10-16 13:06 | 4 | Add 'Select To' to the TC Load Manager tool (Talbert) | Admin Connect | worked with select2 and jquery to toggle the view state of the select2 dropdown list. also started to pull information from the front end to see if i can start populating the dropdown with preselected tags.
86 | 27806 | 2014-10-16 13:11 | 8 | Add 'Select To' to the TC Load Manager tool (Talbert) | Admin Connect | attempt to change up structure to accommodate existing examples so i can get desired results.
86 | 27806 | 2014-10-22 13:40 | 5.5 | Add 'Select To' to the TC Load Manager tool (Talbert) | Admin Connect | Attempted to implement the Select2 tagging system. This is just so that you can select a campus and have it show up as a tag in the Select2 element.
86 | 27806 | 2014-10-22 13:45 | 8 | Add 'Select To' to the TC Load Manager tool (Talbert) | Admin Connect | Tried to continue working on this but could not figure it out so I asked Damien for help. With his help we were able to get the tagging system working. So now when the user hits the button to show the dropdown the Select2 is now populated with a tag of the current school the coordinator is assigned.
86 | 27806 | 2014-10-22 13:53 | 7 | Add 'Select To' to the TC Load Manager tool (Talbert) | Admin Connect | worked to get the Select2 to return information needed for later use. I needed Damien's help with this.
86 | 27806 | 2014-10-22 13:59 | 7 | Add 'Select To' to the TC Load Manager tool (Talbert) | Admin Connect | got the pulling of information done and posting it in the client side only. the database update will come later.
86 | 27806 | 2014-11-06 02:00 | 0.5 | Add 'Select To' to the TC Load Manager tool (Talbert) | Admin Connect | Amanda tested and found one problem. She has made me a task for this. But for now she said this task can be moved to final review.
86 | 27806 | 2014-11-06 02:00 | 0.1 | Add 'Select To' to the TC Load Manager tool (Talbert) | Admin Connect | Task status changed from In Progress to Final Review.
86 | 27807 | 2014-10-08 18:33 | 4 | Hook up 2NAU/TC Assignment UI to the tables (Talbert) | Admin Connect | now that the select2 stuff is in the project. I started to get the data all hooked up. I need to pull the list of campuses so that the select2 can have a list of campuses listed in the dropdown. this is not easy as the structure of the current code is much different than what i have worked with previously. Task status changed from Assigned to In Progress.
86 | 27807 | 2014-10-16 13:00 | 2 | Hook up 2NAU/TC Assignment UI to the tables (Talbert) | Admin Connect | Worked with Damien to get select2 working along with populating the dropdown list with campuses pulled from the backend. So we also got that working pulling the campus list.
86 | 27807 | 2014-10-16 13:07 | 1 | Hook up 2NAU/TC Assignment UI to the tables (Talbert) | Admin Connect | Display of the campus is done onload, but i am trying to get the information to populate the dropdown.
86 | 27807 | 2014-10-16 13:09 | 5 | Hook up 2NAU/TC Assignment UI to the tables (Talbert) | Admin Connect | spent the day trying to populate the dropdown with the preexisting information. how ever i run into javascript errors. Damien point out some other code i might be able to use.
86 | 27807 | 2014-10-16 13:10 | 8 | Hook up 2NAU/TC Assignment UI to the tables (Talbert) | Admin Connect | Attempted to use the code source Damien pointed out. Unfortunately looking at the source it was made for something more basic than what i am using. Looking at that I think I might be able to change the base code to fit the example better.
86 | 27807 | 2014-10-30 03:25 | 7 | Hook up 2NAU/TC Assignment UI to the tables (Talbert) | Admin Connect | Talked to Amanda to get an answer about how to handle the data insertion. I explained the different ways to do it. She said it would be best to talk to Covin or Vivek. Neither one was there. So she said to go with the way that will be easiest for me. And that would be to set all corresponding rows to the selected coordinator to inactive and add all new rows. i stared this process by pulling specific information that will be used in the methods.
86 | 27807 | 2014-10-30 03:25 | 2 | Hook up 2NAU/TC Assignment UI to the tables (Talbert) | Admin Connect | continued with pulling information to be used.
86 | 27807 | 2014-10-30 03:27 | 7 | Hook up 2NAU/TC Assignment UI to the tables (Talbert) | Admin Connect | Damien helped me get the ajax running. have not finished yet.
86 | 27807 | 2014-10-30 03:29 | 7 | Hook up 2NAU/TC Assignment UI to the tables (Talbert) | Admin Connect | Damien helped me again and this time we got very close to getting how I wanted to do this working 100%. but then we ran into an issue with insert permissions. We confronted Colvin and he pointed out this would not be the solution. and i would have to re-work the process to get insert the data and maintain a history. Damien and I, pseudo worked out the logic and i will work on that. I have notified Amanda about this.
86 | 27807 | 2014-11-06 01:30 | 4 | Hook up 2NAU/TC Assignment UI to the tables (Talbert) | Admin Connect | began the process to change the insertion and update sql so that it takes a list of active list and inactive list. the active list will inserts new rows with Effective_Status of A. The inactive list will update existing entries with Effective_Status of I.
86 | 27807 | 2014-11-06 01:42 | 8 | Hook up 2NAU/TC Assignment UI to the tables (Talbert) | Admin Connect | continued work reworking the logic for insertion and updates for adding and removing 2NAU campuses for coordinator.
86 | 27807 | 2014-11-06 01:46 | 6 | Hook up 2NAU/TC Assignment UI to the tables (Talbert) | Admin Connect | with Damien's help was able to finish the change in sql and code so that when a user updates a coordinator's 2NAU Campus assignment it will either insert a new row in the corresponding table with campus and Active status. If they remove a Campus it will look for those campuses and set the date and mark Inactive status.
86 | 27807 | 2014-11-06 02:00 | 0.5 | Hook up 2NAU/TC Assignment UI to the tables (Talbert) | Admin Connect | Amanda tested and found one problem. She has made me a task for this. But for now she said this task can be moved to final review. Task status changed from In Progress to Final Review.
311 | 27808 | 2014-10-08 18:29 | 8 | Merge thumbnail fix on Related Doc widget to Yuma and Yav (Talbert) | EC, Yuma, Yav, PL Widget Maintenance | This didn't seem that hard to implement but the environments (Yuma and Yavapai) were not close to how EC is. So I needed to look through the revisions to pull in not only my code but Damien's as well. End of the day I got all code and successful test done in Dev. Task status changed from Assigned to In Progress.
311 | 27808 | 2014-10-08 18:30 | 5 | Merge thumbnail fix on Related Doc widget to Yuma and Yav (Talbert) | EC, Yuma, Yav, PL Widget Maintenance | Finished up testing by merging and committed to test. I had to do some work with updating Ektron settings.
311 | 27808 | 2014-10-08 18:31 | 1 | Merge thumbnail fix on Related Doc widget to Yuma and Yav (Talbert) | EC, Yuma, Yav, PL Widget Maintenance | Emailed Amanda to let her know this is now in test. She responded back and has some questions. Task status changed from In Progress to In Testing.
311 | 27808 | 2014-10-10 10:32 | 3 | Merge thumbnail fix on Related Doc widget to Yuma and Yav (Talbert) | EC, Yuma, Yav, PL Widget Maintenance | Attempted to solve an issue Amanda saw. I looked at it all and tried to replicated the error and i could not. I presented what I tried to Amanda and she agreed that it might just be a strange bug on that one page. So, with her permission, I have merged and committed to prod.
311 | 27808 | 2014-10-10 10:33 | 1 | Merge thumbnail fix on Related Doc widget to Yuma and Yav (Talbert) | EC, Yuma, Yav, PL Widget Maintenance | Verified the merger and created some test pages in prod for Yuma and Yavapai. Both looked good. Moving this task to final review. Task status changed from In Testing to Final Review.
86 | 28179 | 2014-11-06 01:52 | 6 | TC/2NAU load manager cancel button | Admin Connect | When testing the code came quickly to the conclusion that the user interface is not well made. So I need to add the process such that the users hits the "2NAU" button and that will hide and show two buttons. A check mark that will "confirm" the changes the user wants to make. And a "X" to cancel out of the Select2 stuff. This is just the beginning and there are some code stuff to change. Task status changed from Assigned to In Progress.
86 | 28179 | 2014-11-06 01:58 | 8 | TC/2NAU load manager cancel button | Admin Connect | Finished up the user interface and tested it. Damien helped me with some logic stuff. I committed to dev. Tested and it looked good. Then merged and committed to test. Notified Amanda to test. Task status changed from In Progress to In Testing.
86 | 28179 | 2014-11-07 16:10 | 1 | TC/2NAU load manager cancel button | Admin Connect | merged and committed to prod. notified Amanda. She approved. Moving to final review. Task status changed from In Testing to Final Review.
86 | 28212 | 2014-11-06 02:04 | 8 | Fix Firefox issue with 'second edit' to 2NAU/TC field | Admin Connect | spent the day looking at this and trialed and error'd many things. At the end of the day I found the issue to be a quirk of Firefox. In the code i am setting some Option fields to be false then determine which ones should be true via jquery and .attr(). However, Firefox does not recognize .attr("selected", true). What does work and testing has confirmed is, .prop("selected", true). I have made the code change. Task status changed from Assigned to In Progress.
86 | 28212 | 2014-11-07 16:09 | 5 | Fix Firefox issue with 'second edit' to 2NAU/TC field | Admin Connect | finish testing in firefox. merged and committed to test. test this again in firefox then tested in chrome to make sure nothing has changed. notified Amanda to re-test. She tested and emailed me back saying this was looking good. I then merged and committed to prod. Notified Amanda. Moving this task to final review. Task status changed from In Testing to Final Review.
306 | 28234 | 2014-11-07 16:16 | 6 | Create distinct URLs for News, Press and Ideas on blog page | Site Management: Admin Blog Maintenance | looked over the code and evaluated how i should tackle the code. I then reviewed this with Damien and he gave me some better insight. I added if/else and switch/case logic. At the end of the day I have it so that a user can use the url like: /blog.aspx?filter=news. So i am pulling from a QueryString to show the right filter. The last part is to get the checked box to match which filter is chosen on pageload. Task status changed from Assigned to In Progress.
306 | 28234 | 2014-11-07 16:29 | 8 | Create distinct URLs for News, Press and Ideas on blog page | Site Management: Admin Blog Maintenance | worked on getting the checked box to be set on pageload. had to edit a inline if/else single line statement. Next worked on getting the url aliasing to accept /blog/news/ instead of /blog.aspx?filter=news. in doing so ran into some issues with ektron and not able to login. had to take some time to fix that issue first. after that got the url alias working. Committed and tested in dev. looked good. Merged and committed to test. Notified Amanda to test. Task status changed from In Progress to In Testing.
306 | 28234 | 2014-11-18 12:54 | 8 | Create distinct URLs for News, Press and Ideas on blog page | Site Management: Admin Blog Maintenance | Amanda had one last request. When a user clicks on one of the filter buttons it should change the URL Address to the new URL Aliasing. So I did some research today and found out this is going to take some time. The main thing is that I could change up the code so that what they want could be done. However, this would alter the code so much that I may as well re-engineer the whole page.
306 | 28234 | 2014-11-18 13:11 | 3 | Create distinct URLs for News, Press and Ideas on blog page | Site Management: Admin Blog Maintenance | Informed Amanda about the issue and explained that the current attempt to change the code would be a full on hack. and that the proper way to do this would be to re-engineer the page. she said that would be over doing the task. She was going to ask the client for clarification and get back to me.
306 | 28234 | 2014-11-18 13:13 | 1 | Create distinct URLs for News, Press and Ideas on blog page | Site Management: Admin Blog Maintenance | Amanda notified me that the current solution is acceptable and to move the code to prod. And research into alternative solutions are not needed now. I have merged and committed to prod. Moving this task to final review. Task status changed from In Testing to Final Review.
311 | 28254 | 2014-11-18 13:14 | 1 | Create scaffolding for the Testimonial widget | EC, Yuma, Yav, PL Widget Maintenance | Had a meeting with Jason, Damien, and Amanda to go over the specifics of the task. Task status changed from Assigned to In Progress.
311 | 28254 | 2014-12-11 02:40 | 8 | Create scaffolding for the Testimonial widget | EC, Yuma, Yav, PL Widget Maintenance | After the code copying was done I spent the day ensuring the scaffolding is all done. Got the widget to finally appear in the page. and able to get to edit mode.
311 | 28254 | 2014-12-11 02:41 | 1 | Create scaffolding for the Testimonial widget | EC, Yuma, Yav, PL Widget Maintenance | Notified Amanda that this part of the project could now be considered done. I have proposed three new tasks for me to start now. Moving this task to final review. Task status changed from In Progress to Final Review.
306 | 28289 | 2014-11-18 12:17 | 4 | Research hastag possibility for blog URL (Tal) | Site Management: Admin Blog Maintenance | After I informed Amanda of the issue of trying to do the clicking on a blog filter button will also change the URL Address, I said there was a possibility that I could change up the URL Aliasing from /Blog/News/ to /Blog.aspx#News. I tried the easiest trick by having Ektron work with the URL Aliasing. However, Ektron's URL Aliasing does not work with #. Amanda Informed me that the original solution is fine. This task will be closed.
311 | 28376 | 2014-11-20 11:55 | 7 | Scaffolding cont: Research structure to account for non-Ektron pages | EC, Yuma, Yav, PL Widget Maintenance | Looked at past code Damien wrote for reference. But looking at this I saw that there was a great deal of complexity to the code. I asked Damien about this and he told me that the code is this complex because the widget might not always be in an Ektron page it could be in a standard page. So his code could be placed in either. With that, we agreed that this new widget should be the same way. I began to map out which code i can start to migrate. Task status changed from Assigned to In Progress.
311 | 28376 | 2014-12-03 18:09 | 3 | Scaffolding cont: Research structure to account for non-Ektron pages | EC, Yuma, Yav, PL Widget Maintenance | As apart of me moving code from one source to another I have to modify the original structure to accommodate the new style for the widget.
311 | 28376 | 2014-12-03 18:10 | 3 | Scaffolding cont: Research structure to account for non-Ektron pages | EC, Yuma, Yav, PL Widget Maintenance | Continued to modify structure in tandem with coping code.
311 | 28376 | 2014-12-04 01:19 | 3 | Scaffolding cont: Research structure to account for non-Ektron pages | EC, Yuma, Yav, PL Widget Maintenance | found out i messed up file placement and code copying, cleaning up the mistake.
311 | 28376 | 2014-12-04 01:28 | 3 | Scaffolding cont: Research structure to account for non-Ektron pages | EC, Yuma, Yav, PL Widget Maintenance | I thought i had fixed the problem earlier and continued to migrate code over. Damien helped me some what finalize what code was needed. I thought at this point i was done but there is a strange error with visual studio.
311 | 28376 | 2014-12-04 01:28 | 3 | Scaffolding cont: Research structure to account for non-Ektron pages | EC, Yuma, Yav, PL Widget Maintenance | I thought i had fixed the problem earlier and continued to migrate code over. Damien helped me some what finalize what code was needed. I thought at this point i was done but there is a strange error with visual studio.
311 | 28376 | 2014-12-04 01:32 | 5 | Scaffolding cont: Research structure to account for non-Ektron pages | EC, Yuma, Yav, PL Widget Maintenance | still trying to figure out why visual studio will not properly compile my code
311 | 28376 | 2014-12-04 01:33 | 4 | Scaffolding cont: Research structure to account for non-Ektron pages | EC, Yuma, Yav, PL Widget Maintenance | Figured out that when i was fixing other code i had made a change to a namespace that changed the rest of ec on my machine. I reverted my code and got a lot less errors.
311 | 28376 | 2014-12-11 02:42 | 3 | Scaffolding cont: Research structure to account for non-Ektron pages | EC, Yuma, Yav, PL Widget Maintenance | Continued to work on this task.
311 | 28376 | 2014-12-11 02:43 | 4 | Scaffolding cont: Research structure to account for non-Ektron pages | EC, Yuma, Yav, PL Widget Maintenance | Finished up the code copy and finalized the structure.
311 | 28376 | 2014-12-11 02:43 | 1 | Scaffolding cont: Research structure to account for non-Ektron pages | EC, Yuma, Yav, PL Widget Maintenance | Notified Amanda that this part of the project could now be considered done. I have proposed three new tasks for me to start now. Moving this task to final review. Task status changed from In Progress to Final Review.
311 | 28395 | 2014-11-20 11:57 | 6 | Copy/Paste/Clean code from existing widget for back-end structure code | EC, Yuma, Yav, PL Widget Maintenance | began moving code over. later i realized that i was moving the wrong code. i found the right one and began again to copy code from existing works to be used in this widget. but it is not all 1 to 1 code. so i have to refine it as i go. Task status changed from Assigned to In Progress.
311 | 28395 | 2014-12-03 18:07 | 3 | Copy/Paste/Clean code from existing widget for back-end structure code | EC, Yuma, Yav, PL Widget Maintenance | Continue to copy and move code over to new widget.
311 | 28395 | 2014-12-03 18:08 | 3 | Copy/Paste/Clean code from existing widget for back-end structure code | EC, Yuma, Yav, PL Widget Maintenance | Continue to copy and move code over to new widget.
311 | 28395 | 2014-12-04 01:20 | 3 | Copy/Paste/Clean code from existing widget for back-end structure code | EC, Yuma, Yav, PL Widget Maintenance | found out i messed up file placement and code copying, cleaning up the mistake.
311 | 28395 | 2014-12-04 01:27 | 3 | Copy/Paste/Clean code from existing widget for back-end structure code | EC, Yuma, Yav, PL Widget Maintenance | I thought i had fixed the problem earlier and continued to migrate code over. Damien helped me some what finalize what code was needed. I thought at this point i was done but there is a strange error with visual studio.
311 | 28395 | 2014-12-04 01:35 | 5 | Copy/Paste/Clean code from existing widget for back-end structure code | EC, Yuma, Yav, PL Widget Maintenance | Solved another issue with the UserControl section as a variable was not recognized in the front end. I found out that they had some how got de-reference and i just had to "include in project". i then started to test the widget to be seen in the page.
311 | 28395 | 2014-12-11 02:43 | 3 | Copy/Paste/Clean code from existing widget for back-end structure code | EC, Yuma, Yav, PL Widget Maintenance | Continued to work on this task
311 | 28395 | 2014-12-11 02:44 | 4 | Copy/Paste/Clean code from existing widget for back-end structure code | EC, Yuma, Yav, PL Widget Maintenance | Finalized the code copy and structure stuff.
311 | 28395 | 2014-12-11 02:44 | 1 | Copy/Paste/Clean code from existing widget for back-end structure code | EC, Yuma, Yav, PL Widget Maintenance | Notified Amanda that this part of the project could now be considered done. I have proposed three new tasks for me to start now. Moving this task to final review. Task status changed from In Progress to Final Review.
311 | 28535 | 2014-12-11 02:48 | 6 | Testimonial widget: Make sure info is syncing correctly (Tal) | EC, Yuma, Yav, PL Widget Maintenance | Started to add information to the edit mode and see if they reflect in the front end. here i found issues with the title as it actually sets a title. I thought this would be the widget box title. And started the work to toggle the view of Image or Video sections. Task status changed from Assigned to In Progress.
311 | 28535 | 2014-12-19 11:29 | 8 | Testimonial widget: Make sure info is syncing correctly (Tal) | EC, Yuma, Yav, PL Widget Maintenance | accidentally changed this to change the widget box edit mode title. i reverted my changes because i will need this to be a title of the view mode box. Also started the addition to the video/image toggling.
311 | 28535 | 2014-12-24 14:21 | 8 | Testimonial widget: Make sure info is syncing correctly (Tal) | EC, Yuma, Yav, PL Widget Maintenance | There was actually a lot of code separated in to different area that i had to account for when getting the toggling of the image/video done. First got the code variable set to work with a none radio button. Then made sure that which variable was set only show that component on the published view. So if the variable is set to 0 then hide the image and video sections. Then if 1 show only image. etc.
311 | 28535 | 2014-12-24 14:35 | 5 | Testimonial widget: Make sure info is syncing correctly (Tal) | EC, Yuma, Yav, PL Widget Maintenance | Got the editmode to reflect the viewing of the edit controls to the none/image/video control. Right now it is not dynamic but if you select the control you want and save your selection will be saved and seen on the published view.
311 | 28535 | 2014-12-24 14:38 | 4 | Testimonial widget: Make sure info is syncing correctly (Tal) | EC, Yuma, Yav, PL Widget Maintenance | Got the jquery done so that the user can now choose none/image/video and the control will dynamically show/hide based on the radiobutton click. Now I have ensured that the selection made is saved and working to show the image/video on the front end. so far...good.
311 | 28535 | 2015-01-21 17:51 | 0.1 | Testimonial widget: Make sure info is syncing correctly (Tal) | EC, Yuma, Yav, PL Widget Maintenance | got new tasks so I will final review this task and log time to the new ones. Task status changed from In Progress to Final Review.
311 | 28536 | 2014-12-11 02:45 | 8 | Testimonial widget: Stylize edit mode (Tal) | EC, Yuma, Yav, PL Widget Maintenance | Stylized up the edit mode so now it fits better in the widget space. Task status changed from Assigned to In Progress.
311 | 28536 | 2014-12-19 11:31 | 8 | Testimonial widget: Stylize edit mode (Tal) | EC, Yuma, Yav, PL Widget Maintenance | worked on getting the toggling of the video/image area. but realized that i needed somehow to save the information so that the users choice is not reset every session. so i worked on saving the data and opening the edit mode with the proper view.
311 | 28536 | 2014-12-19 11:33 | 8 | Testimonial widget: Stylize edit mode (Tal) | EC, Yuma, Yav, PL Widget Maintenance | forgot to include an option for no image or video. added this radio button in and got it to show the proper view when going to edit mode.
311 | 28536 | 2015-01-21 17:52 | 0.1 | Testimonial widget: Stylize edit mode (Tal) | EC, Yuma, Yav, PL Widget Maintenance | got new tasks so I will final review this task and log time to the new ones. Task status changed from In Progress to Final Review.
311 | 28537 | 2014-12-19 11:37 | 8 | Testimonial widget: Stylize front end (Tal) | EC, Yuma, Yav, PL Widget Maintenance | worked on cleaning up the css front end stuff. i discovered that Damien's css is rather rushed and not very self contained. also changed out the image filepaths and eventually got the substitute image to show. Task status changed from Assigned to In Progress.
311 | 28537 | 2014-12-19 11:46 | 6 | Testimonial widget: Stylize front end (Tal) | EC, Yuma, Yav, PL Widget Maintenance | after cleaning up the css i found out that I did not import another css correctly. I changed up the css so that i was pulling from the same source to have a stylized box with a title in the top and single line out line.
311 | 28537 | 2014-12-24 14:39 | 4 | Testimonial widget: Stylize front end (Tal) | EC, Yuma, Yav, PL Widget Maintenance | worked on stylizing the font and getting more information from Jason. There was a bit of confusion between comps. that was cleared and started to get the text area in place.
311 | 28537 | 2014-12-24 14:40 | 8 | Testimonial widget: Stylize front end (Tal) | EC, Yuma, Yav, PL Widget Maintenance | continued to stylize the front end.
311 | 28537 | 2015-01-07 17:07 | 8 | Testimonial widget: Stylize front end (Tal) | EC, Yuma, Yav, PL Widget Maintenance | got into the nitty gritty of moving the image of the person around at different screen sizes and associated font sizes. found some bugs with global css. ended the day with added person image done and started video insertion.
311 | 28537 | 2015-01-07 17:10 | 8 | Testimonial widget: Stylize front end (Tal) | EC, Yuma, Yav, PL Widget Maintenance | continued with css stylization with added video into the widget. ran into some dynamic css issues from legacy code. I confirmed with Damien that this was as intended. coded around that and got the placement and resizing of the video correctly down.
311 | 28537 | 2015-01-07 17:11 | 6.5 | Testimonial widget: Stylize front end (Tal) | EC, Yuma, Yav, PL Widget Maintenance | Finished up the associated font styling with added video. moved on to quote text only stylization. finished that up and published to dev.
311 | 28537 | 2015-01-14 17:22 | 1 | Testimonial widget: Stylize front end (Tal) | EC, Yuma, Yav, PL Widget Maintenance | Notified Jason that this task was in dev and I requested that his team provide me final design. This will include final images, font size at specific screen sizes, and overall design.
311 | 28537 | 2015-01-14 18:14 | 5 | Testimonial widget: Stylize front end (Tal) | EC, Yuma, Yav, PL Widget Maintenance | Checked in with Jason about styling review. He told me he assigned Dalasie on the task. I asked him about it. After some time Dalasie provided me style code and was able to add in the quotation marks. I reviewed the code first.
311 | 28537 | 2015-01-14 18:16 | 6 | Testimonial widget: Stylize front end (Tal) | EC, Yuma, Yav, PL Widget Maintenance | Began implementing the style stuff. Ran into an issue with images that sparked a meeting with Jason, Damien, Dalasie, and I. We worked out how retina images should be implemented for this widget. I continued to implement Dalasie's style code.
311 | 28537 | 2015-01-21 17:52 | 0.1 | Testimonial widget: Stylize front end (Tal) | EC, Yuma, Yav, PL Widget Maintenance | got new tasks so I will final review this task and log time to the new ones. Task status changed from In Progress to Final Review.
88 | 28700 | 2014-12-22 12:16 | 0.5 | Computer Support issues with quicktask | Admin TME Maintenance | Helped Adam with some pageload variable assignment.
86 | 28760 | 2015-01-14 17:57 | 1 | Timeouts in TC Load Manager | Admin Connect | Not sure if this is the task to assign time to, but I helped Dave debug (or at least reminded him how to) prod stuff.
296 | 28794 | 2015-01-14 17:31 | 1 | New Player - update to latest version | new video player | Helped Dylan get into the Ektron side of editing.
299 | 28807 | 2015-01-15 12:20 | 2 | designing application architecutre and data requirements | State Regulatory Compliance | Meeting with Kyle, Jason, Damien, Sam, Sheri, and I to discuss the initial planning outlook for Compliance Database project. Followed by a meeting without Sheri to discuss more in details the specifics of the project.
299 | 28807 | 2015-01-15 12:21 | 1 | designing application architecutre and data requirements | State Regulatory Compliance | Meeting with Sam, Damien, Jason, and I to review over initial UML diagrams that Damien drafted up.
299 | 28833 | 2015-01-21 18:52 | 2 | Planning Development Tasks and Architecture | State Regulatory Compliance | Meeting with Damien to discuss initial time estimates for front end tasks for Compliance
299 | 28833 | 2015-01-21 18:53 | 0.5 | Planning Development Tasks and Architecture | State Regulatory Compliance | Meeting with Damien to discuss initial time estimates for front end tasks for Compliance
299 | 28880 | 2015-02-05 14:16 | 6 | Set-up Search View | State Regulatory Compliance | Started to do this on my own to find the location and develop the MVC views myself. I unfortunately failed. Task status changed from Assigned to In Progress.
299 | 28880 | 2015-02-05 14:17 | 5 | Set-up Search View | State Regulatory Compliance | Brought in Damien to help develop the starting environment for MVC. However all code we made was not working at all.
299 | 28880 | 2015-02-05 14:22 | 6 | Set-up Search View | State Regulatory Compliance | Finally working with Sam and Damien and SW Adam we found out that the MVC in Visual studio has to be auto code generated in order to just to setup the environment. At the end of the day we have the environment all set up.
299 | 28880 | 2015-02-12 17:13 | 7 | Set-up Search View | State Regulatory Compliance | The environment is all setup, but ran into some issues with viewing a page and modifying the page. Damien helped me out and got it working. I was able to get a page started with basic html written to the page.
299 | 28880 | 2015-02-12 17:37 | 6 | Set-up Search View | State Regulatory Compliance | worked to get the toggling between two views on this page.
299 | 28880 | 2015-02-12 17:43 | 3 | Set-up Search View | State Regulatory Compliance | final bootstrap review. then merged and committed to dev. this was my first time with this new system and took extra precautions to make sure this was build successfully. emailed Kyle about how we should treat these types of task. as they do not need to go to prod; because it is not a full deliverable. I talked to Damien about this earlier and we came to this conclusion.
299 | 28880 | 2015-02-19 16:09 | 1 | Set-up Search View | State Regulatory Compliance | Kyle emailed me back with his response. He would have liked it to go to prod but differed to my discretion. I think it would be better to commit to dev until there is a deliverable. But with that Kyle is happy with the code. So I will move this task to final review. Task status changed from In Progress to Final Review.
299 | 28881 | 2015-02-19 18:06 | 5 | Create State table cell from state search | State Regulatory Compliance | started this task and got the simple structure down. Task status changed from Assigned to In Progress.
299 | 28881 | 2015-02-19 18:11 | 6 | Create State table cell from state search | State Regulatory Compliance | I tried get the structure down to have a two column with boot strap. but I could not figure out how to do the auto fill of one side then start filling the second column. Damien pointed me to Degree Search on EC and this showed how a webkit handles objects in a div to auto column-ized the content.
299 | 28881 | 2015-02-19 18:14 | 8 | Create State table cell from state search | State Regulatory Compliance | there was a meeting today with Kyle to update our current status of the tasks. I notified him that i will be needing some new mock-ups soon for the State Details page. I need some image stuff from the designers too. I then worked on a bit of the style and got it done.
299 | 28881 | 2015-02-26 16:32 | 2 | Create State table cell from state search | State Regulatory Compliance | Final go-over of styling and what I think is needed for later functionality. I think this is ready for testing.
299 | 28881 | 2015-03-12 11:40 | 1 | Create State table cell from state search | State Regulatory Compliance | Committed to dev.
299 | 28881 | 2015-03-12 11:43 | 0.1 | Create State table cell from state search | State Regulatory Compliance | Emailed Kyle to test. Task status changed from In Progress to In Testing.
299 | 28881 | 2015-03-12 11:46 | 0.5 | Create State table cell from state search | State Regulatory Compliance | Kyle approved. Moving task to final review Task status changed from In Testing to Final Review.
299 | 28882 | 2015-02-12 17:27 | 4 | create state filter section | State Regulatory Compliance | Without realizing it I started this task and forgot to assign it to myself. But starting to generate the scaffolding and the Bootstrap components I ran into some issues with the page recognizing some scripts. Task status changed from Assigned to In Progress.
299 | 28882 | 2015-02-12 17:35 | 4 | create state filter section | State Regulatory Compliance | fixed the issues with importing scripts. got the scaffolding and started the bootstrap stuff. I pretty much got this done. I realized at this point i missed the toggling between pages.
299 | 28882 | 2015-02-12 17:43 | 2.5 | create state filter section | State Regulatory Compliance | final bootstrap review. then merged and committed to dev.
299 | 28882 | 2015-02-19 16:10 | 1 | create state filter section | State Regulatory Compliance | I got a response back from Kyle. He is happy with the code. So I will move this task to final review. Task status changed from In Progress to Final Review.
299 | 28883 | 2015-04-29 18:06 | 7 | create state filter keyword method | State Regulatory Compliance | Had to confirm with Kyle that we are in fact going to search on state name. Damien had already contacted Jason and got this confirmation but i wanted a secondary opinion. I integrated the filter and this is done. I also did work on adding another option to State Search dropdown list; "In Progress". Lastly fixed an issue where someone didn't remove an extra space in razor to a data field. This was causing an issue. Task status changed from Assigned to In Progress.
299 | 28883 | 2015-04-29 18:07 | 1 | create state filter keyword method | State Regulatory Compliance | Merged all other tasks in addition to this one to test. Emailed Kyle to test. Task status changed from In Progress to In Testing.
299 | 28883 | 2015-05-06 15:10 | 0.1 | create state filter keyword method | State Regulatory Compliance | Kyle approved. Moving to final review. Task status changed from In Testing to Final Review.
299 | 28884 | 2015-04-23 12:47 | 6 | Filter Status Dropdown | State Regulatory Compliance | Began work on the javascript code. Task status changed from Assigned to In Progress.
299 | 28884 | 2015-04-23 13:07 | 2 | Filter Status Dropdown | State Regulatory Compliance | got this and the SARA partner all fixed.
299 | 28884 | 2015-04-29 17:46 | 8 | Filter Status Dropdown | State Regulatory Compliance | While working another task Damien helped me make that more efficient and better all around. But I had to rework this section for both State and Program search.
299 | 28884 | 2015-04-29 17:47 | 0.5 | Filter Status Dropdown | State Regulatory Compliance | Emailed Kyle to test Task status changed from In Progress to In Testing.
299 | 28884 | 2015-05-06 15:10 | 0.1 | Filter Status Dropdown | State Regulatory Compliance | Kyle approved. Moving to final review. Task status changed from In Testing to Final Review.
299 | 28885 | 2015-04-23 12:58 | 8 | Filter Sera Partner | State Regulatory Compliance | some logic errors got me on this and had a brain freeze on trying to integrate it with the drop down logic. Task status changed from Assigned to In Progress.
299 | 28885 | 2015-04-29 17:53 | 3 | Filter Sera Partner | State Regulatory Compliance | Earlier in the week Damien helped me write a more efficient filtering method. I finally got to incorporate the SARA Partner filtering into this method. So I need to touch on this again. But now it should be all done.
299 | 28885 | 2015-04-29 17:53 | 0.5 | Filter Sera Partner | State Regulatory Compliance | Emailed Kyle to test this. Task status changed from In Progress to In Testing.
299 | 28885 | 2015-05-06 15:09 | 0.1 | Filter Sera Partner | State Regulatory Compliance | Kyle approved. Moving to final review. Task status changed from In Testing to Final Review.
299 | 28886 | 2015-02-19 18:16 | 8 | Create Progrram table from program | State Regulatory Compliance | started work on this task. this was actually more complicated, code, wise than i expected. I wrestled with the structure just to have the toggling of the area blow it to show/hide. Task status changed from Assigned to In Progress.
299 | 28886 | 2015-02-19 18:17 | 8 | Create Progrram table from program | State Regulatory Compliance | I worked on the structure for the three tiles in the hidden area. I got the structure all done and got good work done on styling.
299 | 28886 | 2015-02-26 17:30 | 4 | Create Progrram table from program | State Regulatory Compliance | I began work on structuring the tiles in the three column area of the hidden div.
299 | 28886 | 2015-02-26 17:35 | 6 | Create Progrram table from program | State Regulatory Compliance | continued to style the tiles in the three column area. also had a quick meeting with Kyle to update him where i am at in the project.
299 | 28886 | 2015-02-26 17:38 | 8 | Create Progrram table from program | State Regulatory Compliance | I thought i had gotten this done but I found an issue with styling alternate row coloring. I had to restructure the tile again.
299 | 28886 | 2015-02-26 17:51 | 4 | Create Progrram table from program | State Regulatory Compliance | Got the structure down so that the alternate rows work with the smaller tiles. Then finished the overall styling. I think this might be ready for testing.
299 | 28886 | 2015-03-12 11:40 | 1 | Create Progrram table from program | State Regulatory Compliance | Committed to dev.
299 | 28886 | 2015-03-12 11:43 | 0.1 | Create Progrram table from program | State Regulatory Compliance | Emailed Kyle to test. Task status changed from In Progress to In Testing.
299 | 28886 | 2015-03-12 11:45 | 0.5 | Create Progrram table from program | State Regulatory Compliance | Kyle approved. Moving task to final review Task status changed from In Testing to Final Review.
299 | 28887 | 2015-04-23 12:25 | 0.1 | create expandable internship requirement and licensure section | State Regulatory Compliance | this is actually done a long time ago. i'm gonna move this task to final review. Task status changed from Assigned to Final Review.
299 | 28888 | 2015-02-12 17:39 | 4 | create program filter section | State Regulatory Compliance | started work on this view of the page. got the scaffolding and bootstrap stuff done. Task status changed from Assigned to In Progress.
299 | 28888 | 2015-02-12 17:44 | 2.5 | create program filter section | State Regulatory Compliance | final bootstrap review. then merged and committed to dev.
299 | 28888 | 2015-02-19 16:10 | 1 | create program filter section | State Regulatory Compliance | I got a response back from Kyle. He is happy with the code. So I will move this task to final review.
299 | 28888 | 2015-02-19 16:10 | 0.1 | create program filter section | State Regulatory Compliance | Task status changed from In Progress to Final Review.
299 | 28889 | 2015-04-29 17:58 | 5 | create program filter keyword method | State Regulatory Compliance | This is actually tricky for me. I am trying to figure out how to search on the substring of an attribute but still keep filtering. Task status changed from Assigned to In Progress.
299 | 28889 | 2015-04-29 17:59 | 8 | create program filter keyword method | State Regulatory Compliance | Damien was able to help me grasp this better and I figured out how to incorporate this into my existing filter method. had some hiccups with the correct jquery function but I got it.
299 | 28889 | 2015-04-29 18:00 | 0.5 | create program filter keyword method | State Regulatory Compliance | Emailed Kyle to test. Task status changed from In Progress to In Testing.
299 | 28889 | 2015-05-06 15:09 | 0.5 | create program filter keyword method | State Regulatory Compliance | Kyle approved. Moving to final review. Task status changed from In Testing to Final Review.
299 | 28890 | 2015-04-23 13:09 | 5 | create filter program level method | State Regulatory Compliance | started working on Javascript code for this Task status changed from Assigned to In Progress.
299 | 28890 | 2015-04-23 13:10 | 8 | create filter program level method | State Regulatory Compliance | There are some missing data missing from the comp for me to work off of. I asked around and found the information i needed. continued work on this. this is a bit more tricky than State search because of the multiple checkboxes.
299 | 28890 | 2015-04-29 17:48 | 3 | create filter program level method | State Regulatory Compliance | Worked to re-do the entire filtering section.
299 | 28890 | 2015-04-29 17:48 | 0.5 | create filter program level method | State Regulatory Compliance | Emailed Kyle to test. Task status changed from In Progress to In Testing.
299 | 28890 | 2015-05-06 15:09 | 0.5 | create filter program level method | State Regulatory Compliance | Kyle approved. Moving to final review. Task status changed from In Testing to Final Review.
299 | 28891 | 2015-04-23 13:08 | 0.1 | create program checkbox filters | State Regulatory Compliance | this was actually done a while back. I will move this task to final review. Task status changed from Assigned to Final Review.
299 | 28892 | 2015-02-26 17:56 | 4 | Create State Compliance Layout | State Regulatory Compliance | Had to do some meetings with designers as the layout for this page was changed. After we got that all sorted I was able to start the layout stuff. Task status changed from Assigned to In Progress.
299 | 28892 | 2015-03-05 18:38 | 4 | Create State Compliance Layout | State Regulatory Compliance | continued adding components to the page.
299 | 28892 | 2015-03-05 18:41 | 8 | Create State Compliance Layout | State Regulatory Compliance | finished up nav and page layout and started to add components to the page
299 | 28892 | 2015-03-12 11:41 | 1 | Create State Compliance Layout | State Regulatory Compliance | Committed to dev.
299 | 28892 | 2015-03-12 11:43 | 0.1 | Create State Compliance Layout | State Regulatory Compliance | Emailed Kyle to test. Task status changed from In Progress to In Testing.
299 | 28892 | 2015-03-12 11:45 | 0.5 | Create State Compliance Layout | State Regulatory Compliance | Kyle approved. Moving task to final review
299 | 28892 | 2015-03-12 11:45 | 0.1 | Create State Compliance Layout | State Regulatory Compliance | Task status changed from In Testing to Final Review.
299 | 28893 | 2015-03-12 11:52 | 6 | Scaffold view state tile | State Regulatory Compliance | I forgot to give myself a task to scaffold and bootstrap-ify the area below the stat title stuff. so i am adding that work to this task. Task status changed from Assigned to In Progress.
299 | 28893 | 2015-03-26 10:13 | 8 | Scaffold view state tile | State Regulatory Compliance | Worked on this task and got a good portion of this done. Later I found out I only did the "Group Tile" version. I then did the "regular tile" version. There is still somethings to get done to finish this up. I will pick this back up after the edit state is done.
299 | 28893 | 2015-04-02 11:37 | 7 | Scaffold view state tile | State Regulatory Compliance | picked this back up after getting like 90% of the edit view done. i added in the components that match up with the edit view. then started to do styling on both the viewstate and editstate.
299 | 28893 | 2015-04-09 03:17 | 2 | Scaffold view state tile | State Regulatory Compliance | Finished up the code and stylization.
299 | 28893 | 2015-04-09 03:18 | 1 | Scaffold view state tile | State Regulatory Compliance | Committed to dev and emailed Kyle to test. Task status changed from In Progress to In Testing.
299 | 28893 | 2015-04-09 17:15 | 0.1 | Scaffold view state tile | State Regulatory Compliance | Because a new task had me redesign the original source I am going to final review this task. Kyle never got back to me about this but the new one is in test. Task status changed from In Testing to Final Review.
299 | 28894 | 2015-03-26 10:14 | 8 | Scaffold edit state tile | State Regulatory Compliance | Started work in adding all the components and structure right now. Task status changed from Assigned to In Progress.
299 | 28894 | 2015-04-02 11:29 | 7 | Scaffold edit state tile | State Regulatory Compliance | Started work on the edit view of a regular tile. working mainly on scaffolding for the section again.
299 | 28894 | 2015-04-02 11:32 | 6 | Scaffold edit state tile | State Regulatory Compliance | Worked on adding input controls for the description, links, and notes.
299 | 28894 | 2015-04-02 11:34 | 7 | Scaffold edit state tile | State Regulatory Compliance | Had to ask a few questions about clarity of the structure of all the components. as all of it was spread out. I think I got majority of the edit stuff done.
299 | 28894 | 2015-04-09 03:15 | 2 | Scaffold edit state tile | State Regulatory Compliance | finished up the edit state and got the styling done.
299 | 28894 | 2015-04-09 03:16 | 1 | Scaffold edit state tile | State Regulatory Compliance | Committed to dev and email Kyle to test. Task status changed from In Progress to In Testing.
299 | 28894 | 2015-04-09 17:15 | 0.1 | Scaffold edit state tile | State Regulatory Compliance | Because a new task had me redesign the original source I am going to final review this task. Kyle never got back to me about this but the new one is in test. Task status changed from In Testing to Final Review.
299 | 28895 | 2015-04-16 10:55 | 7 | scaffold empty tile section | State Regulatory Compliance | created new section with two buttons. all done. Task status changed from Assigned to In Progress.
299 | 28895 | 2015-04-29 17:39 | 0.5 | scaffold empty tile section | State Regulatory Compliance | Emailed Kyle to test this Task status changed from In Progress to In Testing.
299 | 28895 | 2015-05-06 15:08 | 0.5 | scaffold empty tile section | State Regulatory Compliance | Kyle approved. Moving to final review. Task status changed from In Testing to Final Review.
299 | 28896 | 2015-05-06 17:49 | 8 | pull flag on state details | State Regulatory Compliance | had to wait a bit on this because I asked around on where i should get the flag images. I first tried to pull from free sources on the net but nothing really worked. I ended up pulling the images from wiki and placing them into a folder in the images folder. then asked Damien to provide me a better angular variable to pull the images from. Task status changed from Assigned to In Progress.
299 | 28896 | 2015-05-06 17:55 | 0.5 | pull flag on state details | State Regulatory Compliance | Presented this during the meeting and Kyle approved so I am moving this task to final review. Task status changed from In Progress to Final Review.
299 | 28897 | 2015-04-16 10:53 | 6 | skin additional approvals | State Regulatory Compliance | mainly copied code from search page. this should be done now.
299 | 28897 | 2015-04-16 11:01 | 6 | skin additional approvals | State Regulatory Compliance | I don't have another task for this work but I worked on a control to change the status of the State Approval. This is only bootstrap controls and visual stuff.
299 | 28897 | 2015-04-23 11:35 | 2 | skin additional approvals | State Regulatory Compliance | I updated my revisions and found a lot of conflicts. it took me a while to sort it all out.
299 | 28897 | 2015-04-29 17:37 | 0.5 | skin additional approvals | State Regulatory Compliance | Emailed Kyle to test this. Task status changed from In Progress to In Testing.
299 | 28897 | 2015-05-06 15:07 | 0.5 | skin additional approvals | State Regulatory Compliance | kyle approved moving to final review.
299 | 28897 | 2015-05-06 15:07 | 0.1 | skin additional approvals | State Regulatory Compliance | Task status changed from In Testing to Final Review.
299 | 28898 | 2015-05-06 17:35 | 4 | write javascript to filter selections | State Regulatory Compliance | Began work to filter on state search. pulling from angular data attributes and processing them into in the monolithic jquery function I created for checkbox filtering. Task status changed from Assigned to In Progress.
299 | 28898 | 2015-05-06 17:42 | 6 | write javascript to filter selections | State Regulatory Compliance | Finished up the jquery function alteration to filter by textfield entry. I then implemented it on state search. I then applied the code change to program search.
299 | 28898 | 2015-05-06 17:56 | 0.5 | write javascript to filter selections | State Regulatory Compliance | Presented this during our meeting. Kyle approved so I'm gonna place this in final review. Task status changed from In Progress to Final Review.
299 | 28898 | 2015-05-06 17:57 | 0.1 | write javascript to filter selections | State Regulatory Compliance | Task status changed from Final Review to Assigned.
299 | 28898 | 2015-05-06 17:57 | 0.1 | write javascript to filter selections | State Regulatory Compliance | Task status changed from Assigned to Final Review.
299 | 28899 | 2015-05-18 14:59 | 1 | finalize styling | State Regulatory Compliance | Jason emailed me and said that Dalasie will be picking up the review of Details page. Later I somewhat caught up with Dalasie and tried to explain how Details page worked. Task status changed from Assigned to In Progress.
299 | 28899 | 2015-05-18 15:26 | 8 | finalize styling | State Regulatory Compliance | Dalasie provided me the first round of changes. I noticed that he was using the Balsamic Wireframe as the final design. We had some miscommunication. I had to explain to him that I didn't have a final design from anyone. And the balsamic should only be used as a wireframe only; not end all, be all design. I then started the changes to the Details page.
299 | 28899 | 2015-05-20 15:05 | 4 | finalize styling | State Regulatory Compliance | Continued to work on stuff from Dalasie. He provided more input by adding two more drafts of what is to be done. I work on some of this today.
299 | 28899 | 2015-05-20 15:50 | 8 | finalize styling | State Regulatory Compliance | Finished what I could from Dalasie's list. Somethings I cannot do because I am waiting on some components from Damien.
299 | 28899 | 2015-05-20 16:06 | 0.1 | finalize styling | State Regulatory Compliance | Kyle is going to give Damien and I new tasks for the finishing of the project. So I will move this task to final review. Task status changed from In Progress to Final Review.
311 | 28910 | 2015-01-21 18:55 | 6 | Testimonial widget: person overlaps quote at some page widths | EC, Yuma, Yav, PL Widget Maintenance | I had originally committed all my current code for testimonial widget to dev and tested it to make sure it was good. After that I committed to test. Notified Amanda to test. Task status changed from Assigned to In Progress.
311 | 28910 | 2015-01-21 19:06 | 6 | Testimonial widget: person overlaps quote at some page widths | EC, Yuma, Yav, PL Widget Maintenance | looked into this task and messed around with changing css. the problem is much bigger than i thought and may lie in Dalasie code.
311 | 28910 | 2015-01-21 19:08 | 8 | Testimonial widget: person overlaps quote at some page widths | EC, Yuma, Yav, PL Widget Maintenance | worked it out that the css is working on the image to be an arbitrary size and grows as a percentage. This gets messed up as a widget when placed in the main area of the page. I brought up this issue with Jason and informed him the images i got from Dalasie will not work as we had originally planned them. He then got Joshua give me the right size images.
311 | 28910 | 2015-01-21 19:10 | 6 | Testimonial widget: person overlaps quote at some page widths | EC, Yuma, Yav, PL Widget Maintenance | The images that Joshua gave me are a bit off. Jason then personally gave me the images i needed. I then was able incorporate them into the code and got the page to work....i think. Well I then merged and committed the code to test. and notified Amanda to re-test. Task status changed from In Progress to In Testing.
311 | 28910 | 2015-01-28 18:57 | 8 | Testimonial widget: person overlaps quote at some page widths | EC, Yuma, Yav, PL Widget Maintenance | Amanda found some styling issues. This required a meeting with Jason to figure out how to move the image person to allow more room for larger quotes. Then I took the time to clean up CSS rules and ensure all forms of screen sizes looked good for widgets that had a person in them.
311 | 28910 | 2015-01-28 19:02 | 8 | Testimonial widget: person overlaps quote at some page widths | EC, Yuma, Yav, PL Widget Maintenance | Finished up styling for all version of widgets; without image, with video, etc. published to test and had Amanda test again. She approved then requested this code be migrated to Yuma and Yavapai. I then spent the rest of the day migrating this code to all version of Yuma and Yavapai (dev, test, and prod). Amanda has approved the EC version and I checked the Yuma and Yavapai testpages. So...I'm gonna move to final review. Task status changed from In Testing to Final Review.
311 | 28911 | 2015-01-21 18:58 | 6 | Testimonial widget: add padding to bottom of the 'person' version of the widget | EC, Yuma, Yav, PL Widget Maintenance | Amanda got back to me about testing and revealed to me the error present for this task and the other task i have. She then created these tasks for me. I then looked into this task and found a solution. I added a padding-bottom to the main area. Task status changed from Assigned to In Progress.
311 | 28911 | 2015-01-21 19:13 | 0.1 | Testimonial widget: add padding to bottom of the 'person' version of the widget | EC, Yuma, Yav, PL Widget Maintenance | committed to test Task status changed from In Progress to In Testing.
311 | 28911 | 2015-01-28 19:03 | 0.1 | Testimonial widget: add padding to bottom of the 'person' version of the widget | EC, Yuma, Yav, PL Widget Maintenance | Amanda approved EC version and I checked the Yuma and Yavapai testpages. So...I am going to go ahead and move to final review. Task status changed from In Testing to Final Review.
299 | 29233 | 2015-03-05 18:37 | 8 | Scaffold Nav bar (in conjunction with details page scaffolding) | State Regulatory Compliance | forgot i requested to have this task made. This is to be done in conjunction with general scaffolding. I attempted several types of solutions; one type was trying to maintain responsive-ness for the nav menu. in the end i had to go with a structure that keeps the nav menu as one size and the other side can be responsive. Task status changed from Assigned to In Progress.
299 | 29233 | 2015-03-12 11:41 | 1 | Scaffold Nav bar (in conjunction with details page scaffolding) | State Regulatory Compliance | Committed to dev.
299 | 29233 | 2015-03-12 11:42 | 1 | Scaffold Nav bar (in conjunction with details page scaffolding) | State Regulatory Compliance | Meeting with Kyle, Damien, Sam, and myself. Explained that these task are ready for testing. Later I emailed Kyle to test Task status changed from In Progress to In Testing.
299 | 29233 | 2015-03-12 11:44 | 0.1 | Scaffold Nav bar (in conjunction with details page scaffolding) | State Regulatory Compliance | Emailed Kyle to test.
299 | 29233 | 2015-03-12 11:44 | 0.5 | Scaffold Nav bar (in conjunction with details page scaffolding) | State Regulatory Compliance | Kyle approved. Moving task to final review Task status changed from In Testing to Final Review.
299 | 29234 | 2015-03-12 11:48 | 6 | Generate bootstrap component Nav bar | State Regulatory Compliance | began to start this task by adding in components Task status changed from Assigned to In Progress.
299 | 29234 | 2015-03-20 12:04 | 8 | Generate bootstrap component Nav bar | State Regulatory Compliance | I forgot to ask Kyle to make a new task for me and I need to generate time for reporting so I am logging the time here. I started work to add components and bootstrap stuff for the navigation bar on the right hand side. This will include stylization. Today was getting scaffolding down.
299 | 29234 | 2015-03-20 12:07 | 6 | Generate bootstrap component Nav bar | State Regulatory Compliance | Worked on Nav bar Side. worked on the scaffolding for the secondary level.
299 | 29234 | 2015-03-20 12:12 | 8 | Generate bootstrap component Nav bar | State Regulatory Compliance | worked on stylization and javascript component for clicking a button to expand secondary level.
299 | 29234 | 2015-03-20 12:13 | 8 | Generate bootstrap component Nav bar | State Regulatory Compliance | This took me too long but finally got the javascript portion done and now the nav bar can expand and collapse with style. this (sub) task is done.
299 | 29234 | 2015-03-26 09:23 | 0.1 | Generate bootstrap component Nav bar | State Regulatory Compliance | I got a new task but I think this stuff is done. I'm gonna final review this task and log new entries to the new task. Task status changed from In Progress to Final Review.
299 | 29235 | 2015-03-26 10:10 | 2 | Scaffold Group tile with Bootstrap components | State Regulatory Compliance | started this task but realize that this can't really done without the other components structure first. Task status changed from Assigned to In Progress.
299 | 29235 | 2015-04-09 03:19 | 2 | Scaffold Group tile with Bootstrap components | State Regulatory Compliance | Migrated code I did for Edit/View state and modify it to work the same as those ones.
299 | 29235 | 2015-04-09 03:20 | 2 | Scaffold Group tile with Bootstrap components | State Regulatory Compliance | Finished up the component stuff.
299 | 29235 | 2015-04-09 03:20 | 1 | Scaffold Group tile with Bootstrap components | State Regulatory Compliance | Committed to Dev and email Kyle to test. Task status changed from In Progress to In Testing.
299 | 29235 | 2015-04-09 17:15 | 0.1 | Scaffold Group tile with Bootstrap components | State Regulatory Compliance | Because a new task had me redesign the original source I am going to final review this task. Kyle never got back to me about this but the new one is in test. Task status changed from In Testing to Final Review.
299 | 29686 | 2015-03-26 09:41 | 1 | Nav Bar - Create bootstrap components and Toggle views | State Regulatory Compliance | emailed Kyle to test this task. Task status changed from Assigned to In Testing.
299 | 29686 | 2015-04-02 11:02 | 1 | Nav Bar - Create bootstrap components and Toggle views | State Regulatory Compliance | Kyle Approved. Moving task to final review. Task status changed from In Testing to Final Review.
299 | 29742 | 2015-05-06 17:58 | 4 | final styling with Jason | State Regulatory Compliance | Sent email to Jason to request final stylizing. Started on some styling on my own and stuff Kyle added. Task status changed from Assigned to In Progress.
299 | 29742 | 2015-05-06 18:00 | 6 | final styling with Jason | State Regulatory Compliance | Jason responded back and i started to implement his changes. This was all for state search only. I have not received changes for program search.
299 | 29742 | 2015-05-18 13:50 | 4 | final styling with Jason | State Regulatory Compliance | Continued with the list that Jason gave me to work on for search page. Last time worked on combining State and Program buttons into a single looking control. and began work on placing the 'X' into the search bar as a control. I started back up on that today. It took me sometime but was able to get the look and functionality down. I requested "Not Authorized" changed to "Unathorized".
299 | 29742 | 2015-05-18 13:53 | 8 | final styling with Jason | State Regulatory Compliance | Continued with Jason's list. Worked on new SARA Icon. the one that Jason provided seem to small and Kyle had requested the colored version. I just whipped up something on the fly and committed that. Moved on to changing width of State column sizes. I basically finished up the first list.
299 | 29742 | 2015-05-18 14:21 | 8 | final styling with Jason | State Regulatory Compliance | I attempted to look into some of the more complicated stuff from Jason's list. One of which was the use of a glyphicon that we currently do not have access to. Damien mentioned that he was going to upgrade bootstrap so we may have access to it later. I also worked on adding 'tooltips' to input controls on the details page.
299 | 29742 | 2015-05-18 14:35 | 7 | final styling with Jason | State Regulatory Compliance | Jason gave me a second list to work on for Search and Program pages. Worked on resizing textfields to the HR size. And worked on some responsive stuff that was requested.
299 | 29742 | 2015-05-18 14:57 | 5 | final styling with Jason | State Regulatory Compliance | Continued working on list 2 from Jason. I started to fix layout issues when resizing the screen.
299 | 29742 | 2015-05-18 15:11 | 5 | final styling with Jason | State Regulatory Compliance | Still working on Jason's second list. working on changing label font weight, adding in two column look to icon section so licensure and experiential doesn't look all over the place.
299 | 29742 | 2015-05-18 15:23 | 7 | final styling with Jason | State Regulatory Compliance | finished up Jason's second list. Well almost I still have new glyphicons to implement; but Damien has not updated Bootstrap.
299 | 29742 | 2015-05-20 16:06 | 0.1 | final styling with Jason | State Regulatory Compliance | Kyle is going to give Damien and I new tasks for the finishing of the project. So I will move this task to final review. Task status changed from In Progress to Final Review.
299 | 29744 | 2015-03-26 10:09 | 3 | style add new group tile | State Regulatory Compliance | started work on this button. it's pretty indepth. but i shifted gears after our meeting to work on another task Task status changed from Assigned to In Progress.
299 | 29744 | 2015-04-09 03:21 | 2 | style add new group tile | State Regulatory Compliance | finished up styling for group tile.
299 | 29744 | 2015-04-09 03:21 | 1 | style add new group tile | State Regulatory Compliance | Commited to Dev and email Kyle to test. Task status changed from In Progress to In Testing.
299 | 29744 | 2015-04-09 17:14 | 0.1 | style add new group tile | State Regulatory Compliance | Because a new task had me redesign the original source I am going to final review this task. Kyle never got back to me about this but the new one is in test. Task status changed from In Testing to Final Review.
299 | 29766 | 2015-03-26 09:24 | 1 | Meetings, conversations, etc | State Regulatory Compliance | Meeting with Damien and Sam. Basic review of what we have accomplished so far.
299 | 29766 | 2015-03-26 09:25 | 1 | Meetings, conversations, etc | State Regulatory Compliance | Meeting with Kyle, Damien, and Sam. This meeting was to catch up Kyle he was on vacation for a while.
299 | 29766 | 2015-03-26 09:31 | 1 | Meetings, conversations, etc | State Regulatory Compliance | First talked to Jason, then Damien, about design issues from the design doc. Then later Damien talked to Sam and I about this new task. We can now log meetings and conversations to this task.
299 | 29766 | 2015-04-02 09:36 | 0.5 | Meetings, conversations, etc | State Regulatory Compliance | quick meeting with Kyle
299 | 29766 | 2015-04-09 03:23 | 4 | Meetings, conversations, etc | State Regulatory Compliance | Talked to Damien and discussed what I should be work on next. Later Jason stopped by my desk and we discussed the interstices of the current design for Details Page. This lead to many more questions and clarifications on how the page was meant to be. This means that what I sent to be tested is not the fully correct version of what the page should be.
299 | 29766 | 2015-04-09 03:26 | 4 | Meetings, conversations, etc | State Regulatory Compliance | Had a meeting with Sam and Damien to review what we did. I brought up the conflicting designs I had with the design doc and actual code. Later Damien, Jason, and I sat down and we hashed out the details for how the Details page should be reworked to conform to what we want.
299 | 29766 | 2015-04-16 10:35 | 1 | Meetings, conversations, etc | State Regulatory Compliance | Meeting with Damien and Sam
299 | 29766 | 2015-04-23 13:11 | 1 | Meetings, conversations, etc | State Regulatory Compliance | Meeting with Kyle and Damien
299 | 29766 | 2015-04-29 17:29 | 1 | Meetings, conversations, etc | State Regulatory Compliance | Meeting with Sam, Damien, and Kyle
299 | 29766 | 2015-05-06 15:11 | 1 | Meetings, conversations, etc | State Regulatory Compliance | Meeting with Sam, Kyle, and Damien
299 | 29766 | 2015-05-14 14:19 | 1 | Meetings, conversations, etc | State Regulatory Compliance | Meeting with Kyle, Damien, and Sam
299 | 29766 | 2015-05-18 15:14 | 1 | Meetings, conversations, etc | State Regulatory Compliance | Meeting with Kyle, Sam, and Damien
299 | 29766 | 2015-05-27 16:32 | 1 | Meetings, conversations, etc | State Regulatory Compliance | Meeting with Damien, Kyle, and Sam. Kyle suggested that I (and Sam) can leave this project; Amanda was wanting to start her project. Damien will work with Dalasie to finish up the front end stuff. So I will go ahead and remove myself from this task.
299 | 29915 | 2015-04-09 09:57 | 4 | Details Page, View/Edit State redesign | State Regulatory Compliance | started work on redesigning the edit and view state. this includes pretty much removing the 'monolithic' edit tile view. and going for a edit in place design. Task status changed from Assigned to In Progress.
299 | 29915 | 2015-04-09 09:59 | 8 | Details Page, View/Edit State redesign | State Regulatory Compliance | continued to redesign the views. as i move components around I have to clean up the css classes. this actually helped me clean up the overall layout.
299 | 29915 | 2015-04-09 10:00 | 8 | Details Page, View/Edit State redesign | State Regulatory Compliance | finished up the edit/view states. Included simple jquery methods to show the overall goal.
299 | 29915 | 2015-04-09 10:19 | 1 | Details Page, View/Edit State redesign | State Regulatory Compliance | Committed to dev and emailed Kyle to test. Task status changed from In Progress to In Testing.
299 | 29915 | 2015-04-16 10:36 | 1 | Details Page, View/Edit State redesign | State Regulatory Compliance | Kyle approved the task moving this to final review. Task status changed from In Testing to Final Review.
349 | 30100 | 2015-06-03 16:48 | 8 | Learn how to use Git online for Talbert Tso | Programmer Trng/Develop | started and got through lesson 1 of the GIT stuff
299 | 30121 | 2015-05-27 16:22 | 7 | Final Bug Fixes: Front-End | State Regulatory Compliance | Reviewed document provided again to see if I missed anything. Waiting on Dalasie about new stuff. Task status changed from Assigned to In Progress.
299 | 30121 | 2015-05-27 16:25 | 8 | Final Bug Fixes: Front-End | State Regulatory Compliance | Contacted Dalasie to see if he had new stuff for me. Still attempted little changes to the site for enhancements.
299 | 30121 | 2015-05-27 16:28 | 8 | Final Bug Fixes: Front-End | State Regulatory Compliance | Dalasie did not have a fully developed document for me to work on. But he was able to request some changes. It took me some time but I found a solution.
299 | 30121 | 2015-05-27 16:35 | 5 | Final Bug Fixes: Front-End | State Regulatory Compliance | Dalasie emailed Damien and I; he said he would have a doc for us for styling. I reviewed the page one last time. I then decided to commit what changes I have made. Damien then pushed this to test. We had our meeting and Kyle decided I can be let go from this project. And Damien will finish off styling. I will now move this task to final review. Task status changed from In Progress to Final Review.
86 | 30253 | 2015-05-27 16:38 | 2 | Review code | Admin Connect | Talked to Amanda about this task. Later Damien, Amanda, and I had a quick meeting to discuss the start of this project. We decided to do some code review first then meet again on Friday to flesh out the details of the project. I then pulled up the code to begin review. Task status changed from Assigned to In Progress.
86 | 30253 | 2015-06-03 16:30 | 6 | Review code | Admin Connect | Continued to review the code. I discovered that changing the front end controls and scaffolding is going to be easy. I am now trying to figure out the backend code stuff.
86 | 30253 | 2015-06-03 16:32 | 2 | Review code | Admin Connect | Found the files that integrate with front end. The code is heavily reliant on mustache js. Code wise I can foresee some time needed to learn mustache in depth.
86 | 30253 | 2015-06-03 16:50 | 6 | Review code | Admin Connect | finished reviewing the code. I believe I can confidently complete this task. Task status changed from In Progress to Final Review.
233 | 30274 | 2015-06-03 16:40 | 1 | 2014-2015 Annual Self-Appraisal from Talbert | Programming Staff Appraisals | Worked on updated SQL to pull all relevant TME logs to be used in this years self appraisal. Task status changed from Assigned to In Progress.
233 | 30274 | 2015-06-10 16:25 | 8 | 2014-2015 Annual Self-Appraisal from Talbert | Programming Staff Appraisals | worked to sort my data.
86 | 30285 | 2015-06-10 16:25 | 3 | Add checkbox to delete dialog box | Admin Connect | Took me a while to see the layout but got the check box and label in the correct place. Task status changed from Assigned to In Progress.
86 | 30285 | 2015-06-10 16:37 | 0.1 | Add checkbox to delete dialog box | Admin Connect | Just sent an email to Amanda to test. Task status changed from In Progress to In Testing.
86 | 30285 | 2015-06-18 01:53 | 1 | Add checkbox to delete dialog box | Admin Connect | Amanda approved. I will hold off on one big push to test and prod later. Moving to final review. Task status changed from In Testing to Final Review.
86 | 30288 | 2015-06-10 16:27 | 4 | Scaffolding: add new area below existing list | Admin Connect | began working on this. sorting through the code is much harder than i thought. I needed to stop though to update the AUTHZ thing. Task status changed from Assigned to In Progress.
86 | 30288 | 2015-06-10 16:32 | 4 | Scaffolding: add new area below existing list | Admin Connect | began work on this again but this code is rather loose. declaration of sections start and never really seem to have an end.
86 | 30288 | 2015-06-10 16:33 | 7 | Scaffolding: add new area below existing list | Admin Connect | ok the code is not making any more sense to me. I think i have it figured out. I need to add my new stuff in a js file then somehow add that to the index page. i think.
86 | 30288 | 2015-06-18 02:09 | 5 | Scaffolding: add new area below existing list | Admin Connect | I am getting more lost trying to figure out this code.
86 | 30288 | 2015-06-18 02:16 | 8 | Scaffolding: add new area below existing list | Admin Connect | I have read the code but there is just simply no explanation of variable declaration. I am reading up on mustache.js to see if i can explain this.
86 | 30288 | 2015-06-18 02:44 | 8 | Scaffolding: add new area below existing list | Admin Connect | i have now extensively looked through all the files in the project and I cannot for the life of me figure out how declarations are establish.
86 | 30288 | 2015-06-18 02:46 | 7 | Scaffolding: add new area below existing list | Admin Connect | I have exhausted all my resources i can think of to figure out this code. I emailed out a call for help to fellow programmers. Thankfully Duke responded. He told me that what i was looking at was not fully mustache.js code but something called backbone.js. This was a revelation. I am now looking into backbone.
86 | 30288 | 2015-06-18 03:32 | 8 | Scaffolding: add new area below existing list | Admin Connect | with more help from Duke i found out the declaration area but there is still a lot that is confusing. I am looking into backbone.js. this still seems like a daunting task.
86 | 30288 | 2015-06-24 16:17 | 8 | Scaffolding: add new area below existing list | Admin Connect | Looked a little into backbone.js it is still hard to figure out how things are used and set.
86 | 30288 | 2015-06-24 16:19 | 6 | Scaffolding: add new area below existing list | Admin Connect | Well attempting to write some new code. I think I understand the structure of the files now. hopefully the code will run when im all done. right now I am setting up a new 'DeleteCoordinator' model.
86 | 30288 | 2015-06-24 16:20 | 8 | Scaffolding: add new area below existing list | Admin Connect | Continued working on the model of DeleteCoordinator. I then started to create the views for DeleteCoordinator. I think it would be best if i can replicate 'coordinator_list' and 'coordinator_item' and bind them to the index page after the current list of coordinators.
86 | 30288 | 2015-06-24 16:21 | 8 | Scaffolding: add new area below existing list | Admin Connect | continue to work on views of DeleteCoordinator.
86 | 30292 | 2015-06-03 16:45 | 1 | TCLM meetings | Admin Connect | Met with Amanda to discuss the proposed project timeline. I sat down and worked out an estimated task list with hours. Task status changed from Assigned to In Progress.